## Landing Page
🚀 RELEASE DESK |  | Enterprise Release Management Platform |  | 👤 Welcome, Release Manager ¦ 📅 28/06/2026
📊 Dashboard | 📋 Releases | 📅 Calendar | ⚠️ Risks | ⚙️ Admin
⚡ 3 releases scheduled this week ¦ ⚠️ 2 active conflicts require attention ¦ 🔔 5 pending approvals
📊 QUICK STATS
Welcome to Release Desk
Your central hub for managing releases, tracking risks, coordinating environments, and ensuring successful deployments across the enterprise.
📋 Total Releases
83
📱 Main Pages
⚠️ Active Conflicts
📊 |  | 📋 |  | 📅 | 27
DASHBOARD |  | RELEASES |  | CALENDAR
🚫 Blocked Releases
Real-time KPIs, metrics, |  | Manage all releases, |  | CAB meetings, releases, | 1
and release health overview |  | status, priorities & blockers |  | and key milestones
🔴 P1 Critical
🖥️ |  | ⚠️ |  | 🔗 | 11
ENV BOOKING |  | RISK |  | DEPENDENCIES
📝 Pending CAB
Reserve & manage test |  | Risk scores, factors, |  | Track inter-release | 1
and UAT environments |  | and mitigation tracking |  | and system dependencies
✅ Approved
✅ |  | 🏖️ |  | 📉 | 4
APPROVALS |  | LEAVE CALENDAR |  | DRIFT
CAB approvals and |  | Team availability and |  | Schedule drift analysis
sign-off workflows |  | resource scheduling |  | and timeline tracking | ⚡ QUICK ACTIONS
🔔 Operational Monitoring
➕ Create New Release
🔔 |  | 🚨 |  | 🖥️
MONITORING |  | INCIDENTS |  | APP STATUS | 📅 Book Environment
System alerts, health |  | P1/P2 incident tracking |  | Real-time application | 📋 View All Risks
checks & notifications |  | and resolution status |  | availability by env
🔔 Active Alerts
🔧 |  | 📦 |  | 🗺️
MAINTENANCE |  | VERSIONS |  | SYSTEM MAPPING | 📊 Open Dashboard
Scheduled outages |  | Version history and |  | Environment and system | Last refreshed:
and maintenance windows |  | deployment tracking |  | architecture views | 2026-06-30 00:04
📚 Reference Data (Admin Only)
📱 Applications |  | 👥 Users |  | ⚙️ Admin Config
Master app registry |  | User directory |  | Release Managers & Super Admins
🎨 Color Guide: | 🟢 Dashboard | 🟠 Core Release Pages | 🔵 Monitoring & Ops | 🟣 Resources ¦ 🔴 Risk ¦ 🔷 Reference Data
Release Desk v1.0 ¦ Enterprise Release Management Platform ¦ © 2026 |  |  |  | 📧 Support ¦ 📖 Documentation ¦ 🔒 Security

## Dashboard
| RELEASE DESK DASHBOARD | [7 empty] | Last Refresh:
| 🔍 FILTERS | Time Period: | This Month | Department: | All | Application: | All |  | 2026-06-30 00:04
| 📦 RELEASE PIPELINE |  |  | ⚠️ RELEASE CONFLICTS & RISKS |  |  | 🖥️ ENVIRONMENT BOOKINGS
| Total Releases | 9 |  | Active Conflicts | 6 |  | Env Conflicts | 26
| Blocked | 1 |  | Critical Risk (Score 20+) | 2 |  | Env Bookings Active | 101
| Approved | 4 |  | High Risk (Score 15-19) | 3
| Testing | 3 |  | Medium Risk (Score 10-14) | 12 |  | 🔗 DEPENDENCIES
| Planning | 0 |  | Low Risk (Score <10) | 14 |  | Blocked Dependencies | 5
| Draft | 0 |  |  |  |  | Total Dependencies | 69
| Pending CAB | 1 |  | 📋 CAB & APPROVALS
| P1 - Critical | 2 |  | CAB Meetings (Next 7 Days) | 9 |  | 👥 RESOURCE AVAILABILITY
| P2 - High | 4 |  | Pending Approvals | 2 |  | Staff on Leave Today | 1
| P3 - Medium | 2 |  |  |  |  | Staff on Leave (7 Days) | 4
| P4 - Low | 1
| 🚨 MONITORING ALERTS |  |  | 🔥 INCIDENTS |  |  | 📊 APPLICATION AVAILABILITY
| Critical Alerts (Active) | 11 |  | P1 Incidents (Active) | 4 |  | Apps Down - Production | 4
| Warning Alerts (Active) | 16 |  | P2 Incidents (Active) | 6 |  | Apps Degraded - Production | 5
| Info Alerts (Active) | 2 |  | P3 Incidents (Active) | 3 |  | Apps Healthy - Production | 11
| Acknowledged | 5 |  | Investigating | 4 |  | Apps Down - Lower Env | 5
| Resolved (Last 24h) | 0 |  | Resolved (Last 24h) | 0 |  | Apps Degraded - Lower Env | 3
| Total Active Alerts | 34 |  | Total Active Incidents | 13 |  | Total App-Env Records | 85
| 🔧 PLANNED MAINTENANCE |  |  | ❄️ CHANGE FREEZE |  |  | 📈 QUICK STATS
| Scheduled Today | 2 |  | Quarter-End Freeze | 1 |  | Releases This Week | 5
| DB Refreshes (30 Days) | 4 |  | Year-End Freeze | 0 |  | Releases This Month | 9
| Vendor Windows (30 Days) | 4 |  | Audit Freeze | 0 |  | With Rollback Plan Ready | 4
| Full Outages (30 Days) | 7 |  | Holiday Freeze | 0 |  | Rollback At Risk | 1
| Total Maintenance (30 Days) | 15 |  | Total Frozen Releases | 1 |  | Avg Go-Live Checklist % | 18%
🚦 OVERALL HEALTH STATUS
| Release Pipeline |  | Environment Health |  | Incident Status |  | Alert Status
| 🟡 Warning |  | 🔴 Critical |  | 🔴 Critical |  | 🔴 Critical
📊 SUMMARY TOTALS
| Total Releases | 9 | Active Incidents | 13 | Active Alerts | 34 | Apps Down | 9
📈 RELEASE TREND (Next 4 Weeks)
| Week 1 | Week 2 | Week 3 | Week 4 | Trend
Releases | 5 | 1 | 3 | 0 | 📉 ↓ Decreasing
| █████ | █ | ███
Incidents | P1 | P2 | P3 | Total | Trend
| 4 | 6 | 3 | 13 | 🔴 P1 Active!
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: RELEASE DESK DASHBOARD: Enterprise Release Management Dashboard for real-time visibility.
Note on J1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Last Refresh: Auto-updates when workbook recalculates.
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 🔍 FILTERS: Use dropdowns to filter all dashboard metrics.
Note on D2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Time Period: All Time ¦ Today ¦ This Week ¦ This Month ¦ This Year
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Department: Filter by department or select 'All'.
Note on H2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Application: Filter by application or select 'All'.
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 📦 RELEASE PIPELINE Overview of all releases in the system, filtered by your selected time period, department, and application.
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ⚠️ RELEASE CONFLICTS & RISKS Identifies scheduling conflicts and risk levels. High numbers indicate potential deployment issues.
Note on H4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 🖥️ ENVIRONMENT BOOKINGS: Test and UAT environment utilization tracking.
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Releases: The complete count of all releases matching your current filter criteria. Includes all statuses.
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Active Conflicts: Releases with scheduling or resource conflicts (overlapping windows, shared environments).
Note on H5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Env Conflicts: Environment booking conflicts requiring scheduling resolution.
Note on B6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Blocked: Releases that are currently blocked and cannot proceed. Require immediate attention.
Note on E6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Critical Risk (20+): Requires executive attention and detailed mitigation plans.
Note on H6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Env Bookings Active: Total active environment reservations.
Note on B7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Approved: Releases that have received all necessary approvals and are cleared for deployment.
Note on E7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: High Risk (15-19): Elevated risk, requires additional review and contingency planning.
Note on B8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Testing: Releases currently in the testing phase (unit, integration, QA).
Note on E8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Medium Risk (10-14): Moderate risk, standard change management applies.
Note on H8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 🔗 DEPENDENCIES: Inter-release and system dependencies affecting scheduling.
Note on B9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Planning: Releases in planning stage. Requirements and scheduling being finalized.
Note on E9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Low Risk (<10): Minimal risk, routine changes with proven rollback.
Note on H9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Blocked Dependencies: Dependencies blocking release progress.
Note on B10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Draft: Releases in draft status. Initial documentation being prepared.
Note on H10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Dependencies: All tracked upstream/downstream dependencies.
Note on B11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending CAB: Releases awaiting Change Advisory Board review and approval.
Note on E11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 📋 CAB & APPROVALS: Change Advisory Board meeting schedule and approval pipeline.
Note on B12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: P1 - Critical: Highest priority. Security patches, critical fixes. Target SLA: 24-48 hours.
Note on E12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CAB Meetings: Number of CAB meetings scheduled within selected time period.
Note on H12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 👥 RESOURCE AVAILABILITY: Staff availability for release activities.
Note on B13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: P2 - High: Significant business impact. Target SLA: 1-2 weeks.
Note on E13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending Approvals: Releases awaiting approval (CAB review or sign-offs).
Note on H13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Staff on Leave Today: Team members on leave today.
Note on B14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: P3 - Medium: Planned enhancements, non-critical fixes. Target SLA: 2-4 weeks.
Note on H14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Staff on Leave (7 Days): Total leave days in next 7 days.
Note on B15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: P4 - Low: Minor improvements, cosmetic changes. Target SLA: 4-8 weeks.
Note on B17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 🚨 MONITORING ALERTS: Real-time infrastructure and application alerts.
Note on E17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 🔥 INCIDENTS: Active incidents affecting production and non-production environments.
Note on H17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 📊 APPLICATION AVAILABILITY: Real-time health status across all environments.
Note on B18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Critical Alerts: CRITICAL severity. Requires immediate action (<15 min response).
Note on E18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: P1 Incidents: Severity 1 - Critical. Major business impact. Target: <4 hours.
Note on H18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Apps Down - Production: 🔴 CRITICAL. Production apps unavailable. Immediate business impact.
Note on B19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Warning Alerts: WARNING severity. Potential issue developing (<1 hour response).
Note on E19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: P2 Incidents: Severity 2 - High. Significant impact. Target: <8 hours.
Note on H19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Apps Degraded - Production: 🟡 WARNING. Reduced functionality or performance.
Note on B20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Info Alerts: INFO severity. Informational notifications.
Note on E20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: P3 Incidents: Severity 3 - Medium. Minor impact. Target: <24 hours.
Note on H20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Apps Healthy - Production: 🟢 HEALTHY. Operating normally.
Note on B21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Acknowledged: Alerts acknowledged by ops team, under investigation.
Note on E21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Investigating: Incidents under active investigation.
Note on H21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Apps Down - Lower Env: Non-production apps unavailable. May block testing.
Note on B22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Resolved (24h): Alerts resolved in past 24 hours.
Note on E22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Resolved (24h): Incidents resolved in past 24 hours.
Note on H22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Apps Degraded - Lower Env: Non-production apps with issues.
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Active Alerts: Sum of all unresolved alerts. Key health indicator.
Note on E23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Active Incidents: All unresolved incidents. Key operational health indicator.
Note on H23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total App-Env Records: Total application-environment combinations monitored.
Note on B26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 🔧 PLANNED MAINTENANCE: Scheduled maintenance windows and infrastructure activities.
Note on E26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ❄️ CHANGE FREEZE: Releases affected by freeze periods. No deployments except emergencies.
Note on H26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 📈 QUICK STATS: Key release metrics and readiness indicators for executive overview.
Note on B27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scheduled Today: Maintenance activities scheduled for today.
Note on E27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Quarter-End Freeze: Releases during quarter-end (finance system lockdown).
Note on H27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Releases This Week: Releases scheduled in next 7 days. Capacity planning metric.
Note on B28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DB Refreshes: Database refresh activities (copies prod data to lower envs).
Note on E28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Year-End Freeze: Releases during year-end (Dec-Jan annual close).
Note on H28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Releases This Month: Releases scheduled in next 30 days. Monthly planning metric.
Note on B29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Vendor Windows: Vendor-scheduled maintenance for SaaS/cloud apps.
Note on E29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Audit Freeze: Releases during audit periods (maintain audit trail).
Note on H29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Rollback Plan Ready: Releases with documented, tested rollback plans. Target: 100%.
Note on B30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Full Outages: Activities causing complete service unavailability.
Note on E30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Holiday Freeze: Releases during holidays (reduced staffing).
Note on H30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Rollback At Risk: Releases with at-risk rollback plans. Need attention.
Note on B31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Maintenance: All scheduled maintenance in selected period.
Note on E31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Frozen Releases: All releases needing reschedule or exception approval.
Note on H31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Avg Go-Live Checklist %: Average checklist completion. Target: >90% before deploy.
Note on B35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 🚦 OVERALL HEALTH STATUS: RAG indicators showing system health at a glance.
Note on B36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Release Pipeline: 🟢=0 blocked ¦ 🟡=1-2 blocked ¦ 🔴=>2 blocked
Note on D36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Environment Health: 🟢=0 apps down ¦ 🟡=1 down ¦ 🔴=>2 down
Note on F36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Incident Status: 🟢=0 P1 ¦ 🟡=1 P1 ¦ 🔴=>2 P1
Note on H36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Alert Status: 🟢=0 critical ¦ 🟡=1-5 critical ¦ 🔴=>5 critical
Note on B39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 📊 SUMMARY TOTALS: Quick reference totals for executive overview.
Note on B40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total Releases: Count of all releases matching current filters.
Note on D40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Active Incidents: Total unresolved incidents (P1+P2+P3).
Note on F40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Active Alerts: Total unresolved monitoring alerts.
Note on H40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Apps Down: Total unavailable apps (Production + Lower Environments).
Note on B42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 📈 RELEASE TREND: Visualization of release volume over next 4 weeks.
Note on F44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Trend Direction: 📈=Increasing ¦ 📉=Decreasing ¦ ➡️=Stable
Note on F47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Incident Trend: 🔴=P1 Active ¦ 🟠=Watch P2 ¦ 🟢=Stable

## README
═══════════════════════════════════════════════════════════════════════════════════════════════════════════════════
RELEASEDESK - SAMPLE DATA SPECIFICATION FOR PROTOTYPE BUILDER
═══════════════════════════════════════════════════════════════════════════════════════════════════════════════════
DOCUMENT PURPOSE
This workbook provides structured sample/seed data for a Release Management System prototype.
It is designed to be parsed and interpreted by an AI/Machine that generates wireframes and UI prototypes.
Each sheet represents a distinct data entity with defined schemas, relationships, and business rules.
HOW TO USE THIS DOCUMENT
1. Start with this README to understand the data model and relationships
2. Reference the 'Reference Data' sheet for all lookup values, status codes, and enumeration tables
3. Each data sheet has a defined schema (column headers in Row 1 or as specified)
4. Foreign keys (FK) link entities - always validate relationships exist
5. Business rules and validation logic are documented per entity below
QUICK NAVIGATION BY AUDIENCE:
┌──────────────────────────┬───────────────────────────────────────────────────────────────────────┐
│ 🎨 WIREFRAME BUILDERS │ Focus on: Sections 5, 6, 7 ¦ Skip: Sections 3, 4, 8 │
│ 💻 BACKEND DEVELOPERS │ Use: 'Technical Specifications' sheet for schema, FK/PK, validation │
│ 📋 EVERYONE │ Start: Section 2 (Sheet Inventory) for navigation │
└──────────────────────────┴───────────────────────────────────────────────────────────────────────┘
═══════════════════════════════════════════════════════════════════════════════════════════════════════════════════
SECTION 1: WORKBOOK OVERVIEW & STATISTICS
═══════════════════════════════════════════════════════════════════════════════════════════════════════════════════
ENTITY COUNTS (for prototype sizing)
Entity | Count | Primary Key | Source Sheet
Departments | 8 | DEPT-## | Reference Data (Row 40)
Applications | 84 | Composite (Dept+App) | Applications
Environment Instances | 504 | Composite (App+Env) | Applications (84 apps × 6 envs)
Users | 100 | USR-### | Users
Release Managers | 12 | RM-### | Admin (Release Managers)
Super Admins | 12 | SA-### | Super Admins
Releases | 80 | REL-#### | Releases
Environment Bookings | 80+ | ENV-#### | Env booking
Calendar Events | 166 | Row-based | Calendar
Risk Records | 31 | RSK-### | Risk
Drift Issues | 7 | DFT-### | Drift
Dependencies | 26 | DEP-### | Dependencies
Approvals | 27 | APR-### | Approvals
Leave Records | 30 | LV-### | Leave Calendar
Version Records | 180 | APP-### | Versions
Risk Factors | 44-46 | Category+Factor | Risk Factors
TIME SPAN
Release Calendar Period: July 2026 - June 2027 (12 months)
Simulated 'Today' Date: June 25, 2026
KEY METRICS FOR PROTOTYPE
Conflict Rate: ~32% (26 releases have resource conflicts)
Environments per Application: 6 (Dev, Test, UAT, Pre-prod, Prod, DR)
Average Releases per Month: 6-7
Risk Score Range: 1-25 (Likelihood × Impact)
═══════════════════════════════════════════════════════════════════════════════════════════════════════════════════
SECTION 2: SHEET INVENTORY & NAVIGATION
═══════════════════════════════════════════════════════════════════════════════════════════════════════════════════
SHEET INDEX (in logical order)
# | Sheet Name | Range | Rows | Purpose | UI Screen Suggestion
0 | Landing Page | A1:H60 | 60 | Web application home page with navigation | Home Page, Entry Point
1 | Dashboard | A1:J47 | 47 | Real-time metrics and status overview | Executive Dashboard
2 | README | A1:F489 | 489 | User guide for wireframe/prototype builders | Help, Documentation
3 | Technical Specifications | A1:F309 | 309 | Database schema, FK/PK for developers | Developer Reference
4 | Reference Data | A1:F244 | 244 | All lookup tables & enums | Admin Settings, Dropdowns
5 | Applications | A1:F505 | 505 | Master app inventory (84 apps × 6 envs) | Application Catalog
6 | Users | A1:I101 | 101 | 100 users across roles | User Management, Directory
7 | Admin (Release Managers) | A1:I13 | 13 | 12 release managers | RM Admin Panel
8 | Super Admins | A1:K15 | 15 | 12 elevated-privilege admins | System Admin Panel
9 | Releases | A1:AC84 | 84 | 80 releases (core transactional data) | Release Dashboard, Pipeline
10 | Calendar | A1:J180 | 180 | 166+ events (releases, CAB, freezes) | Calendar View, Gantt Chart
11 | Env booking | A1:V115 | 115 | Environment scheduling with conflicts | Resource Planner, Booking Grid
12 | Risk Factors | A1:AX227 | 227 | Risk scoring weights and calculations | Risk Configuration
13 | Risk | A1:T118 | 118 | Active risks for releases | Risk Register, Heat Map
14 | Drift | A1:N74 | 74 | Environment/config drift issues | Drift Dashboard
15 | Dependencies | A1:K95 | 95 | Release-to-release dependencies | Dependency Graph
16 | Approvals | A1:L95 | 95 | CAB approval workflow records | Approval Workflow
17 | Leave Calendar | A1:L92 | 92 | Leave records affecting releases | Resource Availability
18 | Versions | A1:J242 | 242 | Version tracking across environments | Version Dashboard
19 | System Mapping | A1:K195 | 195 | Integration architecture diagram | System Map, Integrations
20 | Monitoring Alerts | A1:L122 | 122 | System alerts and notifications | Alerts Dashboard
21 | Incidents | A1:K86 | 86 | Incident tracking and resolution | Incident Management
22 | Application Status | A1:G105 | 105 | Real-time application health | Health Status Dashboard
23 | Planned Maintenance | A1:L89 | 89 | Scheduled maintenance windows | Maintenance Calendar
═══════════════════════════════════════════════════════════════════════════════════════════════════════════════════
SECTION 3: TECHNICAL SPECIFICATIONS
═══════════════════════════════════════════════════════════════════════════════════════════════════════════════════
📋 FOR TECHNICAL DETAILS (Entity Relationships, Foreign Keys, Data Types, Validation Rules):
→ See the 'Technical Specifications' sheet (Sheet #3)
This README focuses on helping wireframe/prototype builders understand:
• What each sheet contains (Section 2: Sheet Inventory)
• Business rules and workflows (Section 4)
• UI screen suggestions (Section 5)
• Test scenarios for prototypes (Section 6)
═══════════════════════════════════════════════════════════════════════════════════════════════════════════════════
SECTION 4: BUSINESS RULES & SIMULATION SCENARIOS
═══════════════════════════════════════════════════════════════════════════════════════════════════════════════════
CONFLICT DETECTION RULES
─────────────────────────────────────────────────────────────────────────────────────────────────────────────────────
• Two releases CONFLICT if they require the same SME or critical resource during overlapping periods
• Cross-reference: Leave Calendar affects resource availability during release phases
• Stakeholder IDs in Releases sheet indicate which users are involved
Rule 3: Dependency Conflict
• A release CANNOT proceed if its predecessor (Dependencies.Depends On Release) is blocked or delayed
• Status must be 'Satisfied' before dependent release can enter Testing phase
CHANGE FREEZE RULES
─────────────────────────────────────────────────────────────────────────────────────────────────────────────────────
Freeze Period | Dates | Rule
Year-End Freeze | Dec 15, 2026 - Jan 5, 2027 | NO production deployments; exceptions require VP approval
Q1 Quarter-End | Mar 29-31, 2027 | LIMITED deployments; only critical/regulatory allowed
Q2 Quarter-End | Jun 28-30, 2027 | LIMITED deployments; only critical/regulatory allowed
• Releases with Regulatory='GDPR/SOX/SOC2' may request freeze exemption
• All freeze exemptions require documented business justification and CAB approval
CAB APPROVAL WORKFLOW
─────────────────────────────────────────────────────────────────────────────────────────────────────────────────────
Workflow Stages:
Stage | Description | Required Actions
1. Draft | Release created, initial planning | Complete release scope and impact assessment
2. Planning | Detailed planning underway | Assign resources, define test strategy
3. Testing | Test phase in progress | Complete all test cases, document results
4. CAB Submitted | Submitted for CAB review | Package sent 2-3 days before CAB date
5. CAB Approved | Approved by Change Advisory Board | Proceed to deployment preparation
6. Deploying | Deployment in progress | Execute deployment runbook
7. Deployed | Successfully deployed to production | Verify deployment, monitor
8. PIR Complete | Post-Implementation Review done | Lessons learned documented
9. Closed | Release officially closed | All artifacts archived
CAB Lead Time Requirements:
• Large releases: 3 days before Prod date
• Medium/Small releases: 2 days before Prod date
RISK CALCULATION METHODOLOGY
─────────────────────────────────────────────────────────────────────────────────────────────────────────────────────
Simple Risk Score (Risk sheet):
Risk Score = Likelihood (1-5) × Impact (1-5) = 1-25
Weighted Risk Score (Risk Factors sheet):
Weighted Score = Σ (Factor Score × Factor Weight) for all 44-46 factors
Each factor scored 1-5, weights sum to 100%
Final score range: 1.00 - 5.00
Risk Action Thresholds:
Simple Score | Weighted Score | Level | Required Action
46027 | 1.00-2.00 | Low | Monitor monthly
46184 | 2.01-3.00 | Medium | Active mitigation required
46375 | 3.01-4.00 | High | Escalate to senior management
20-25 | 4.01-5.00 | Critical | Stop release, remediate immediately
═══════════════════════════════════════════════════════════════════════════════════════════════════════════════════
SECTION 5: UI SCREEN MAPPING SUGGESTIONS FOR PROTOTYPE
═══════════════════════════════════════════════════════════════════════════════════════════════════════════════════
The following suggestions map Excel sheets to potential UI screens/wireframes:
CORE OPERATIONAL SCREENS
─────────────────────────────────────────────────────────────────────────────────────────────────────────────────────
Screen Name | Primary Data Source | Key Features | User Role
Release Dashboard | Releases sheet | Pipeline view, status cards, KPIs, filters by dept/status/priority | Release Manager, All Users
Release Detail View | Releases + Env booking + Risk + Dependencies | Single release deep-dive, all related data, edit capability | Release Manager
Environment Booking Grid | Env booking sheet | Gantt-style timeline, conflict highlighting, drag-drop reschedule | Release Manager
Calendar View | Calendar sheet | Month/week view, release markers, freeze periods, CAB dates | All Users
Risk Register | Risk sheet | Sortable table, risk heat map, mitigation tracking | Release Manager, Risk Owner
Drift Dashboard | Drift sheet | Open issues list, severity indicators, remediation status | Release Manager, Tech Lead
APPROVAL & WORKFLOW SCREENS
─────────────────────────────────────────────────────────────────────────────────────────────────────────────────────
Screen Name | Primary Data Source | Key Features | User Role
CAB Meeting View | Approvals + Releases | Agenda items, vote tracking, decision history | CAB Members, Release Manager
Approval Queue | Approvals sheet | Pending approvals list, approve/reject actions | Approvers
Workflow Status | Releases.Approval Status | Visual workflow stages, progress tracking | Release Manager
CONFIGURATION & ADMIN SCREENS
─────────────────────────────────────────────────────────────────────────────────────────────────────────────────────
Screen Name | Primary Data Source | Key Features | User Role
Application Catalog | Applications sheet | Searchable app list, env owners, filtering | All Users
User Management | Users sheet | User list, role assignment, status management | Admin
Release Manager Portal | Admin (Release Managers) sheet | RM directory, specializations, workload view | Admin, Release Manager
Super Admin Console | Super Admins sheet | Elevated access management, audit trail | Super Admin
Risk Factor Configuration | Risk Factors sheet | Edit weights, factor definitions, scoring rules | Admin, Risk Manager
Reference Data Admin | Reference Data sheet | Manage dropdowns, status codes, lookup values | Admin
ANALYTICS & REPORTING SCREENS
─────────────────────────────────────────────────────────────────────────────────────────────────────────────────────
Screen Name | Primary Data Source | Key Features | User Role
Version Dashboard | Versions sheet | Version comparison across envs, deployment history | Release Manager, Dev
System Integration Map | System Mapping sheet | Visual integration diagram, dependency exploration | Architect, All Users
Leave Impact Report | Leave Calendar + Releases | Resource availability, release risk assessment | Release Manager
Dependency Graph | Dependencies sheet | Visual release dependency network, critical path | Release Manager
Conflict Resolution Queue | Env booking (Conflict=Y) | Filtered list of conflicts, resolution actions | Release Manager
MOBILE / QUICK-VIEW SCREENS
─────────────────────────────────────────────────────────────────────────────────────────────────────────────────────
Screen Name | Primary Data Source | Key Features | User Role
My Releases | Releases (filtered by owner) | Personal release list, quick status update | Release Owner
Today's Events | Calendar (filtered by date) | Day view of releases, meetings, freezes | All Users
My Approvals | Approvals (filtered by approver) | Pending approvals requiring my action | Approvers
Risk Alerts | Risk (High/Critical) | Push notifications for escalated risks | Release Manager, Risk Owner
═══════════════════════════════════════════════════════════════════════════════════════════════════════════════════
SECTION 6: SIMULATION SCENARIOS FOR PROTOTYPE TESTING
═══════════════════════════════════════════════════════════════════════════════════════════════════════════════════
The sample data includes realistic scenarios for testing the prototype. Each scenario represents a challenge a
Release Manager would face in a real enterprise environment.
SCENARIO 1: ENVIRONMENT CONFLICTS (~32% of releases)
─────────────────────────────────────────────────────────────────────────────────────────────────────────────────────
Data Location: Env booking sheet where Conflict Flag = 'Y'
Challenge: Multiple releases need the same Test/UAT environment at the same time
Expected Action: Release Manager negotiates reschedule, expands capacity, or prioritizes by business impact
Sample Releases: Look for REL-0002, REL-0005, REL-0008, etc. (26 total conflicts)
SCENARIO 2: CHANGE FREEZE VIOLATIONS
─────────────────────────────────────────────────────────────────────────────────────────────────────────────────────
Data Location: Releases sheet where Change Freeze column is not blank
Challenge: 7 releases are scheduled during freeze periods
Freeze Periods: Year-End (Dec 15 - Jan 5), Q1 End (Mar 29-31), Q2 End (Jun 28-30)
Expected Action: Reschedule release or obtain VP-level exemption approval
SCENARIO 3: DEPENDENCY BLOCKING
─────────────────────────────────────────────────────────────────────────────────────────────────────────────────────
Data Location: Dependencies sheet where Status = 'Blocked' or 'At Risk'
Challenge: Child release cannot proceed until parent is complete
Expected Action: Expedite parent release, adjust child timeline, or decouple dependency
Sample: Check DEP-003, DEP-007 for blocked dependencies
SCENARIO 4: HIGH-RISK RELEASES
─────────────────────────────────────────────────────────────────────────────────────────────────────────────────────
Data Location: Risk sheet where Risk Score >= 12 (High/Critical)
Challenge: Releases with elevated risk requiring additional mitigation
Expected Action: Implement mitigation strategies, escalate to leadership, consider delay
Sample: Look for RSK-001, RSK-005 (Risk Score 20+)
SCENARIO 5: RESOURCE UNAVAILABILITY
─────────────────────────────────────────────────────────────────────────────────────────────────────────────────────
Data Location: Leave Calendar where Risk Score = 'Critical' or 'High'
Challenge: Key personnel on leave during critical release phases
Expected Action: Identify backup resources, adjust release timing, cross-train team
Sample: 5 Critical risk leaves, 10 High risk leaves affecting 40+ releases
SCENARIO 6: ENVIRONMENT DRIFT
─────────────────────────────────────────────────────────────────────────────────────────────────────────────────────
Data Location: Drift sheet
Challenge: Test/UAT environments don't match Production configuration
Expected Action: Remediate drift before proceeding, accept risk with documentation
Sample: 7 drift issues affecting REL-0004 and REL-0010 (Infrastructure, Config, Data, Integration, Security)
SCENARIO 7: CAB APPROVAL BOTTLENECK
─────────────────────────────────────────────────────────────────────────────────────────────────────────────────────
Data Location: Approvals sheet where Decision = 'Pending'
Challenge: Multiple releases awaiting CAB approval, limited meeting slots
Expected Action: Batch similar releases, prepare comprehensive packages, schedule special CAB
Sample: Check pending approvals with upcoming CAB dates
SCENARIO 8: REGULATORY COMPLIANCE
─────────────────────────────────────────────────────────────────────────────────────────────────────────────────────
Data Location: Releases sheet where Regulatory is not blank (GDPR, SOX, SOC2)
Challenge: 8 releases have compliance requirements with strict deadlines
Expected Action: Prioritize regulatory releases, ensure audit trail, document compliance
SCENARIO 9: LOW READINESS RELEASES
─────────────────────────────────────────────────────────────────────────────────────────────────────────────────────
Data Location: Releases sheet where Readiness % < 75%
Challenge: Releases approaching deadline with incomplete preparation
Expected Action: Escalate blockers, reduce scope, defer to next release window
SCENARIO 10: VENDOR MAINTENANCE WINDOWS
─────────────────────────────────────────────────────────────────────────────────────────────────────────────────────
Data Location: Releases sheet where Vendor Maintenance is not blank
Challenge: 2 releases coincide with Oracle patch windows
Expected Action: Coordinate timing with vendor, adjust deployment window
═══════════════════════════════════════════════════════════════════════════════════════════════════════════════════
SECTION 7: DOCUMENT METADATA
═══════════════════════════════════════════════════════════════════════════════════════════════════════════════════
Field | Value
Document Title | ReleaseDesk Sample Data Specification
Version | 2
Generated | 46198
Purpose | Machine-readable specification for prototype/wireframe generation
Data Period | July 2026 - June 2027
Total Sheets | 17
Total Data Rows | ~2,500 (excluding headers and metadata)
NOTES FOR PROTOTYPE BUILDER
─────────────────────────────────────────────────────────────────────────────────────────────────────────────────────
• All data is fictional and for demonstration purposes only
• Company names, applications, and user names are examples representing typical enterprise scenarios
• The ~32% conflict rate simulates real-world resource contention challenges
• Risk scores and readiness percentages vary to create realistic testing scenarios
• Date ranges span 12 months to show full annual release cycle patterns
• The Reference Data sheet should be used to populate all dropdown menus
• Foreign key relationships must be validated on data entry
• Workflow states should be enforced (cannot skip stages)
═══════════════════════════════════════════════════════════════════════════════════════════════════════════════════
SECTION 8: RECENT ENHANCEMENTS & NEW FEATURES (June 2026)
═══════════════════════════════════════════════════════════════════════════════════════════════════════════════════
This section documents enhancements made to improve usability, documentation, and web application readiness.
───────────────────────────────────────────────────────────────────────────────────────────────────────────────────
9.1 LANDING PAGE (NEW)
───────────────────────────────────────────────────────────────────────────────────────────────────────────────────
A new Landing Page sheet has been added as the application entry point, designed to resemble a web application homepage.
Features:
• Header bar with Release Desk branding and user welcome message
• Navigation bar with quick links to main sections
• Alert banner showing live notifications (releases scheduled, conflicts, pending approvals)
• Hero section with welcome message and platform description
• Navigation cards organized by function:
- Main Pages: Dashboard, Releases, Calendar, Env Booking, Risk, Dependencies, Approvals, Leave Calendar, Drift
- Operational Monitoring: Monitoring Alerts, Incidents, Application Status, Maintenance, Versions, System Mapping
- Reference Data (Admin Only): Applications, Users, Admin Config
• Quick Stats panel with live formulas showing real-time metrics from the workbook
• Quick Actions panel for common tasks
• Color-coded cards indicating page categories:
- Green: Dashboard (main operational view)
- Orange: Core release management pages
- Red: Risk and incident tracking (requires attention)
- Purple: Resource management (Leave Calendar)
- Blue/Teal: Monitoring and operations
- Dark Blue: Reference data (admin only)
• Footer with version info and support links
───────────────────────────────────────────────────────────────────────────────────────────────────────────────────
9.2 HYBRID DOCUMENTATION STRUCTURE
───────────────────────────────────────────────────────────────────────────────────────────────────────────────────
All operational pages now include a two-tier documentation system designed for web display:
QUICK REFERENCE SECTION (Green Header)
• Collapsible by default in web UI
• Provides at-a-glance information for experienced users
• Includes: key formulas, severity guides, decision rules, important warnings
• Ends with a link: '[▼ Full documentation below]'
FULL DOCUMENTATION SECTION (Blue Header)
• Expandable for new users or detailed reference
• Comprehensive explanations with multiple subsections
• Includes: purpose, methodology, interpretation guides, decision frameworks, examples
• Section headers use emojis for visual scanning (🎯📊🚦✅⚠️)
SHEETS WITH HYBRID DOCUMENTATION:
Sheet Name | Quick Ref Rows | Full Doc Rows | Topic
Risk | 38-50 | 53-118 | Risk scoring methodology and interpretation
Risk Factors | 150-163 | 166-227 | Risk factor weights and assessment criteria
Drift | 15-25 | 27+ | Schedule drift analysis and remediation
Dependencies | 32-40 | 42+ | Release dependency management
Approvals | 33-41 | 43+ | CAB approval workflow
Leave Calendar | 36-44 | 46+ | Resource availability planning
Versions | 184-192 | 194+ | Version tracking and deployment history
System Mapping | 131-139 | 141+ | Integration architecture
Monitoring Alerts | 44-52 | 54+ | Alert management and response
Incidents | 22-30 | 32+ | Incident tracking and resolution
Application Status | 40-48 | 50+ | Application health monitoring
Planned Maintenance | 24-32 | 34+ | Maintenance window coordination
───────────────────────────────────────────────────────────────────────────────────────────────────────────────────
9.3 WEB UI IMPLEMENTATION GUIDELINES
───────────────────────────────────────────────────────────────────────────────────────────────────────────────────
For web application developers implementing this prototype:
QUICK REFERENCE DISPLAY:
• Render as a collapsible accordion panel at the top of each page
• Default state: collapsed (showing only header 'Quick Reference')
• Green color scheme (#2E7D32 header, #E8F5E9 background)
• Include expand/collapse toggle icon
FULL DOCUMENTATION DISPLAY:
• Render as expandable section below main content
• Default state: collapsed or as a 'Help' link/button
• Blue color scheme (#1F4E79 header, #F8F9FA background)
• Consider side panel or modal for larger documentation
COLOR CODING STANDARDS:
• Green (#4EA72E): Dashboard, success states, approved items
• Orange (#E97132): Core release pages, warning states
• Red (#C00000): Risk, incidents, critical alerts
• Purple (#7030A0): Resource management, leave tracking
• Teal (#008B8B): Monitoring, operational pages
• Dark Blue (#156082): Reference data, admin-only pages
NAVIGATION STRUCTURE:
• Landing Page serves as home/entry point
• Main navigation: Dashboard > Releases > Calendar > Risk
• Secondary navigation: Operational pages (Monitoring, Incidents, etc.)
• Admin section: Reference data pages (visible to admins only)
───────────────────────────────────────────────────────────────────────────────────────────────────────────────────
9.4 DASHBOARD & RISK FACTOR DATA NOTES
───────────────────────────────────────────────────────────────────────────────────────────────────────────────────
DASHBOARD DATA (Sheet: Dashboard):
• All metrics are formula-driven, pulling live data from other sheets
• Filters (Department, Priority, Status) affect displayed metrics dynamically
• Charts and KPIs update automatically as release data changes
RELEASE RISK ASSESSMENT DATA (Sheet: Risk Factors, rows 67-145):
• Contains calculated risk scores for IMMEDIATE RELEASES ONLY (next 14 days)
• Cannot calculate risk assessment for releases far in the future (data not available)
• IMPORTANT: Dashboard filters DO NOT apply to this table
• This data is independent and shows risk assessment for all upcoming releases regardless of filter
• Use this for immediate go/no-go decisions on releases within the assessment window
LANDING PAGE QUICK STATS:
• Uses live formulas (COUNTA, COUNTIF) referencing the Releases sheet
• Stats update automatically as data changes
• Includes: Total Releases, Active Conflicts, Blocked Releases, P1 Critical, Pending CAB, Approved
───────────────────────────────────────────────────────────────────────────────────────────────────────────────────
9.5 CHANGE LOG
───────────────────────────────────────────────────────────────────────────────────────────────────────────────────
Date | Version | Change | Impact
46201 | 1.1 | Added Landing Page sheet | New entry point for web application
46201 | 1.1 | Added Quick Reference sections to 12 sheets | Improved usability with collapsible help
46201 | 110% | Enhanced Full Documentation guides | Comprehensive help for all operational pages
46201 | 110% | Updated README with new sections | Documentation of all enhancements
46201 | 110% | Release Calendar legend added | Visual guide for calendar event types
46201 | 110% | Risk Factor documentation clarified | Notes about immediate release calculations
═══════════════════════════════════════════════════════════════════════════════════════════════════════════════════
END OF SPECIFICATION
═══════════════════════════════════════════════════════════════════════════════════════════════════════════════════

## Technical Specifications
TECHNICAL SPECIFICATIONS - Release Desk Data Dictionary
PURPOSE OF THIS DOCUMENT
═══════════════════════════════════════════════════════════════════════════════════════════════════════════════════════════════════════════
This sheet contains technical specifications for developers building the Release Desk application.
CONTENTS:
• Data types, Primary Keys (PK), and Foreign Keys (FK) for each table/sheet
• Entity relationship diagrams showing how data connects
• Validation rules and integrity constraints
• Cardinality (1:1, 1:M, M:M relationships)
WHO SHOULD USE THIS:
• Backend developers implementing the database schema
• API developers creating endpoints
• Data engineers setting up integrations
FOR WIREFRAME/PROTOTYPE BUILDERS:
Refer to the README sheet instead - it focuses on UI screens, business rules, and user workflows.
This technical sheet is NOT required for creating wireframes or UI mockups.
═══════════════════════════════════════════════════════════════════════════════════════════════════════════════════════════════════════════
SECTION 1: ENTITY RELATIONSHIPS (DATA MODEL)
═══════════════════════════════════════════════════════════════════════════════════════════════════════════════════
This diagram shows how the data entities connect across the Release Desk system.
PRIMARY ENTITIES & FOREIGN KEY RELATIONSHIPS
┌─────────────────────┐ ┌─────────────────────┐ ┌─────────────────────┐
│ DEPARTMENTS │◄─────────│ APPLICATIONS │◄─────────│ RELEASES │
│ (Reference Data │ 1:M │ (Applications │ M:1 │ (Releases │
│ Sheet) │ │ Sheet) │ │ Sheet) │
│ PK: Dept Code │ │ FK: Department │ │ PK: Release ID │
└─────────────────────┘ │ Composite PK │ │ FK: Application │
└─────────────────────┘ │ FK: Department │
│ │ FK: Release Owner │
│ 1:M └─────────────────────┘
▼ │
┌─────────────────────┐ │ 1:M
│ ENVIRONMENTS │ │
│ (6 per Application)│ ▼
│ Dev,Test,UAT, │ ┌─────────────────────┐
│ Pre-prod,Prod,DR │ │ ENV BOOKING │
└─────────────────────┘ │ (Env booking │
│ Sheet) │
┌─────────────────────┐ │ FK: Release ID │
│ USERS │◄──────────────────────────────────────────│ FK: Application │
│ (Users Sheet) │ M:M (Stakeholders) └─────────────────────┘
│ PK: User ID │
│ FK: Department │◄──────────────────────────────────────────┐
└─────────────────────┘ FK: Release Owner ID │
│ │
│ 1:M │
▼ │
┌─────────────────────┐ ┌─────────────────────┐ ┌─────────────────────┐
│ LEAVE CALENDAR │ │ RISK │ │ DEPENDENCIES │
│ (Leave Calendar │ │ (Risk Sheet) │ │ (Dependencies │
│ Sheet) │ │ FK: Release ID │ │ Sheet) │
│ FK: User ID │ │ FK: Risk Owner ID │ │ FK: Release ID │
│ FK: Affected Rel. │ └─────────────────────┘ │ FK: Depends On ID │
└─────────────────────┘ └─────────────────────┘
FOREIGN KEY REFERENCE TABLE
Source Sheet | FK Column | → | Target Sheet | PK Column
Releases | Department | → | Reference Data | Dept Code
Releases | Application | → | Applications | Application Name
Releases | Release Owner ID | → | Users | User ID
Releases | Stakeholder IDs | → | Users | User ID (M:M)
Applications | Department | → | Reference Data | Dept Code
Env booking | Release ID | → | Releases | Release ID
Env booking | Application | → | Applications | Application Name
Risk | Release ID | → | Releases | Release ID
Risk | Risk Owner ID | → | Users | User ID
Drift | Release ID | → | Releases | Release ID
Drift | Application | → | Applications | Application Name
Dependencies | Release ID | → | Releases | Release ID
Dependencies | Depends On ID | → | Releases | Release ID
Approvals | Release ID | → | Releases | Release ID
Approvals | Approver ID | → | Users | User ID
Leave Calendar | User ID | → | Users | User ID
Leave Calendar | Affected Release | → | Releases | Release ID
Calendar | Release ID | → | Releases | Release ID
Versions | Release ID | → | Releases | Release ID
Versions | Application | → | Applications | Application Name
Monitoring Alerts | Application | → | Applications | Application Name
Incidents | Application | → | Applications | Application Name
Application Status | Application | → | Applications | Application Name
Planned Maintenance | Application | → | Applications | Application Name
SECTION 2: DETAILED SCHEMA DOCUMENTATION
═══════════════════════════════════════════════════════════════════════════════════════════════════════════════════
Each sheet's schema is documented below with column definitions, data types, and validation rules.
DATA TYPE LEGEND:
• TEXT: Free-form text string
• INT: Integer number
• DATE: Date in YYYY-MM-DD format
• DECIMAL: Number with decimal places
• ENUM: Value from predefined list (see Reference Data sheet)
• FK: Foreign key - must match value in referenced table
• BOOL: Boolean (Yes/No or True/False)
• ID: Auto-generated unique identifier
───────────────────────────────────────────────────────────────────────────────────────────────────────────────────
SHEET: Applications ¦ Range: A1:F505 ¦ Records: 504 (84 applications × 6 environments)
───────────────────────────────────────────────────────────────────────────────────────────────────────────────────
Column | Header Name | Data Type | Required | Validation/Constraints | Description
A | Department | ENUM | Yes | Valid: Finance, Logistics, CRM, Manufacturing, IT, HR, Legal, Security | Business unit that owns the application
B | Application | TEXT | Yes | Max 100 chars; Must be unique within department | Name of the software application
C | Env | ENUM | Yes | Valid: Dev, Test, UAT, Pre-prod, Prod, DR | Environment type (6 per application)
D | Application Owner | TEXT | No | Business owner name (first row only) | Primary business owner
E | Tech Lead | TEXT | No | Technical lead name (first row only) | Technical lead contact
F | Env Owner | TEXT | Yes | Environment-specific owner | Person responsible for this environment
Business Rules:
• Each application appears 6 times (once per environment type: Dev, Test, UAT, Pre-prod, Prod, DR)
• Department value only shown on first row of each application group
• Application Owner and Tech Lead only populated on Dev environment row
• Env Owner varies by environment type (Dev Mgr, QA Lead, Business Analyst, Release Mgr, Ops Mgr, Infra Lead)
───────────────────────────────────────────────────────────────────────────────────────────────────────────────────
SHEET: Releases ¦ Range: A1:AB81 ¦ Records: 80 releases
───────────────────────────────────────────────────────────────────────────────────────────────────────────────────
Column | Header Name | Data Type | Required | Validation/Constraints | Description
A | Release ID | ID | Yes | Format: REL-NNNN; Auto-generated; PK | Unique release identifier
B | Release Name | TEXT | Yes | Max 200 chars; Include version number | Descriptive name with version
C | Department | ENUM/FK | Yes | Must exist in Reference Data sheet | Owning business unit
D | Application | TEXT/FK | Yes | Must exist in Applications sheet | Target application name
E | Dependencies | TEXT | No | Comma-separated list or 'NA' | Other releases this depends on
F | Release Size | ENUM | Yes | Valid: Small, Medium, Large | Effort estimation category
G | Impact | ENUM | Yes | Valid: High, Medium, Low | Business impact level
H | Priority | ENUM | Yes | Valid: P1 - Critical, P2 - High, P3 - Medium, P4 - Low | Urgency classification
I | CAB Date | DATE | Yes | YYYY-MM-DD format | Change Advisory Board review date
J | Start Date | DATE | Yes | Must be >= CAB Date | Planned deployment start
K | End Date | DATE | Yes | Must be >= Start Date | Planned deployment completion
L | Test Env Required | TEXT/FK | No | Environment code from Applications | Test environment needed
M | UAT Env Required | TEXT/FK | No | Environment code from Applications | UAT environment needed
N | Status | ENUM | Yes | 12 valid status values (see Reference Data) | Current workflow state
O | Conflict Flag | TEXT | No | ⚠️ CONFLICT or blank | Resource/schedule conflict indicator
P | Notes | TEXT | No | Max 500 chars | Additional context
Q | Readiness % | INT | Yes | 0-100; Format as percentage | Overall readiness score
R | Blockers | TEXT | No | Description of blocking issues | What's preventing progress
S | Vendor Maintenance | TEXT | No | Vendor window description | Vendor-dependent timing
T | Change Freeze | TEXT | No | Freeze period name if applicable | Blocked by freeze period
U | Regulatory | TEXT | No | Compliance requirements | Regulatory considerations
V | Release Owner ID | ID/FK | Yes | Must exist in Users sheet | Primary responsible person
W | Approval Status | ENUM | Yes | CAB workflow states | CAB approval status
X | Depends On | TEXT | No | Release IDs this depends on | Dependency chain
Y | Rollback Plan | ENUM | Yes | Valid: Ready, In Progress, At Risk | Rollback preparedness
Z | Go-Live Checklist % | INT | Yes | 0-100; Format as percentage | Deployment checklist completion
AA | Stakeholder IDs | TEXT | No | Comma-separated User IDs | Interested parties (M:M)
AB | Deployment Window | ENUM | Yes | Valid: Business Hours, Off-Peak, Weekend | Deployment timing preference
───────────────────────────────────────────────────────────────────────────────────────────────────────────────────
SHEET: Env booking ¦ Range: A1:I102 ¦ Records: 101 environment bookings
───────────────────────────────────────────────────────────────────────────────────────────────────────────────────
Column | Header Name | Data Type | Required | Validation/Constraints | Description
A | Booking ID | ID | Yes | Format: ENV-NNNN; Auto-generated; PK | Unique booking identifier
B | Release ID | ID/FK | Yes | Must exist in Releases sheet | Associated release
C | Application | TEXT/FK | Yes | Must exist in Applications sheet | Application requiring environment
D | Env Type | ENUM | Yes | Valid: Dev, Test, UAT, Pre-prod, Prod, DR | Environment type being booked
E | Start Date | DATE | Yes | YYYY-MM-DD format | Booking start date
F | End Date | DATE | Yes | Must be >= Start Date | Booking end date
G | Status | ENUM | Yes | Valid: Confirmed, Pending, Cancelled | Booking status
H | Conflict | TEXT | No | Conflict description if overlapping | Environment conflict indicator
I | Notes | TEXT | No | Max 500 chars | Additional booking notes
───────────────────────────────────────────────────────────────────────────────────────────────────────────────────
SHEET: Risk ¦ Range: A1:K32 ¦ Records: 31 risks
───────────────────────────────────────────────────────────────────────────────────────────────────────────────────
Column | Header Name | Data Type | Required | Validation/Constraints | Description
A | Risk ID | ID | Yes | Format: RSK-NNNN; Auto-generated; PK | Unique risk identifier
B | Release ID | ID/FK | Yes | Must exist in Releases sheet | Associated release
C | Risk Category | ENUM | Yes | Technical, Business, Resource, Timeline, External | Classification of risk type
D | Risk Description | TEXT | Yes | Max 500 chars | Detailed risk description
E | Likelihood | INT | Yes | 1-5 scale (see Reference Data) | Probability of occurrence
F | Impact | INT | Yes | 1-5 scale (see Reference Data) | Severity if occurs
G | Risk Score | INT | Yes | Formula: Likelihood × Impact (1-25) | Composite risk score
H | Mitigation Plan | TEXT | No | Max 500 chars | Risk mitigation approach
I | Risk Owner ID | ID/FK | Yes | Must exist in Users sheet | Person responsible
J | Status | ENUM | Yes | Open, Mitigating, Accepted, Closed | Current risk status
K | Review Date | DATE | No | YYYY-MM-DD format | Next review date
───────────────────────────────────────────────────────────────────────────────────────────────────────────────────
ADDITIONAL SHEET SCHEMAS (SUMMARY)
───────────────────────────────────────────────────────────────────────────────────────────────────────────────────
The following sheets follow similar patterns. Key columns are listed below:
SHEET: Calendar ¦ Primary Key: Event ID ¦ Foreign Keys: Release ID
- Columns: Event ID, Release ID, Event Type, Event Date, Start Time, End Time, Description, Location, Attendees
SHEET: Dependencies ¦ Primary Key: Dependency ID ¦ Foreign Keys: Release ID, Depends On Release ID
- Columns: Dependency ID, Release ID, Depends On, Dependency Type, Status, Description, Blocking
SHEET: Approvals ¦ Primary Key: Approval ID ¦ Foreign Keys: Release ID, Approver ID
- Columns: Approval ID, Release ID, Approval Type, Approver ID, Status, Requested Date, Decided Date, Comments
SHEET: Leave Calendar ¦ Primary Key: Leave ID ¦ Foreign Keys: User ID, Affected Release ID
- Columns: Leave ID, User ID, Leave Type, Start Date, End Date, Affected Release, Backup Contact, Status
SHEET: Drift ¦ Primary Key: Drift ID ¦ Foreign Keys: Release ID, Application
- Columns: Drift ID, Release ID, Application, Drift Type, Original Date, New Date, Drift Reason, Impact, Status
SHEET: Versions ¦ Primary Key: Version ID ¦ Foreign Keys: Release ID, Application
- Columns: Version ID, Release ID, Application, Version Number, Environment, Deployed Date, Deployed By, Status
SHEET: System Mapping ¦ Primary Key: Mapping ID ¦ Foreign Keys: Source Application, Target Application
- Columns: Mapping ID, Source App, Target App, Integration Type, Data Flow, Frequency, Status, Owner
SHEET: Monitoring Alerts ¦ Primary Key: Alert ID ¦ Foreign Keys: Application
- Columns: Alert ID, Timestamp, Application, Department, Alert Type, Severity, Metric, Threshold, Status
SHEET: Incidents ¦ Primary Key: Incident ID ¦ Foreign Keys: Application, Related Release
- Columns: Incident ID, Timestamp, Application, Severity (P1-P3), Title, Status, Impact, Assigned To
SHEET: Application Status ¦ Primary Key: Composite (Application + Environment) ¦ Foreign Keys: Application
- Columns: Application, Department, Environment, Status (Healthy/Degraded/Down), Last Check, Uptime %, Notes
SHEET: Planned Maintenance ¦ Primary Key: Maintenance ID ¦ Foreign Keys: Application
- Columns: Maintenance ID, Scheduled Date, Start Time, End Time, Type, Application, Environment, Impact
SHEET: Users ¦ Primary Key: User ID ¦ Foreign Keys: Department
- Columns: User ID, Name, Email, Department, Role, Manager ID, Active Status, Phone, Last Login
SECTION 3: DATA VALIDATION RULES & INTEGRITY CHECKS
═══════════════════════════════════════════════════════════════════════════════════════════════════════════════════
These rules must be enforced in the application to maintain data integrity.
REFERENTIAL INTEGRITY (FK must exist in target table):
• Releases.Department → Reference Data.Departments
• Releases.Application → Applications.Application
• Releases.Release Owner ID → Users.User ID
• Env booking.Release ID → Releases.Release ID
• Risk.Release ID → Releases.Release ID
• Dependencies.Release ID → Releases.Release ID
• Approvals.Release ID → Releases.Release ID
DATE VALIDATION RULES:
• Release Start Date ≥ CAB Date (cannot deploy before approval)
• Release End Date ≥ Start Date (logical duration)
• Booking End Date ≥ Booking Start Date
• Leave End Date ≥ Leave Start Date
BUSINESS LOGIC VALIDATIONS:
• Readiness % must be 0-100
• Go-Live Checklist % must be 0-100
• Risk Score = Likelihood × Impact (auto-calculated)
• Risk Score must be 1-25 (1×1 to 5×5)
• Status transitions must follow workflow (see Reference Data sheet)
• Cannot approve release during Change Freeze period
UNIQUE CONSTRAINTS:
• Release ID must be unique across all releases
• User ID must be unique across all users
• Application name must be unique within department
CASCADE RULES:
• Deleting a Release should orphan-check: Env bookings, Risks, Dependencies, Approvals
• Deleting a User should orphan-check: Release Ownership, Risk Ownership, Approvals
SECTION 4: DOCUMENT METADATA
═══════════════════════════════════════════════════════════════════════════════════════════════════════════════════
Document Title: Release Desk - Technical Specifications
Version: 1.1
Created: June 28, 2026
Purpose: Database schema and data validation rules for application development
Related Document: README sheet (for UI/wireframe specifications)
NOTES FOR DEVELOPERS:
• All IDs use format: PREFIX-NNNN (e.g., REL-0001, USR-001, RSK-001)
• Dates should be stored in YYYY-MM-DD format for sorting
• ENUM values are defined in Reference Data sheet - use dropdowns in UI
• Foreign key relationships must be validated before saving records
• Workflow state transitions must follow defined paths (see Reference Data sheet)
• Risk Score is calculated field: Likelihood × Impact
═══════════════════════════════════════════════════════════════════════════════════════════════════════════════════
END OF TECHNICAL SPECIFICATIONS
═══════════════════════════════════════════════════════════════════════════════════════════════════════════════════

## Reference Data
RELEASE DESK - REFERENCE DATA CATALOG
Consolidated lookup tables, status codes, thresholds, and configuration data
Version 1.0 ¦ Generated: June 2026
WORKBOOK STATISTICS
Metric | Value | Source
Total Departments | 8 | Applications sheet
Total Applications | 84 | Applications sheet
Total Releases | 80 | Releases sheet
Total Users | 100+ | Users, Release Managers, Super Admins
Risk Factors | 44-46 | Risk Factors sheet
1. DEPARTMENTS
Dept ID | Dept Code | Dept Name | Primary Focus
DEPT-01 | FIN | Finance | Financial planning, reporting, treasury
DEPT-02 | LOG | Logistics | Warehouse, transportation, supply chain
DEPT-03 | CRM | CRM | Sales, marketing, customer service
DEPT-04 | MFG | Manufacturing | Production, quality, MES systems
DEPT-05 | IT | IT | Infrastructure, monitoring, service desk
DEPT-06 | HR | HR | HCM, payroll, learning, talent
DEPT-07 | LEG | Legal | Contracts, compliance, document management
DEPT-08 | SEC | Security | Identity, access, threat detection
2. ENVIRONMENTS
Env Code | Env Name | Promotion Order | Availability | Description
DEV | Development | 1 | 24/7 | Developer sandbox environment
TEST | Testing | 2 | Business Hours | QA and integration testing
UAT | User Acceptance | 3 | Business Hours | Business validation environment
PREPROD | Pre-Production | 4 | Business Hours | Production mirror for final validation
PROD | Production | 5 | 24/7 | Live production environment
DR | Disaster Recovery | 6 | 24/7 | Business continuity failover
3. RELEASE SIZES
Size | Test Days | UAT Days | Pre-Prod Days | Total Lead Time | Examples
Small | 3 | 2 | 1 | ~8 days | Bug fixes, minor UI changes
Medium | 5 | 3 | 2 | ~12 days | Feature enhancements, integrations
Large | 10 | 5 | 4 | ~22 days | Major releases, platform upgrades
4. IMPACT LEVELS
Level | Code | Color | Description | Examples
High | H | #FF0000 | Critical business impact | Core ERP, Payment Systems
Medium | M | #FFC000 | Moderate impact, workarounds exist | Reporting, Secondary CRM
Low | L | #00B050 | Minimal impact, easily recoverable | UI changes, Minor enhancements
5. PRIORITY LEVELS
Priority | Code | Response Time | Escalation | Description
Critical | P1 | Immediate | CIO/VP Level | Business-stopping issues, security breaches
High | P2 | 4 hours | Director Level | Major degradation, customer impacting
Medium | P3 | 1 business day | Manager Level | Important but not urgent issues
Low | P4 | 5 business days | Standard | Minor issues, enhancements
6. RELEASE STATUS CODES
Status Code | Display Name | Stage | Description
DRAFT | Draft | Initial | Release being planned, not yet submitted
SUBMITTED | Submitted | Review | Release submitted for review and approval
PENDING_CAB | Pending CAB | Review | Awaiting Change Advisory Board review
APPROVED | Approved | Ready | All approvals obtained, ready to proceed
IN_PROGRESS | In Progress | Active | Release deployment actively underway
BLOCKED | Blocked | Hold | Release halted due to dependency or issue
ON_HOLD | On Hold | Hold | Temporarily paused for business reasons
COMPLETED | Completed | Closed | Release successfully deployed
FAILED | Failed | Closed | Release deployment failed, rollback executed
CANCELLED | Cancelled | Closed | Release cancelled before deployment
7. RISK SCORE THRESHOLDS
Risk Level | Score Range | Color Code | Action Required | Approval Level
LOW | < 1.5 | #00B050 | Standard process | Release Manager
MEDIUM | 1.5 - 2.5 | #FFC000 | Enhanced monitoring | Release Manager + Tech Lead
HIGH | 2.5 - 3.5 | #FF6600 | Risk mitigation plan required | Director Approval
CRITICAL | 3.5 - 4.0 | #FF0000 | Executive review, CAB escalation | VP/CIO Approval
SEVERE | ≥ 4.0 | #7030A0 | Consider postponement | Emergency CAB
8. APPROVAL TYPES & WORKFLOW
Approval Type | Code | Approver Role | SLA (Hours) | Sequence
Technical Review | TECH | Tech Lead / Architect | 24 | 1
Security Review | SEC | Security Team | 48 | 2
Business Review | BIZ | Business Owner | 24 | 3
QA Sign-off | QA | QA Lead | 8 | 4
CAB Review | CAB | Change Advisory Board | 48 | 5
Final Approval | FINAL | Release Manager | 4 | 6
9. DEPENDENCY TYPES
Type | Code | Impact | Description
Hard | HARD | Blocking | Must be resolved before release can proceed
Soft | SOFT | Advisory | Recommended but not mandatory
Technical | TECH | Blocking | Code or infrastructure dependencies
Data | DATA | Blocking | Data migration or sync requirements
Integration | INTG | Variable | External system integration points
10. DEPENDENCY STATUS
Status | Code | Color | Description
Clear | CLR | #00B050 | Dependency resolved, no action needed
At Risk | RISK | #FFC000 | Potential issue, requires monitoring
Blocked | BLK | #FF0000 | Active blocker, must be resolved
Resolved | RES | #0070C0 | Previously blocked, now cleared
11. LEAVE TYPES
Leave Type | Code | Risk Impact | Coverage Required
Annual Leave | AL | Low-Medium | If key resource, backup needed
Personal Leave | PL | Low | Standard handover
Sick Leave | SL | Variable | Emergency coverage protocol
Conference | CONF | Low | Planned, backup assigned
Training | TRN | Low | Planned, limited availability
12. USER ROLES & PERMISSIONS
Role | Code | Create Release | Approve | Admin
Super Admin | SADM | Yes | Yes | Yes
Release Manager | RELMGR | Yes | Yes | Limited
Development Manager | DEVMGR | Yes | Yes | No
QA Lead | QALEAD | No | Yes | No
Tech Lead | TLEAD | Yes | Yes | No
Business Analyst | BA | Yes | No | No
Developer | DEV | Limited | No | No
Tester | TEST | No | No | No
Viewer | VIEW | No | No | No
CAB Member | CAB | No | Yes | No
13. DRIFT CATEGORIES
Category | Code | Severity | Description
Infrastructure | INFRA | High | Server, network, or hardware drift
Configuration | CONFIG | Medium | Application or system settings drift
Data | DATA | High | Database schema or data inconsistency
Integration | INTG | High | API or interface version mismatch
Security | SEC | Critical | Security patch or certificate drift
Code | CODE | Medium | Unauthorized code changes
14. CHANGE FREEZE PERIODS
Period | Type | Duration | Timing | Exceptions
Year-End Freeze | Mandatory | 19 days | Dec 13 - Dec 31 | P1 emergencies only
Q1 Quarter-End | Advisory | 3 days | Mar 29 - Mar 31 | Pre-approved only
Q2 Quarter-End | Advisory | 3 days | Jun 28 - Jun 30 | Pre-approved only
Q3 Quarter-End | Advisory | 3 days | Sep 28 - Sep 30 | Pre-approved only
Major Events | Variable | As defined | Board meetings, audits | Emergency only
Holiday Periods | Advisory | Variable | Public holidays | Minimal changes
15. RISK FACTOR WEIGHTS BY CATEGORY
Category | Weight % | # Factors | Key Factors
Technical Complexity | 12% | 5 | New Tech Stack, Code Complexity, DB Changes
Testing Quality | 14% | 6 | Test Coverage, Env Parity, Automation
Security & Compliance | 12% | 5 | Vulnerabilities, Pen Test, Compliance Gate
Data Migration | 10% | 4 | Migration Required, Scripts Tested, Backup
Resource & Schedule | 10% | 4 | Team Availability, Overlapping Releases
Environment & Dependencies | 10% | 4 | Upstream/Downstream, Feature Flags
Operational Readiness | 10% | 5 | Rollback Time, Runbook, Automation Level
Performance & Scalability | 8% | 4 | Load Test, Performance Regression
Release History | 8% | 5 | Past Failures, MTBR, MTBF
Business Criticality | 6% | 4 | Revenue Impact, User Blast Radius
TOTAL | 100% | 46 | Full weighted risk assessment
16. SHARED ENVIRONMENTS
Environment | Shared By | Booking Required | Max Concurrent | Contention Level
UAT-Shared-1 | Finance, HR, Legal | Yes | 2 teams | High
UAT-Shared-2 | IT, Security | Yes | 2 teams | Medium
Test-Integration | All Departments | Yes | 3 teams | High
Pre-Prod-Core | Finance, Manufacturing | Yes | 1 team | Critical
DR-Test | All Departments | Yes | 1 team | Medium
Performance Lab | IT, CRM, Manufacturing | Yes | 1 team | High
Security Scan | All Departments | Yes | 2 teams | Medium
Data Migration | Finance, HR | Yes | 1 team | High
17. INTEGRATION TYPES
Type | Code | Latency Req | Description
Real-Time API | RT-API | < 100ms | Synchronous REST/SOAP calls
Batch File | BATCH | Scheduled | Nightly or scheduled file transfers
Message Queue | MQ | < 1 sec | Asynchronous messaging (Kafka, MQ)
Database Link | DBLINK | < 500ms | Direct database connections
Event Stream | EVENT | Near real-time | Event-driven architecture
Middleware | MW | Variable | ESB or integration platform
Manual | MANUAL | N/A | Human-initiated data entry
18. RISK LIKELIHOOD SCALE
Level | Score | Probability | Description
Rare | 1 | < 5% | Unlikely to occur in normal circumstances
Unlikely | 2 | 5-25% | Could occur but not expected
Possible | 3 | 25-50% | May occur at some time
Likely | 4 | 50-75% | Will probably occur
Almost Certain | 5 | > 75% | Expected to occur in most circumstances
19. RISK IMPACT SCALE
Level | Score | Business Impact | Description
Negligible | 1 | < $10K | Minor inconvenience, no service impact
Minor | 2 | $10K-$100K | Limited impact, workarounds available
Moderate | 3 | $100K-$500K | Significant impact, degraded service
Major | 4 | $500K-$1M | Major disruption, critical functions affected
Catastrophic | 5 | > $1M | Complete service failure, regulatory breach
20. APPLICATION CATEGORIES
Category | Tier | Criticality | Example Applications
Core ERP | Tier 1 | Mission Critical | SAP S/4HANA, Oracle EBS
Financial Systems | Tier 1 | Mission Critical | Treasury, Tax, Revenue Recognition
Customer Facing | Tier 1 | High | CRM, E-commerce, Portal
Manufacturing/Operations | Tier 2 | High | MES, WMS, Supply Chain
HR Systems | Tier 2 | Medium | HCM, Payroll, Recruiting
Security/Compliance | Tier 2 | High | IAM, SIEM, GRC
Analytics/Reporting | Tier 3 | Medium | BI Tools, Data Warehouse
Collaboration | Tier 3 | Low | Email, Messaging, Document Mgmt
Development Tools | Tier 3 | Low | CI/CD, Repositories, IDEs
21. NOTIFICATION TYPES
Type | Trigger | Recipients | Channel
Release Submitted | New release created | Tech Lead, QA Lead | Email, Teams
Approval Required | Review stage reached | Designated approver | Email, Teams
CAB Scheduled | CAB meeting set | All stakeholders | Email, Calendar
Go-Live Alert | 24h before deployment | All teams | Email, SMS, Teams
Deployment Started | Release begins | Operations, Support | Teams, Slack
Deployment Complete | Release finished | All stakeholders | Email, Teams
Rollback Initiated | Failure detected | All teams, Management | Email, SMS, Phone
22. TESTING PHASES & GATES
Phase | Environment | Entry Criteria | Exit Criteria | Sign-off Required
Unit Testing | DEV | Code complete | > 80% coverage | Developer
Integration Test | TEST | Unit tests pass | All APIs verified | Tech Lead
System Test | TEST | Integration complete | End-to-end scenarios pass | QA Lead
Performance Test | TEST/PERF | System test pass | Meet SLA benchmarks | Performance Team
Security Test | TEST | Code freeze | No critical vulnerabilities | Security Team
UAT | UAT | System test pass | Business sign-off | Business Owner
Pre-Prod Validation | PREPROD | UAT complete | Prod-mirror verified | Release Manager
Go/No-Go | N/A | All gates passed | Final approval | CAB
23. DEPLOYMENT WINDOWS
Window | Day | Time (Local) | Duration | Suitable For
Standard | Tue-Thu | 02:00 - 06:00 | 4 hours | Medium/Low risk releases
Extended | Saturday | 00:00 - 08:00 | 8 hours | Large releases, migrations
Emergency | Any | As needed | Minimal | P1 hotfixes only
Maintenance | Sunday | 02:00 - 06:00 | 4 hours | Infra, patching
Business Hours | Mon-Fri | 10:00 - 16:00 | Variable | Low risk, no downtime
Off-Peak | Fri | 22:00 - 02:00 | 4 hours | Regional releases
Quarterly Major | Saturday | 00:00 - 12:00 | 12 hours | Major upgrades
24. SLA METRICS & TARGETS
Metric | Target | Warning | Critical | Measurement
Release Success Rate | > 95% | 90-95% | < 90% | Monthly
Mean Time to Deploy | < 4 hours | 4-6 hours | > 6 hours | Per release
Rollback Rate | < 5% | 5-10% | > 10% | Monthly
CAB Approval Time | < 48 hours | 48-72 hours | > 72 hours | Per release
Environment Availability | > 99% | 95-99% | < 95% | Weekly
Test Pass Rate | > 98% | 95-98% | < 95% | Per release
Change Lead Time | < 14 days | 14-21 days | > 21 days | Per release
Incident Rate Post-Deploy | < 2% | 2-5% | > 5% | 7 days post
Documentation Complete | 100% | 95-100% | < 95% | Per release
Stakeholder Satisfaction | > 4.0/5 | 3.5-4.0 | < 3.5 | Quarterly survey

## Applications
Department | Application | Env | Application Owner | Tech Lead | Env Owner
Finance | SAP S/4HANA Finance (FICO) | Dev | Sarah Mitchell | James Wilson | Alex Rivera (Dev Mgr)
| SAP S/4HANA Finance (FICO) | Test |  |  | Sam Anderson (QA Lead)
| SAP S/4HANA Finance (FICO) | UAT |  |  | Rachel Green (Bus Analyst)
| SAP S/4HANA Finance (FICO) | Pre-prod |  |  | Nathan Cole (Release Mgr)
| SAP S/4HANA Finance (FICO) | Prod |  |  | Victoria Sterling (Ops Mgr)
| SAP S/4HANA Finance (FICO) | DR |  |  | Robert Shield (Infra Lead)
| Anaplan | Dev | David Chen | Emily Zhang | Jordan Lee (Dev Mgr)
| Anaplan | Test |  |  | Chris Park (QA Lead)
| Anaplan | UAT |  |  | Monica Geller (Bus Analyst)
| Anaplan | Pre-prod |  |  | Ethan Black (Release Mgr)
| Anaplan | Prod |  |  | Elizabeth Crown (Ops Mgr)
| Anaplan | DR |  |  | William Guard (Infra Lead)
| Oracle Hyperion HFM | Dev | Jennifer Walsh | Michael Brown | Casey Chen (Dev Mgr)
| Oracle Hyperion HFM | Test |  |  | Pat Murphy (QA Lead)
| Oracle Hyperion HFM | UAT |  |  | Phoebe Buffay (Bus Analyst)
| Oracle Hyperion HFM | Pre-prod |  |  | Lucas White (Release Mgr)
| Oracle Hyperion HFM | Prod |  |  | Catherine Royal (Ops Mgr)
| Oracle Hyperion HFM | DR |  |  | James Fortress (Infra Lead)
| Kyriba | Dev | Robert Kim | Priya Sharma | Morgan Taylor (Dev Mgr)
| Kyriba | Test |  |  | Jesse Garcia (QA Lead)
| Kyriba | UAT |  |  | Emma Watson (Bus Analyst)
| Kyriba | Pre-prod |  |  | Mason Gray (Release Mgr)
| Kyriba | Prod |  |  | Margaret Noble (Ops Mgr)
| Kyriba | DR |  |  | Michael Bastion (Infra Lead)
| Coupa | Dev | Michelle Torres | Christopher Davis | Jamie Patel (Dev Mgr)
| Coupa | Test |  |  | Robin Chen (QA Lead)
| Coupa | UAT |  |  | Sophie Turner (Bus Analyst)
| Coupa | Pre-prod |  |  | Logan Stone (Release Mgr)
| Coupa | Prod |  |  | Diana Prince (Ops Mgr)
| Coupa | DR |  |  | David Tower (Infra Lead)
| Zuora | Dev | Andrew Patel | Angela Liu | Riley Kim (Dev Mgr)
| Zuora | Test |  |  | Dana Wilson (QA Lead)
| Zuora | UAT |  |  | Mia Collins (Bus Analyst)
| Zuora | Pre-prod |  |  | Jacob Hill (Release Mgr)
| Zuora | Prod |  |  | Helena Troy (Ops Mgr)
| Zuora | DR |  |  | Richard Wall (Infra Lead)
| RevPro | Dev | Lisa Thompson | Daniel Park | Quinn Johnson (Dev Mgr)
| RevPro | Test |  |  | Kelly Nguyen (QA Lead)
| RevPro | UAT |  |  | Isabella Moore (Bus Analyst)
| RevPro | Pre-prod |  |  | Aiden Clark (Release Mgr)
| RevPro | Prod |  |  | Sophia Grace (Ops Mgr)
| RevPro | DR |  |  | Thomas Castle (Infra Lead)
| Thomson Reuters ONESOURCE | Dev | Mark Rodriguez | Jessica Nguyen | Avery Williams (Dev Mgr)
| Thomson Reuters ONESOURCE | Test |  |  | Terry Brooks (QA Lead)
| Thomson Reuters ONESOURCE | UAT |  |  | Olivia James (Bus Analyst)
| Thomson Reuters ONESOURCE | Pre-prod |  |  | Jackson Moore (Release Mgr)
| Thomson Reuters ONESOURCE | Prod |  |  | Alexandra Reid (Ops Mgr)
| Thomson Reuters ONESOURCE | DR |  |  | Charles Vault (Infra Lead)
| SAP Concur | Dev | Amanda Foster | Ryan Cooper | Drew Martinez (Dev Mgr)
| SAP Concur | Test |  |  | Skyler Davis (QA Lead)
| SAP Concur | UAT |  |  | Ava Mitchell (Bus Analyst)
| SAP Concur | Pre-prod |  |  | Sebastian Hall (Release Mgr)
| SAP Concur | Prod |  |  | Christina Vale (Ops Mgr)
| SAP Concur | DR |  |  | Daniel Bunker (Infra Lead)
| Workday Financials | Dev | Kevin O'Brien | Samantha Reed | Cameron Brown (Dev Mgr)
| Workday Financials | Test |  |  | Jordan Reed (QA Lead)
| Workday Financials | UAT |  |  | Charlotte Price (Bus Analyst)
| Workday Financials | Pre-prod |  |  | Caleb Young (Release Mgr)
| Workday Financials | Prod |  |  | Natasha Roman (Ops Mgr)
| Workday Financials | DR |  |  | Matthew Haven (Infra Lead)
| MetricStream | Dev | Rachel Green | William Chen | Taylor Singh (Dev Mgr)
| MetricStream | Test |  |  | Alex Foster (QA Lead)
| MetricStream | UAT |  |  | Amelia Scott (Bus Analyst)
| MetricStream | Pre-prod |  |  | Owen King (Release Mgr)
| MetricStream | Prod |  |  | Amanda Cross (Ops Mgr)
| MetricStream | DR |  |  | Anthony Secure (Infra Lead)
| IBM Cognos | Dev | Thomas Wright | Olivia Martinez | Blake Thompson (Dev Mgr)
| IBM Cognos | Test |  |  | Morgan Hayes (QA Lead)
| IBM Cognos | UAT |  |  | Harper Lewis (Bus Analyst)
| IBM Cognos | Pre-prod |  |  | Liam Wright (Release Mgr)
| IBM Cognos | Prod |  |  | Rebecca Stone (Ops Mgr)
| IBM Cognos | DR |  |  | Mark Backup (Infra Lead)
| HighRadius | Dev | Diana Lee | Nathan Brooks | Alex Rivera (Dev Mgr)
| HighRadius | Test |  |  | Sam Anderson (QA Lead)
| HighRadius | UAT |  |  | Rachel Green (Bus Analyst)
| HighRadius | Pre-prod |  |  | Nathan Cole (Release Mgr)
| HighRadius | Prod |  |  | Victoria Sterling (Ops Mgr)
| HighRadius | DR |  |  | Robert Shield (Infra Lead)
| Basware | Dev | Steven Martinez | Karen Singh | Jordan Lee (Dev Mgr)
| Basware | Test |  |  | Chris Park (QA Lead)
| Basware | UAT |  |  | Monica Geller (Bus Analyst)
| Basware | Pre-prod |  |  | Ethan Black (Release Mgr)
| Basware | Prod |  |  | Elizabeth Crown (Ops Mgr)
| Basware | DR |  |  | William Guard (Infra Lead)
Logistics | SAP Transportation Management (TM) | Dev | Brian Murphy | Marcus Johnson | Alex Rivera (Dev Mgr)
| SAP Transportation Management (TM) | Test |  |  | Sam Anderson (QA Lead)
| SAP Transportation Management (TM) | UAT |  |  | Rachel Green (Bus Analyst)
| SAP Transportation Management (TM) | Pre-prod |  |  | Nathan Cole (Release Mgr)
| SAP Transportation Management (TM) | Prod |  |  | Victoria Sterling (Ops Mgr)
| SAP Transportation Management (TM) | DR |  |  | Robert Shield (Infra Lead)
| Oracle Transportation Management | Dev | Catherine Hayes | Tina Wang | Jordan Lee (Dev Mgr)
| Oracle Transportation Management | Test |  |  | Chris Park (QA Lead)
| Oracle Transportation Management | UAT |  |  | Monica Geller (Bus Analyst)
| Oracle Transportation Management | Pre-prod |  |  | Ethan Black (Release Mgr)
| Oracle Transportation Management | Prod |  |  | Elizabeth Crown (Ops Mgr)
| Oracle Transportation Management | DR |  |  | William Guard (Infra Lead)
| Blue Yonder WMS | Dev | Eric Johansson | Alexander Petrov | Casey Chen (Dev Mgr)
| Blue Yonder WMS | Test |  |  | Pat Murphy (QA Lead)
| Blue Yonder WMS | UAT |  |  | Phoebe Buffay (Bus Analyst)
| Blue Yonder WMS | Pre-prod |  |  | Lucas White (Release Mgr)
| Blue Yonder WMS | Prod |  |  | Catherine Royal (Ops Mgr)
| Blue Yonder WMS | DR |  |  | James Fortress (Infra Lead)
| Manhattan Associates WMS | Dev | Patricia Wong | Rachel Kim | Morgan Taylor (Dev Mgr)
| Manhattan Associates WMS | Test |  |  | Jesse Garcia (QA Lead)
| Manhattan Associates WMS | UAT |  |  | Emma Watson (Bus Analyst)
| Manhattan Associates WMS | Pre-prod |  |  | Mason Gray (Release Mgr)
| Manhattan Associates WMS | Prod |  |  | Margaret Noble (Ops Mgr)
| Manhattan Associates WMS | DR |  |  | Michael Bastion (Infra Lead)
| JDA Supply Chain Planning | Dev | Gregory Adams | Vincent Lopez | Jamie Patel (Dev Mgr)
| JDA Supply Chain Planning | Test |  |  | Robin Chen (QA Lead)
| JDA Supply Chain Planning | UAT |  |  | Sophie Turner (Bus Analyst)
| JDA Supply Chain Planning | Pre-prod |  |  | Logan Stone (Release Mgr)
| JDA Supply Chain Planning | Prod |  |  | Diana Prince (Ops Mgr)
| JDA Supply Chain Planning | DR |  |  | David Tower (Infra Lead)
| Kinaxis RapidResponse | Dev | Nicole Fraser | Heather Stone | Riley Kim (Dev Mgr)
| Kinaxis RapidResponse | Test |  |  | Dana Wilson (QA Lead)
| Kinaxis RapidResponse | UAT |  |  | Mia Collins (Bus Analyst)
| Kinaxis RapidResponse | Pre-prod |  |  | Jacob Hill (Release Mgr)
| Kinaxis RapidResponse | Prod |  |  | Helena Troy (Ops Mgr)
| Kinaxis RapidResponse | DR |  |  | Richard Wall (Infra Lead)
| E2open | Dev | Jason Burke | Brandon Lee | Quinn Johnson (Dev Mgr)
| E2open | Test |  |  | Kelly Nguyen (QA Lead)
| E2open | UAT |  |  | Isabella Moore (Bus Analyst)
| E2open | Pre-prod |  |  | Aiden Clark (Release Mgr)
| E2open | Prod |  |  | Sophia Grace (Ops Mgr)
| E2open | DR |  |  | Thomas Castle (Infra Lead)
| Descartes Systems | Dev | Laura Schmidt | Melissa Chang | Avery Williams (Dev Mgr)
| Descartes Systems | Test |  |  | Terry Brooks (QA Lead)
| Descartes Systems | UAT |  |  | Olivia James (Bus Analyst)
| Descartes Systems | Pre-prod |  |  | Jackson Moore (Release Mgr)
| Descartes Systems | Prod |  |  | Alexandra Reid (Ops Mgr)
| Descartes Systems | DR |  |  | Charles Vault (Infra Lead)
| project44 | Dev | Derek Coleman | Tyler Morrison | Drew Martinez (Dev Mgr)
| project44 | Test |  |  | Skyler Davis (QA Lead)
| project44 | UAT |  |  | Ava Mitchell (Bus Analyst)
| project44 | Pre-prod |  |  | Sebastian Hall (Release Mgr)
| project44 | Prod |  |  | Christina Vale (Ops Mgr)
| project44 | DR |  |  | Daniel Bunker (Infra Lead)
| FourKites | Dev | Stephanie Mills | Christina Reyes | Cameron Brown (Dev Mgr)
| FourKites | Test |  |  | Jordan Reed (QA Lead)
| FourKites | UAT |  |  | Charlotte Price (Bus Analyst)
| FourKites | Pre-prod |  |  | Caleb Young (Release Mgr)
| FourKites | Prod |  |  | Natasha Roman (Ops Mgr)
| FourKites | DR |  |  | Matthew Haven (Infra Lead)
CRM | Salesforce Sales Cloud | Dev | Matthew Clarke | Carlos Mendez | Alex Rivera (Dev Mgr)
| Salesforce Sales Cloud | Test |  |  | Sam Anderson (QA Lead)
| Salesforce Sales Cloud | UAT |  |  | Rachel Green (Bus Analyst)
| Salesforce Sales Cloud | Pre-prod |  |  | Nathan Cole (Release Mgr)
| Salesforce Sales Cloud | Prod |  |  | Victoria Sterling (Ops Mgr)
| Salesforce Sales Cloud | DR |  |  | Robert Shield (Infra Lead)
| Salesforce Service Cloud | Dev | Victoria Santos | Jennifer Park | Jordan Lee (Dev Mgr)
| Salesforce Service Cloud | Test |  |  | Chris Park (QA Lead)
| Salesforce Service Cloud | UAT |  |  | Monica Geller (Bus Analyst)
| Salesforce Service Cloud | Pre-prod |  |  | Ethan Black (Release Mgr)
| Salesforce Service Cloud | Prod |  |  | Elizabeth Crown (Ops Mgr)
| Salesforce Service Cloud | DR |  |  | William Guard (Infra Lead)
| Microsoft Dynamics 365 CRM | Dev | Benjamin Scott | Michael Chang | Casey Chen (Dev Mgr)
| Microsoft Dynamics 365 CRM | Test |  |  | Pat Murphy (QA Lead)
| Microsoft Dynamics 365 CRM | UAT |  |  | Phoebe Buffay (Bus Analyst)
| Microsoft Dynamics 365 CRM | Pre-prod |  |  | Lucas White (Release Mgr)
| Microsoft Dynamics 365 CRM | Prod |  |  | Catherine Royal (Ops Mgr)
| Microsoft Dynamics 365 CRM | DR |  |  | James Fortress (Infra Lead)
| SAP CRM | Dev | Alexis Rivera | Natalie Brooks | Morgan Taylor (Dev Mgr)
| SAP CRM | Test |  |  | Jesse Garcia (QA Lead)
| SAP CRM | UAT |  |  | Emma Watson (Bus Analyst)
| SAP CRM | Pre-prod |  |  | Mason Gray (Release Mgr)
| SAP CRM | Prod |  |  | Margaret Noble (Ops Mgr)
| SAP CRM | DR |  |  | Michael Bastion (Infra Lead)
| HubSpot CRM | Dev | Jonathan Reed | David Kim | Jamie Patel (Dev Mgr)
| HubSpot CRM | Test |  |  | Robin Chen (QA Lead)
| HubSpot CRM | UAT |  |  | Sophie Turner (Bus Analyst)
| HubSpot CRM | Pre-prod |  |  | Logan Stone (Release Mgr)
| HubSpot CRM | Prod |  |  | Diana Prince (Ops Mgr)
| HubSpot CRM | DR |  |  | David Tower (Infra Lead)
| Zoho CRM | Dev | Megan O'Connor | Rebecca Torres | Riley Kim (Dev Mgr)
| Zoho CRM | Test |  |  | Dana Wilson (QA Lead)
| Zoho CRM | UAT |  |  | Mia Collins (Bus Analyst)
| Zoho CRM | Pre-prod |  |  | Jacob Hill (Release Mgr)
| Zoho CRM | Prod |  |  | Helena Troy (Ops Mgr)
| Zoho CRM | DR |  |  | Richard Wall (Infra Lead)
| Oracle CX Cloud | Dev | Patrick Dunn | Anthony Chen | Quinn Johnson (Dev Mgr)
| Oracle CX Cloud | Test |  |  | Kelly Nguyen (QA Lead)
| Oracle CX Cloud | UAT |  |  | Isabella Moore (Bus Analyst)
| Oracle CX Cloud | Pre-prod |  |  | Aiden Clark (Release Mgr)
| Oracle CX Cloud | Prod |  |  | Sophia Grace (Ops Mgr)
| Oracle CX Cloud | DR |  |  | Thomas Castle (Infra Lead)
| Pega CRM | Dev | Ashley Gonzalez | Stephanie Wu | Avery Williams (Dev Mgr)
| Pega CRM | Test |  |  | Terry Brooks (QA Lead)
| Pega CRM | UAT |  |  | Olivia James (Bus Analyst)
| Pega CRM | Pre-prod |  |  | Jackson Moore (Release Mgr)
| Pega CRM | Prod |  |  | Alexandra Reid (Ops Mgr)
| Pega CRM | DR |  |  | Charles Vault (Infra Lead)
| Zendesk | Dev | Trevor Banks | Justin Taylor | Drew Martinez (Dev Mgr)
| Zendesk | Test |  |  | Skyler Davis (QA Lead)
| Zendesk | UAT |  |  | Ava Mitchell (Bus Analyst)
| Zendesk | Pre-prod |  |  | Sebastian Hall (Release Mgr)
| Zendesk | Prod |  |  | Christina Vale (Ops Mgr)
| Zendesk | DR |  |  | Daniel Bunker (Infra Lead)
| Freshworks CRM | Dev | Courtney Price | Amanda Lee | Cameron Brown (Dev Mgr)
| Freshworks CRM | Test |  |  | Jordan Reed (QA Lead)
| Freshworks CRM | UAT |  |  | Charlotte Price (Bus Analyst)
| Freshworks CRM | Pre-prod |  |  | Caleb Young (Release Mgr)
| Freshworks CRM | Prod |  |  | Natasha Roman (Ops Mgr)
| Freshworks CRM | DR |  |  | Matthew Haven (Infra Lead)
Manufacturing | SAP S/4HANA Manufacturing | Dev | Richard Hoffman | Kenneth Wright | Alex Rivera (Dev Mgr)
| SAP S/4HANA Manufacturing | Test |  |  | Sam Anderson (QA Lead)
| SAP S/4HANA Manufacturing | UAT |  |  | Rachel Green (Bus Analyst)
| SAP S/4HANA Manufacturing | Pre-prod |  |  | Nathan Cole (Release Mgr)
| SAP S/4HANA Manufacturing | Prod |  |  | Victoria Sterling (Ops Mgr)
| SAP S/4HANA Manufacturing | DR |  |  | Robert Shield (Infra Lead)
| Siemens Opcenter | Dev | Sandra Peters | Laura Schmidt | Jordan Lee (Dev Mgr)
| Siemens Opcenter | Test |  |  | Chris Park (QA Lead)
| Siemens Opcenter | UAT |  |  | Monica Geller (Bus Analyst)
| Siemens Opcenter | Pre-prod |  |  | Ethan Black (Release Mgr)
| Siemens Opcenter | Prod |  |  | Elizabeth Crown (Ops Mgr)
| Siemens Opcenter | DR |  |  | William Guard (Infra Lead)
| Rockwell FactoryTalk | Dev | Edward Mueller | Paul Anderson | Casey Chen (Dev Mgr)
| Rockwell FactoryTalk | Test |  |  | Pat Murphy (QA Lead)
| Rockwell FactoryTalk | UAT |  |  | Phoebe Buffay (Bus Analyst)
| Rockwell FactoryTalk | Pre-prod |  |  | Lucas White (Release Mgr)
| Rockwell FactoryTalk | Prod |  |  | Catherine Royal (Ops Mgr)
| Rockwell FactoryTalk | DR |  |  | James Fortress (Infra Lead)
| AVEVA MES | Dev | Christine Larson | Michelle Davis | Morgan Taylor (Dev Mgr)
| AVEVA MES | Test |  |  | Jesse Garcia (QA Lead)
| AVEVA MES | UAT |  |  | Emma Watson (Bus Analyst)
| AVEVA MES | Pre-prod |  |  | Mason Gray (Release Mgr)
| AVEVA MES | Prod |  |  | Margaret Noble (Ops Mgr)
| AVEVA MES | DR |  |  | Michael Bastion (Infra Lead)
| Dassault DELMIA | Dev | George Volkov | Steven Nakamura | Jamie Patel (Dev Mgr)
| Dassault DELMIA | Test |  |  | Robin Chen (QA Lead)
| Dassault DELMIA | UAT |  |  | Sophie Turner (Bus Analyst)
| Dassault DELMIA | Pre-prod |  |  | Logan Stone (Release Mgr)
| Dassault DELMIA | Prod |  |  | Diana Prince (Ops Mgr)
| Dassault DELMIA | DR |  |  | David Tower (Infra Lead)
| Oracle Manufacturing Cloud | Dev | Deborah Nash | Teresa Gonzalez | Riley Kim (Dev Mgr)
| Oracle Manufacturing Cloud | Test |  |  | Dana Wilson (QA Lead)
| Oracle Manufacturing Cloud | UAT |  |  | Mia Collins (Bus Analyst)
| Oracle Manufacturing Cloud | Pre-prod |  |  | Jacob Hill (Release Mgr)
| Oracle Manufacturing Cloud | Prod |  |  | Helena Troy (Ops Mgr)
| Oracle Manufacturing Cloud | DR |  |  | Richard Wall (Infra Lead)
| Plex Smart Manufacturing | Dev | Harold Chen | Bruce Thompson | Quinn Johnson (Dev Mgr)
| Plex Smart Manufacturing | Test |  |  | Kelly Nguyen (QA Lead)
| Plex Smart Manufacturing | UAT |  |  | Isabella Moore (Bus Analyst)
| Plex Smart Manufacturing | Pre-prod |  |  | Aiden Clark (Release Mgr)
| Plex Smart Manufacturing | Prod |  |  | Sophia Grace (Ops Mgr)
| Plex Smart Manufacturing | DR |  |  | Thomas Castle (Infra Lead)
| Epicor Kinetic | Dev | Monica Fernandez | Angela Park | Avery Williams (Dev Mgr)
| Epicor Kinetic | Test |  |  | Terry Brooks (QA Lead)
| Epicor Kinetic | UAT |  |  | Olivia James (Bus Analyst)
| Epicor Kinetic | Pre-prod |  |  | Jackson Moore (Release Mgr)
| Epicor Kinetic | Prod |  |  | Alexandra Reid (Ops Mgr)
| Epicor Kinetic | DR |  |  | Charles Vault (Infra Lead)
| Infor CloudSuite Industrial | Dev | Russell White | Douglas Chen | Drew Martinez (Dev Mgr)
| Infor CloudSuite Industrial | Test |  |  | Skyler Davis (QA Lead)
| Infor CloudSuite Industrial | UAT |  |  | Ava Mitchell (Bus Analyst)
| Infor CloudSuite Industrial | Pre-prod |  |  | Sebastian Hall (Release Mgr)
| Infor CloudSuite Industrial | Prod |  |  | Christina Vale (Ops Mgr)
| Infor CloudSuite Industrial | DR |  |  | Daniel Bunker (Infra Lead)
| QAD Adaptive ERP | Dev | Janet Kowalski | Carolyn Reed | Cameron Brown (Dev Mgr)
| QAD Adaptive ERP | Test |  |  | Jordan Reed (QA Lead)
| QAD Adaptive ERP | UAT |  |  | Charlotte Price (Bus Analyst)
| QAD Adaptive ERP | Pre-prod |  |  | Caleb Young (Release Mgr)
| QAD Adaptive ERP | Prod |  |  | Natasha Roman (Ops Mgr)
| QAD Adaptive ERP | DR |  |  | Matthew Haven (Infra Lead)
IT | ServiceNow ITSM | Dev | Christopher Blake | Jeffrey Kumar | Alex Rivera (Dev Mgr)
| ServiceNow ITSM | Test |  |  | Sam Anderson (QA Lead)
| ServiceNow ITSM | UAT |  |  | Rachel Green (Bus Analyst)
| ServiceNow ITSM | Pre-prod |  |  | Nathan Cole (Release Mgr)
| ServiceNow ITSM | Prod |  |  | Victoria Sterling (Ops Mgr)
| ServiceNow ITSM | DR |  |  | Robert Shield (Infra Lead)
| BMC Remedy | Dev | Elizabeth Morgan | Stephanie Liu | Jordan Lee (Dev Mgr)
| BMC Remedy | Test |  |  | Chris Park (QA Lead)
| BMC Remedy | UAT |  |  | Monica Geller (Bus Analyst)
| BMC Remedy | Pre-prod |  |  | Ethan Black (Release Mgr)
| BMC Remedy | Prod |  |  | Elizabeth Crown (Ops Mgr)
| BMC Remedy | DR |  |  | William Guard (Infra Lead)
| Jira Service Management | Dev | Joseph Turner | Robert Chang | Casey Chen (Dev Mgr)
| Jira Service Management | Test |  |  | Pat Murphy (QA Lead)
| Jira Service Management | UAT |  |  | Phoebe Buffay (Bus Analyst)
| Jira Service Management | Pre-prod |  |  | Lucas White (Release Mgr)
| Jira Service Management | Prod |  |  | Catherine Royal (Ops Mgr)
| Jira Service Management | DR |  |  | James Fortress (Infra Lead)
| Splunk Enterprise | Dev | Margaret Sullivan | Karen Patel | Morgan Taylor (Dev Mgr)
| Splunk Enterprise | Test |  |  | Jesse Garcia (QA Lead)
| Splunk Enterprise | UAT |  |  | Emma Watson (Bus Analyst)
| Splunk Enterprise | Pre-prod |  |  | Mason Gray (Release Mgr)
| Splunk Enterprise | Prod |  |  | Margaret Noble (Ops Mgr)
| Splunk Enterprise | DR |  |  | Michael Bastion (Infra Lead)
| Dynatrace | Dev | Raymond Diaz | Brian Yamamoto | Jamie Patel (Dev Mgr)
| Dynatrace | Test |  |  | Robin Chen (QA Lead)
| Dynatrace | UAT |  |  | Sophie Turner (Bus Analyst)
| Dynatrace | Pre-prod |  |  | Logan Stone (Release Mgr)
| Dynatrace | Prod |  |  | Diana Prince (Ops Mgr)
| Dynatrace | DR |  |  | David Tower (Infra Lead)
| New Relic | Dev | Pamela Anderson | Lisa Hernandez | Riley Kim (Dev Mgr)
| New Relic | Test |  |  | Dana Wilson (QA Lead)
| New Relic | UAT |  |  | Mia Collins (Bus Analyst)
| New Relic | Pre-prod |  |  | Jacob Hill (Release Mgr)
| New Relic | Prod |  |  | Helena Troy (Ops Mgr)
| New Relic | DR |  |  | Richard Wall (Infra Lead)
| PagerDuty | Dev | Timothy Foster | Scott McKenzie | Quinn Johnson (Dev Mgr)
| PagerDuty | Test |  |  | Kelly Nguyen (QA Lead)
| PagerDuty | UAT |  |  | Isabella Moore (Bus Analyst)
| PagerDuty | Pre-prod |  |  | Aiden Clark (Release Mgr)
| PagerDuty | Prod |  |  | Sophia Grace (Ops Mgr)
| PagerDuty | DR |  |  | Thomas Castle (Infra Lead)
| Datadog | Dev | Diane Wilson | Nicole Chen | Avery Williams (Dev Mgr)
| Datadog | Test |  |  | Terry Brooks (QA Lead)
| Datadog | UAT |  |  | Olivia James (Bus Analyst)
| Datadog | Pre-prod |  |  | Jackson Moore (Release Mgr)
| Datadog | Prod |  |  | Alexandra Reid (Ops Mgr)
| Datadog | DR |  |  | Charles Vault (Infra Lead)
| Ansible Tower | Dev | Gary Martinez | Adam Roberts | Drew Martinez (Dev Mgr)
| Ansible Tower | Test |  |  | Skyler Davis (QA Lead)
| Ansible Tower | UAT |  |  | Ava Mitchell (Bus Analyst)
| Ansible Tower | Pre-prod |  |  | Sebastian Hall (Release Mgr)
| Ansible Tower | Prod |  |  | Christina Vale (Ops Mgr)
| Ansible Tower | DR |  |  | Daniel Bunker (Infra Lead)
| Terraform Enterprise | Dev | Barbara Collins | Katherine Wong | Cameron Brown (Dev Mgr)
| Terraform Enterprise | Test |  |  | Jordan Reed (QA Lead)
| Terraform Enterprise | UAT |  |  | Charlotte Price (Bus Analyst)
| Terraform Enterprise | Pre-prod |  |  | Caleb Young (Release Mgr)
| Terraform Enterprise | Prod |  |  | Natasha Roman (Ops Mgr)
| Terraform Enterprise | DR |  |  | Matthew Haven (Infra Lead)
HR | Workday HCM | Dev | Daniel Crawford | Nicholas Chen | Alex Rivera (Dev Mgr)
| Workday HCM | Test |  |  | Sam Anderson (QA Lead)
| Workday HCM | UAT |  |  | Rachel Green (Bus Analyst)
| Workday HCM | Pre-prod |  |  | Nathan Cole (Release Mgr)
| Workday HCM | Prod |  |  | Victoria Sterling (Ops Mgr)
| Workday HCM | DR |  |  | Robert Shield (Infra Lead)
| SAP SuccessFactors | Dev | Susan Perry | Amanda Foster | Jordan Lee (Dev Mgr)
| SAP SuccessFactors | Test |  |  | Chris Park (QA Lead)
| SAP SuccessFactors | UAT |  |  | Monica Geller (Bus Analyst)
| SAP SuccessFactors | Pre-prod |  |  | Ethan Black (Release Mgr)
| SAP SuccessFactors | Prod |  |  | Elizabeth Crown (Ops Mgr)
| SAP SuccessFactors | DR |  |  | William Guard (Infra Lead)
| Oracle HCM Cloud | Dev | William Hughes | Jonathan Park | Casey Chen (Dev Mgr)
| Oracle HCM Cloud | Test |  |  | Pat Murphy (QA Lead)
| Oracle HCM Cloud | UAT |  |  | Phoebe Buffay (Bus Analyst)
| Oracle HCM Cloud | Pre-prod |  |  | Lucas White (Release Mgr)
| Oracle HCM Cloud | Prod |  |  | Catherine Royal (Ops Mgr)
| Oracle HCM Cloud | DR |  |  | James Fortress (Infra Lead)
| ADP Workforce Now | Dev | Dorothy Barnes | Christine Lee | Morgan Taylor (Dev Mgr)
| ADP Workforce Now | Test |  |  | Jesse Garcia (QA Lead)
| ADP Workforce Now | UAT |  |  | Emma Watson (Bus Analyst)
| ADP Workforce Now | Pre-prod |  |  | Mason Gray (Release Mgr)
| ADP Workforce Now | Prod |  |  | Margaret Noble (Ops Mgr)
| ADP Workforce Now | DR |  |  | Michael Bastion (Infra Lead)
| UKG Pro | Dev | Frank Reynolds | Gregory Wang | Jamie Patel (Dev Mgr)
| UKG Pro | Test |  |  | Robin Chen (QA Lead)
| UKG Pro | UAT |  |  | Sophie Turner (Bus Analyst)
| UKG Pro | Pre-prod |  |  | Logan Stone (Release Mgr)
| UKG Pro | Prod |  |  | Diana Prince (Ops Mgr)
| UKG Pro | DR |  |  | David Tower (Infra Lead)
| Ceridian Dayforce | Dev | Helen Stewart | Melissa Johnson | Riley Kim (Dev Mgr)
| Ceridian Dayforce | Test |  |  | Dana Wilson (QA Lead)
| Ceridian Dayforce | UAT |  |  | Mia Collins (Bus Analyst)
| Ceridian Dayforce | Pre-prod |  |  | Jacob Hill (Release Mgr)
| Ceridian Dayforce | Prod |  |  | Helena Troy (Ops Mgr)
| Ceridian Dayforce | DR |  |  | Richard Wall (Infra Lead)
| BambooHR | Dev | Keith Nelson | Eric Tanaka | Quinn Johnson (Dev Mgr)
| BambooHR | Test |  |  | Kelly Nguyen (QA Lead)
| BambooHR | UAT |  |  | Isabella Moore (Bus Analyst)
| BambooHR | Pre-prod |  |  | Aiden Clark (Release Mgr)
| BambooHR | Prod |  |  | Sophia Grace (Ops Mgr)
| BambooHR | DR |  |  | Thomas Castle (Infra Lead)
| Cornerstone OnDemand | Dev | Gloria Ramirez | Patricia Kim | Avery Williams (Dev Mgr)
| Cornerstone OnDemand | Test |  |  | Terry Brooks (QA Lead)
| Cornerstone OnDemand | UAT |  |  | Olivia James (Bus Analyst)
| Cornerstone OnDemand | Pre-prod |  |  | Jackson Moore (Release Mgr)
| Cornerstone OnDemand | Prod |  |  | Alexandra Reid (Ops Mgr)
| Cornerstone OnDemand | DR |  |  | Charles Vault (Infra Lead)
| Greenhouse | Dev | Ronald Cooper | Howard Lin | Drew Martinez (Dev Mgr)
| Greenhouse | Test |  |  | Skyler Davis (QA Lead)
| Greenhouse | UAT |  |  | Ava Mitchell (Bus Analyst)
| Greenhouse | Pre-prod |  |  | Sebastian Hall (Release Mgr)
| Greenhouse | Prod |  |  | Christina Vale (Ops Mgr)
| Greenhouse | DR |  |  | Daniel Bunker (Infra Lead)
| LinkedIn Talent Solutions | Dev | Ruth Simmons | Sandra Mitchell | Cameron Brown (Dev Mgr)
| LinkedIn Talent Solutions | Test |  |  | Jordan Reed (QA Lead)
| LinkedIn Talent Solutions | UAT |  |  | Charlotte Price (Bus Analyst)
| LinkedIn Talent Solutions | Pre-prod |  |  | Caleb Young (Release Mgr)
| LinkedIn Talent Solutions | Prod |  |  | Natasha Roman (Ops Mgr)
| LinkedIn Talent Solutions | DR |  |  | Matthew Haven (Infra Lead)
Legal | Thomson Reuters Legal Tracker | Dev | Howard Blackwell | Jeremy Thompson | Alex Rivera (Dev Mgr)
| Thomson Reuters Legal Tracker | Test |  |  | Sam Anderson (QA Lead)
| Thomson Reuters Legal Tracker | UAT |  |  | Rachel Green (Bus Analyst)
| Thomson Reuters Legal Tracker | Pre-prod |  |  | Nathan Cole (Release Mgr)
| Thomson Reuters Legal Tracker | Prod |  |  | Victoria Sterling (Ops Mgr)
| Thomson Reuters Legal Tracker | DR |  |  | Robert Shield (Infra Lead)
| Mitratech TeamConnect | Dev | Cynthia Drake | Kimberly Chen | Jordan Lee (Dev Mgr)
| Mitratech TeamConnect | Test |  |  | Chris Park (QA Lead)
| Mitratech TeamConnect | UAT |  |  | Monica Geller (Bus Analyst)
| Mitratech TeamConnect | Pre-prod |  |  | Ethan Black (Release Mgr)
| Mitratech TeamConnect | Prod |  |  | Elizabeth Crown (Ops Mgr)
| Mitratech TeamConnect | DR |  |  | William Guard (Infra Lead)
| Wolters Kluwer ELM Solutions | Dev | Vincent Marshall | Patrick Sullivan | Casey Chen (Dev Mgr)
| Wolters Kluwer ELM Solutions | Test |  |  | Pat Murphy (QA Lead)
| Wolters Kluwer ELM Solutions | UAT |  |  | Phoebe Buffay (Bus Analyst)
| Wolters Kluwer ELM Solutions | Pre-prod |  |  | Lucas White (Release Mgr)
| Wolters Kluwer ELM Solutions | Prod |  |  | Catherine Royal (Ops Mgr)
| Wolters Kluwer ELM Solutions | DR |  |  | James Fortress (Infra Lead)
| ContractPodAi | Dev | Evelyn Rhodes | Diana Wong | Morgan Taylor (Dev Mgr)
| ContractPodAi | Test |  |  | Jesse Garcia (QA Lead)
| ContractPodAi | UAT |  |  | Emma Watson (Bus Analyst)
| ContractPodAi | Pre-prod |  |  | Mason Gray (Release Mgr)
| ContractPodAi | Prod |  |  | Margaret Noble (Ops Mgr)
| ContractPodAi | DR |  |  | Michael Bastion (Infra Lead)
| Ironclad | Dev | Lawrence Griffin | Raymond Lee | Jamie Patel (Dev Mgr)
| Ironclad | Test |  |  | Robin Chen (QA Lead)
| Ironclad | UAT |  |  | Sophie Turner (Bus Analyst)
| Ironclad | Pre-prod |  |  | Logan Stone (Release Mgr)
| Ironclad | Prod |  |  | Diana Prince (Ops Mgr)
| Ironclad | DR |  |  | David Tower (Infra Lead)
| DocuSign CLM | Dev | Judith Palmer | Vanessa Garcia | Riley Kim (Dev Mgr)
| DocuSign CLM | Test |  |  | Dana Wilson (QA Lead)
| DocuSign CLM | UAT |  |  | Mia Collins (Bus Analyst)
| DocuSign CLM | Pre-prod |  |  | Jacob Hill (Release Mgr)
| DocuSign CLM | Prod |  |  | Helena Troy (Ops Mgr)
| DocuSign CLM | DR |  |  | Richard Wall (Infra Lead)
| Conga Contracts | Dev | Stanley Cross | Derek Martin | Quinn Johnson (Dev Mgr)
| Conga Contracts | Test |  |  | Kelly Nguyen (QA Lead)
| Conga Contracts | UAT |  |  | Isabella Moore (Bus Analyst)
| Conga Contracts | Pre-prod |  |  | Aiden Clark (Release Mgr)
| Conga Contracts | Prod |  |  | Sophia Grace (Ops Mgr)
| Conga Contracts | DR |  |  | Thomas Castle (Infra Lead)
| Agiloft CLM | Dev | Marilyn Webb | Julie Park | Avery Williams (Dev Mgr)
| Agiloft CLM | Test |  |  | Terry Brooks (QA Lead)
| Agiloft CLM | UAT |  |  | Olivia James (Bus Analyst)
| Agiloft CLM | Pre-prod |  |  | Jackson Moore (Release Mgr)
| Agiloft CLM | Prod |  |  | Alexandra Reid (Ops Mgr)
| Agiloft CLM | DR |  |  | Charles Vault (Infra Lead)
| SimpleLegal | Dev | Leonard Foster | Marcus Davis | Drew Martinez (Dev Mgr)
| SimpleLegal | Test |  |  | Skyler Davis (QA Lead)
| SimpleLegal | UAT |  |  | Ava Mitchell (Bus Analyst)
| SimpleLegal | Pre-prod |  |  | Sebastian Hall (Release Mgr)
| SimpleLegal | Prod |  |  | Christina Vale (Ops Mgr)
| SimpleLegal | DR |  |  | Daniel Bunker (Infra Lead)
| Onit | Dev | Theresa Quinn | Eleanor Kim | Cameron Brown (Dev Mgr)
| Onit | Test |  |  | Jordan Reed (QA Lead)
| Onit | UAT |  |  | Charlotte Price (Bus Analyst)
| Onit | Pre-prod |  |  | Caleb Young (Release Mgr)
| Onit | Prod |  |  | Natasha Roman (Ops Mgr)
| Onit | DR |  |  | Matthew Haven (Infra Lead)
Security | CrowdStrike Falcon | Dev | Charles Hamilton | Donald Chen | Alex Rivera (Dev Mgr)
| CrowdStrike Falcon | Test |  |  | Sam Anderson (QA Lead)
| CrowdStrike Falcon | UAT |  |  | Rachel Green (Bus Analyst)
| CrowdStrike Falcon | Pre-prod |  |  | Nathan Cole (Release Mgr)
| CrowdStrike Falcon | Prod |  |  | Victoria Sterling (Ops Mgr)
| CrowdStrike Falcon | DR |  |  | Robert Shield (Infra Lead)
| Palo Alto Cortex XDR | Dev | Nancy Porter | Sarah Yamamoto | Jordan Lee (Dev Mgr)
| Palo Alto Cortex XDR | Test |  |  | Chris Park (QA Lead)
| Palo Alto Cortex XDR | UAT |  |  | Monica Geller (Bus Analyst)
| Palo Alto Cortex XDR | Pre-prod |  |  | Ethan Black (Release Mgr)
| Palo Alto Cortex XDR | Prod |  |  | Elizabeth Crown (Ops Mgr)
| Palo Alto Cortex XDR | DR |  |  | William Guard (Infra Lead)
| Splunk SIEM | Dev | Franklin Shaw | Bruce Lee | Casey Chen (Dev Mgr)
| Splunk SIEM | Test |  |  | Pat Murphy (QA Lead)
| Splunk SIEM | UAT |  |  | Phoebe Buffay (Bus Analyst)
| Splunk SIEM | Pre-prod |  |  | Lucas White (Release Mgr)
| Splunk SIEM | Prod |  |  | Catherine Royal (Ops Mgr)
| Splunk SIEM | DR |  |  | James Fortress (Infra Lead)
| Microsoft Sentinel | Dev | Joan Mitchell | Michelle Patel | Morgan Taylor (Dev Mgr)
| Microsoft Sentinel | Test |  |  | Jesse Garcia (QA Lead)
| Microsoft Sentinel | UAT |  |  | Emma Watson (Bus Analyst)
| Microsoft Sentinel | Pre-prod |  |  | Mason Gray (Release Mgr)
| Microsoft Sentinel | Prod |  |  | Margaret Noble (Ops Mgr)
| Microsoft Sentinel | DR |  |  | Michael Bastion (Infra Lead)
| Okta Identity Cloud | Dev | Gerald Davidson | Victor Wang | Jamie Patel (Dev Mgr)
| Okta Identity Cloud | Test |  |  | Robin Chen (QA Lead)
| Okta Identity Cloud | UAT |  |  | Sophie Turner (Bus Analyst)
| Okta Identity Cloud | Pre-prod |  |  | Logan Stone (Release Mgr)
| Okta Identity Cloud | Prod |  |  | Diana Prince (Ops Mgr)
| Okta Identity Cloud | DR |  |  | David Tower (Infra Lead)
| CyberArk PAM | Dev | Alice Brennan | Cynthia Kim | Riley Kim (Dev Mgr)
| CyberArk PAM | Test |  |  | Dana Wilson (QA Lead)
| CyberArk PAM | UAT |  |  | Mia Collins (Bus Analyst)
| CyberArk PAM | Pre-prod |  |  | Jacob Hill (Release Mgr)
| CyberArk PAM | Prod |  |  | Helena Troy (Ops Mgr)
| CyberArk PAM | DR |  |  | Richard Wall (Infra Lead)
| Qualys VMDR | Dev | Eugene Watts | Arthur Santos | Quinn Johnson (Dev Mgr)
| Qualys VMDR | Test |  |  | Kelly Nguyen (QA Lead)
| Qualys VMDR | UAT |  |  | Isabella Moore (Bus Analyst)
| Qualys VMDR | Pre-prod |  |  | Aiden Clark (Release Mgr)
| Qualys VMDR | Prod |  |  | Sophia Grace (Ops Mgr)
| Qualys VMDR | DR |  |  | Thomas Castle (Infra Lead)
| Tenable.io | Dev | Marie Coleman | Linda Nguyen | Avery Williams (Dev Mgr)
| Tenable.io | Test |  |  | Terry Brooks (QA Lead)
| Tenable.io | UAT |  |  | Olivia James (Bus Analyst)
| Tenable.io | Pre-prod |  |  | Jackson Moore (Release Mgr)
| Tenable.io | Prod |  |  | Alexandra Reid (Ops Mgr)
| Tenable.io | DR |  |  | Charles Vault (Infra Lead)
| Zscaler | Dev | Henry Sutton | Norman Park | Drew Martinez (Dev Mgr)
| Zscaler | Test |  |  | Skyler Davis (QA Lead)
| Zscaler | UAT |  |  | Ava Mitchell (Bus Analyst)
| Zscaler | Pre-prod |  |  | Sebastian Hall (Release Mgr)
| Zscaler | Prod |  |  | Christina Vale (Ops Mgr)
| Zscaler | DR |  |  | Daniel Bunker (Infra Lead)
| Proofpoint | Dev | Grace Hartley | Betty Liu | Cameron Brown (Dev Mgr)
| Proofpoint | Test |  |  | Jordan Reed (QA Lead)
| Proofpoint | UAT |  |  | Charlotte Price (Bus Analyst)
| Proofpoint | Pre-prod |  |  | Caleb Young (Release Mgr)
| Proofpoint | Prod |  |  | Natasha Roman (Ops Mgr)
| Proofpoint | DR |  |  | Matthew Haven (Infra Lead)

## Users
User ID | Name | Email | Role | Department | Manager | Access Level | Status | Last Login
USR-001 | Alex Rivera | alex.rivera@company.com | Development Manager | IT | CTO Office | Admin | Active | 2026-06-25
USR-002 | Jordan Lee | jordan.lee@company.com | Development Manager | IT | CTO Office | Admin | Active | 2026-06-25
USR-003 | Casey Chen | casey.chen@company.com | Development Manager | IT | CTO Office | Admin | Active | 2026-06-24
USR-004 | Morgan Taylor | morgan.taylor@company.com | Development Manager | IT | CTO Office | Admin | Active | 2026-06-25
USR-005 | Jamie Patel | jamie.patel@company.com | Development Manager | IT | CTO Office | Admin | Active | 2026-06-24
USR-006 | Riley Kim | riley.kim@company.com | Development Manager | IT | CTO Office | Admin | Active | 2026-06-25
USR-007 | Quinn Johnson | quinn.johnson@company.com | Development Manager | IT | CTO Office | Admin | Active | 2026-06-23
USR-008 | Avery Williams | avery.williams@company.com | Development Manager | IT | CTO Office | Admin | Active | 2026-06-25
USR-009 | Drew Martinez | drew.martinez@company.com | Development Manager | IT | CTO Office | Admin | Active | 2026-06-24
USR-010 | Cameron Brown | cameron.brown@company.com | Development Manager | IT | CTO Office | Admin | Active | 2026-06-25
USR-011 | Taylor Singh | taylor.singh@company.com | Development Manager | IT | CTO Office | Admin | Active | 2026-06-22
USR-012 | Blake Thompson | blake.thompson@company.com | Development Manager | IT | CTO Office | Admin | Active | 2026-06-25
USR-013 | Sam Anderson | sam.anderson@company.com | QA Lead | QA | QA Director | Standard | Active | 2026-06-25
USR-014 | Chris Park | chris.park@company.com | QA Lead | QA | QA Director | Standard | Active | 2026-06-25
USR-015 | Pat Murphy | pat.murphy@company.com | QA Lead | QA | QA Director | Standard | Active | 2026-06-24
USR-016 | Jesse Garcia | jesse.garcia@company.com | QA Lead | QA | QA Director | Standard | Active | 2026-06-25
USR-017 | Robin Chen | robin.chen@company.com | QA Lead | QA | QA Director | Standard | Active | 2026-06-23
USR-018 | Dana Wilson | dana.wilson@company.com | QA Lead | QA | QA Director | Standard | Active | 2026-06-25
USR-019 | Kelly Nguyen | kelly.nguyen@company.com | QA Lead | QA | QA Director | Standard | Active | 2026-06-24
USR-020 | Terry Brooks | terry.brooks@company.com | QA Lead | QA | QA Director | Standard | Active | 2026-06-25
USR-021 | Skyler Davis | skyler.davis@company.com | QA Lead | QA | QA Director | Standard | Active | 2026-06-25
USR-022 | Jordan Reed | jordan.reed@company.com | QA Lead | QA | QA Director | Standard | Active | 2026-06-22
USR-023 | Alex Foster | alex.foster@company.com | QA Lead | QA | QA Director | Standard | Active | 2026-06-25
USR-024 | Morgan Hayes | morgan.hayes@company.com | QA Lead | QA | QA Director | Standard | Active | 2026-06-24
USR-025 | Rachel Green | rachel.green@company.com | Business Analyst | Business Ops | BA Manager | Standard | Active | 2026-06-25
USR-026 | Monica Geller | monica.geller@company.com | Business Analyst | Business Ops | BA Manager | Standard | Active | 2026-06-25
USR-027 | Phoebe Buffay | phoebe.buffay@company.com | Business Analyst | Business Ops | BA Manager | Standard | Active | 2026-06-24
USR-028 | Emma Watson | emma.watson@company.com | Business Analyst | Business Ops | BA Manager | Standard | Active | 2026-06-25
USR-029 | Sophie Turner | sophie.turner@company.com | Business Analyst | Business Ops | BA Manager | Standard | Active | 2026-06-23
USR-030 | Mia Collins | mia.collins@company.com | Business Analyst | Business Ops | BA Manager | Standard | Active | 2026-06-25
USR-031 | Isabella Moore | isabella.moore@company.com | Business Analyst | Business Ops | BA Manager | Standard | Active | 2026-06-24
USR-032 | Olivia James | olivia.james@company.com | Business Analyst | Business Ops | BA Manager | Standard | Active | 2026-06-25
USR-033 | Ava Mitchell | ava.mitchell@company.com | Business Analyst | Business Ops | BA Manager | Standard | Active | 2026-06-25
USR-034 | Charlotte Price | charlotte.price@company.com | Business Analyst | Business Ops | BA Manager | Standard | Active | 2026-06-22
USR-035 | Amelia Scott | amelia.scott@company.com | Business Analyst | Business Ops | BA Manager | Standard | Active | 2026-06-25
USR-036 | Harper Lewis | harper.lewis@company.com | Business Analyst | Business Ops | BA Manager | Standard | Active | 2026-06-24
USR-037 | Nathan Cole | nathan.cole@company.com | Release Manager | IT | IT Director | Admin | Active | 2026-06-25
USR-038 | Ethan Black | ethan.black@company.com | Release Manager | IT | IT Director | Admin | Active | 2026-06-25
USR-039 | Lucas White | lucas.white@company.com | Release Manager | IT | IT Director | Admin | Active | 2026-06-24
USR-040 | Mason Gray | mason.gray@company.com | Release Manager | IT | IT Director | Admin | Active | 2026-06-25
USR-041 | Logan Stone | logan.stone@company.com | Release Manager | IT | IT Director | Admin | Active | 2026-06-23
USR-042 | Jacob Hill | jacob.hill@company.com | Release Manager | IT | IT Director | Admin | Active | 2026-06-25
USR-043 | Aiden Clark | aiden.clark@company.com | Release Manager | IT | IT Director | Admin | Active | 2026-06-24
USR-044 | Jackson Moore | jackson.moore@company.com | Release Manager | IT | IT Director | Admin | Active | 2026-06-25
USR-045 | Sebastian Hall | sebastian.hall@company.com | Release Manager | IT | IT Director | Admin | Active | 2026-06-25
USR-046 | Caleb Young | caleb.young@company.com | Release Manager | IT | IT Director | Admin | Active | 2026-06-22
USR-047 | Owen King | owen.king@company.com | Release Manager | IT | IT Director | Admin | Active | 2026-06-25
USR-048 | Liam Wright | liam.wright@company.com | Release Manager | IT | IT Director | Admin | Active | 2026-06-24
USR-049 | Victoria Sterling | victoria.sterling@company.com | Operations Manager | Operations | VP Operations | Admin | Active | 2026-06-25
USR-050 | Elizabeth Crown | elizabeth.crown@company.com | Operations Manager | Operations | VP Operations | Admin | Active | 2026-06-25
USR-051 | Catherine Royal | catherine.royal@company.com | Operations Manager | Operations | VP Operations | Admin | Active | 2026-06-24
USR-052 | Margaret Noble | margaret.noble@company.com | Operations Manager | Operations | VP Operations | Admin | Active | 2026-06-25
USR-053 | Diana Prince | diana.prince@company.com | Operations Manager | Operations | VP Operations | Admin | Active | 2026-06-23
USR-054 | Helena Troy | helena.troy@company.com | Operations Manager | Operations | VP Operations | Admin | Active | 2026-06-25
USR-055 | Sophia Grace | sophia.grace@company.com | Operations Manager | Operations | VP Operations | Admin | Active | 2026-06-24
USR-056 | Alexandra Reid | alexandra.reid@company.com | Operations Manager | Operations | VP Operations | Admin | Active | 2026-06-25
USR-057 | Christina Vale | christina.vale@company.com | Operations Manager | Operations | VP Operations | Admin | Active | 2026-06-25
USR-058 | Natasha Roman | natasha.roman@company.com | Operations Manager | Operations | VP Operations | Admin | Active | 2026-06-22
USR-059 | Amanda Cross | amanda.cross@company.com | Operations Manager | Operations | VP Operations | Admin | Active | 2026-06-25
USR-060 | Rebecca Stone | rebecca.stone@company.com | Operations Manager | Operations | VP Operations | Admin | Active | 2026-06-24
USR-061 | Robert Shield | robert.shield@company.com | Infrastructure Lead | Infrastructure | Infra Director | Admin | Active | 2026-06-25
USR-062 | William Guard | william.guard@company.com | Infrastructure Lead | Infrastructure | Infra Director | Admin | Active | 2026-06-25
USR-063 | James Fortress | james.fortress@company.com | Infrastructure Lead | Infrastructure | Infra Director | Admin | Active | 2026-06-24
USR-064 | Michael Bastion | michael.bastion@company.com | Infrastructure Lead | Infrastructure | Infra Director | Admin | Active | 2026-06-25
USR-065 | David Tower | david.tower@company.com | Infrastructure Lead | Infrastructure | Infra Director | Admin | Active | 2026-06-23
USR-066 | Richard Wall | richard.wall@company.com | Infrastructure Lead | Infrastructure | Infra Director | Admin | Active | 2026-06-25
USR-067 | Thomas Castle | thomas.castle@company.com | Infrastructure Lead | Infrastructure | Infra Director | Admin | Active | 2026-06-24
USR-068 | Charles Vault | charles.vault@company.com | Infrastructure Lead | Infrastructure | Infra Director | Admin | Active | 2026-06-25
USR-069 | Daniel Bunker | daniel.bunker@company.com | Infrastructure Lead | Infrastructure | Infra Director | Admin | Active | 2026-06-25
USR-070 | Matthew Haven | matthew.haven@company.com | Infrastructure Lead | Infrastructure | Infra Director | Admin | Active | 2026-06-22
USR-071 | Anthony Secure | anthony.secure@company.com | Infrastructure Lead | Infrastructure | Infra Director | Admin | Active | 2026-06-25
USR-072 | Mark Backup | mark.backup@company.com | Infrastructure Lead | Infrastructure | Infra Director | Admin | Active | 2026-06-24
USR-073 | Sarah Mitchell | sarah.mitchell@company.com | Application Owner | Finance | Finance Director | Standard | Active | 2026-06-25
USR-074 | David Chen | david.chen@company.com | Application Owner | Finance | Finance Director | Standard | Active | 2026-06-24
USR-075 | Brian Murphy | brian.murphy@company.com | Application Owner | Logistics | Logistics Director | Standard | Active | 2026-06-25
USR-076 | Matthew Clarke | matthew.clarke@company.com | Application Owner | CRM | Sales Director | Standard | Active | 2026-06-23
USR-077 | Richard Hoffman | richard.hoffman@company.com | Application Owner | Manufacturing | Mfg Director | Standard | Active | 2026-06-25
USR-078 | Christopher Blake | christopher.blake@company.com | Application Owner | IT | IT Director | Standard | Active | 2026-06-24
USR-079 | Daniel Crawford | daniel.crawford@company.com | Application Owner | HR | HR Director | Standard | Active | 2026-06-25
USR-080 | Howard Blackwell | howard.blackwell@company.com | Application Owner | Legal | Legal Director | Standard | Active | 2026-06-25
USR-081 | Charles Hamilton | charles.hamilton@company.com | Application Owner | Security | CISO | Standard | Active | 2026-06-22
USR-082 | James Wilson | james.wilson@company.com | Tech Lead | Finance | App Owner | Standard | Active | 2026-06-25
USR-083 | Marcus Johnson | marcus.johnson@company.com | Tech Lead | Logistics | App Owner | Standard | Active | 2026-06-24
USR-084 | Carlos Mendez | carlos.mendez@company.com | Tech Lead | CRM | App Owner | Standard | Active | 2026-06-25
USR-085 | Kenneth Wright | kenneth.wright@company.com | Tech Lead | Manufacturing | App Owner | Standard | Active | 2026-06-23
USR-086 | Jeffrey Kumar | jeffrey.kumar@company.com | Tech Lead | IT | App Owner | Standard | Active | 2026-06-25
USR-087 | Nicholas Chen | nicholas.chen@company.com | Tech Lead | HR | App Owner | Standard | Active | 2026-06-24
USR-088 | Michael Sterling | michael.sterling@company.com | CTO | Executive | CEO | Executive | Active | 2026-06-25
USR-089 | Jennifer Morrison | jennifer.morrison@company.com | CIO | Executive | CEO | Executive | Active | 2026-06-25
USR-090 | Robert Anderson | robert.anderson@company.com | CFO | Executive | CEO | Executive | Active | 2026-06-22
USR-091 | Linda Prescott | linda.prescott@company.com | VP Engineering | IT | CTO | Executive | Active | 2026-06-25
USR-092 | Thomas Reynolds | thomas.reynolds@company.com | VP Operations | Operations | COO | Executive | Active | 2026-06-24
USR-093 | Emily Zhang | emily.zhang@company.com | Senior Developer | IT | Dev Manager | Standard | Active | 2026-06-25
USR-094 | Michael Brown | michael.brown@company.com | Senior Developer | IT | Dev Manager | Standard | Active | 2026-06-23
USR-095 | Priya Sharma | priya.sharma@company.com | Database Admin | IT | Infra Lead | Standard | Active | 2026-06-25
USR-096 | Angela Liu | angela.liu@company.com | Systems Analyst | IT | BA Manager | Standard | Active | 2026-06-24
USR-097 | Ryan Cooper | ryan.cooper@company.com | DevOps Engineer | IT | Infra Lead | Standard | Active | 2026-06-25
USR-098 | Jessica Nguyen | jessica.nguyen@company.com | Security Analyst | Security | CISO | Standard | Active | 2026-06-25
USR-099 | Brandon Lee | brandon.lee@company.com | Network Engineer | IT | Infra Lead | Standard | Active | 2026-06-22
USR-100 | Michelle Davis | michelle.davis@company.com | Project Manager | PMO | PMO Director | Standard | Active | 2026-06-25

## Admin (Release Managers)
ID | Name | Email | Department | Region | Phone | Status | Start Date | Specialization
RM-001 | Nathan Cole | nathan.cole@company.com | IT | North America | +1-555-0101 | Active | 2020-03-15 | Finance & HR Systems
RM-002 | Ethan Black | ethan.black@company.com | IT | North America | +1-555-0102 | Active | 2019-06-20 | Manufacturing & Logistics
RM-003 | Lucas White | lucas.white@company.com | IT | EMEA | +44-20-5550103 | Active | 2021-01-10 | CRM & Sales Systems
RM-004 | Mason Gray | mason.gray@company.com | IT | EMEA | +44-20-5550104 | Active | 2018-09-01 | Security & Infrastructure
RM-005 | Logan Stone | logan.stone@company.com | IT | APAC | +61-2-5550105 | Active | 2020-11-15 | Legal & Compliance
RM-006 | Jacob Hill | jacob.hill@company.com | IT | APAC | +61-2-5550106 | Active | 2022-02-28 | HR & Talent Systems
RM-007 | Aiden Clark | aiden.clark@company.com | IT | North America | +1-555-0107 | Active | 2019-04-12 | Integration & Middleware
RM-008 | Jackson Moore | jackson.moore@company.com | IT | EMEA | +44-20-5550108 | Active | 2021-07-22 | Data & Analytics
RM-009 | Sebastian Hall | sebastian.hall@company.com | IT | LATAM | +55-11-5550109 | Active | 2020-08-05 | ERP Systems
RM-010 | Caleb Young | caleb.young@company.com | IT | North America | +1-555-0110 | Active | 2017-12-01 | Cloud & SaaS Platforms
RM-011 | Owen King | owen.king@company.com | IT | APAC | +65-5550111 | Active | 2022-05-18 | Manufacturing Execution
RM-012 | Liam Wright | liam.wright@company.com | IT | EMEA | +49-30-5550112 | On Leave | 2019-10-30 | Finance Reporting

## Super Admins
Admin ID | Name | Email | Title | Department | Access Scope | Granted Date | Granted By | Status | Expiry Date | Notes
SA-001 | Michael Stevens | michael.stevens@company.com | Chief Information Officer | IT | Global - All Systems | 2022-03-15 | CEO Office | Active | 2027-03-15 | Executive sponsor for all IT initiatives
SA-002 | Jennifer Walsh | jennifer.walsh@company.com | VP of Enterprise Applications | IT | Global - All Systems | 2023-01-10 | Michael Stevens | Active | 2027-01-10 | Oversight of all enterprise systems
SA-003 | Christopher Blake | christopher.blake@company.com | Director of IT Operations | IT | Global - Infrastructure | 2023-06-20 | Jennifer Walsh | Active | 2026-12-31 | 24/7 operations oversight
SA-004 | Elizabeth Morgan | elizabeth.morgan@company.com | Head of Cybersecurity | Security | Global - All Systems | 2022-08-01 | Michael Stevens | Active | 2027-08-01 | Security incident response authority
SA-005 | Robert Chen | robert.chen@company.com | Chief Technology Officer | IT | Global - All Systems | 2021-05-10 | CEO Office | Active | 2027-05-10 | Technical architecture decisions
SA-006 | Patricia Wong | patricia.wong@company.com | Director of Release Management | IT | Global - Release Systems | 2024-02-15 | Jennifer Walsh | Active | 2026-08-15 | Emergency release authority
SA-007 | Daniel Crawford | daniel.crawford@company.com | VP of HR Technology | HR | HR Systems - Global | 2023-09-01 | Jennifer Walsh | Active | 2026-09-01 | HR data governance
SA-008 | Sarah Mitchell | sarah.mitchell@company.com | VP of Finance Systems | Finance | Finance Systems - Global | 2023-04-15 | Michael Stevens | Active | 2026-10-15 | Financial data authority
SA-009 | Raymond Diaz | raymond.diaz@company.com | Cloud Platform Architect | IT | Global - Cloud Infrastructure | 2024-01-05 | Robert Chen | Active | 2026-07-05 | AWS/Azure/GCP root access
SA-010 | Margaret Sullivan | margaret.sullivan@company.com | Identity & Access Manager | Security | Global - IAM Systems | 2023-11-20 | Elizabeth Morgan | Active | 2026-11-20 | Identity management authority
SA-011 | Timothy Foster | timothy.foster@company.com | Disaster Recovery Manager | IT | Global - DR Systems | 2024-03-10 | Christopher Blake | Active | 2026-09-10 | DR failover authority
SA-012 | Diane Wilson | diane.wilson@company.com | Database Administrator Lead | IT | Global - Databases | 2023-07-15 | Christopher Blake | Active | 2026-07-15 | DBA root access all environments
⚠️ RESTRICTED ACCESS: Super Admin privileges require CIO or CEO approval. Access is audited and reviewed quarterly.

## Releases
🔍 FILTERS
Department: | All | Application: | All | Time Period: | All Time | Status: | All | Conflict: | All
Showing: | 80 of 80 releases | [9 empty] | 💡 Change filter values above to filter releases. Matching rows are highlighted in green; non-matching rows are greyed out.
Release ID | Release Name | Department | Application | Dependencies | Release Size | Impact | Priority | CAB Date | Start Date | End Date | Test Env Required | UAT Env Required | Status | Conflict Flag | Notes | Readiness % | Blockers | Vendor Maintenance | Change Freeze | Regulatory | Release Owner ID | Approval Status | Depends On | Rollback Plan | Go-Live Checklist % | Stakeholder IDs | Deployment Window | Filter Match
REL-0001 | Kyriba UI Tweak v4.5 | Finance | Kyriba | NA | Small | Low | P4 - Low | 2026-06-28 | 2026-06-30 | 2026-06-30 | FIN-TEST-01 | FIN-UAT-01 | Blocked | ⚠️ CONFLICT | Resource conflict with REL-0003 - Same Test/UAT env required | 75% | Environment conflict with REL-0003; awaiting conflict resolution meeting |  | Quarter-End Freeze |  | USR-061 | On Hold |  | At Risk | 79% | USR-073,USR-085,USR-097 | Off-Peak | TRUE
REL-0002 | Blue Workflow Automation v2.1 | Logistics | Blue Yonder WMS | NA | Medium | High | P1 - Critical | 2026-07-02 | 2026-07-04 | 2026-07-05 | LOG-TEST-01 | LOG-UAT-01 | Approved |  | Executive sponsor: CFO | 95% |  |  |  |  | USR-062 | CAB Approved |  | Ready | 85% | USR-074,USR-086,USR-098 | Weekend | TRUE
REL-0003 | Zendesk Minor Update v4.3 | CRM | Zendesk | NA | Small | Low | P3 - Medium | 2026-06-30 | 2026-07-02 | 2026-07-02 | FIN-TEST-01 | FIN-UAT-01 | Approved | ⚠️ CONFLICT | Resource conflict with REL-0007 - Same Test/UAT env required | 70% | Shared UAT env with REL-0001; QA sign-off pending |  |  |  | USR-063 | CAB Approved |  | Ready | 91% | USR-075,USR-087,USR-097 | Business Hours | TRUE
REL-0004 | AVEVA Dashboard Upgrade v5.5 | Manufacturing | AVEVA MES | NA | Medium | High | P1 - Critical | 2026-07-10 | 2026-07-12 | 2026-07-13 | MAN-TEST-03 | MAN-UAT-01 | Pending CAB |  | Blackout period consideration | 88% |  |  |  |  | USR-064 | CAB Submitted |  | In Progress | 78% | USR-076,USR-088,USR-098 | Weekend | TRUE
REL-0005 | Datadog Security Patch Bundle v3.5 | IT | Datadog | NA | Medium | High | P2 - High | 2026-07-14 | 2026-07-16 | 2026-07-17 | IT-TEST-01 | IT-UAT-01 | Testing | ⚠️ CONFLICT | Resource conflict with REL-0010 - Same Test/UAT env required | 80% | Security review in progress; awaiting CISO approval |  |  |  | USR-065 | Testing |  | In Progress | 52% | USR-077,USR-089,USR-097 | Off-Peak | TRUE
REL-0006 | SAP Configuration Change v5.2 | HR | SAP SuccessFactors | NA | Small | Medium | P2 - High | 2026-07-18 | 2026-07-20 | 2026-07-20 | HR-TEST-01 | HR-UAT-01 | Testing |  | Integration testing with downstream systems | 82% |  |  |  |  | USR-066 | Testing |  | In Progress | 64% | USR-078,USR-090,USR-098 | Business Hours | TRUE
REL-0007 | Mitratech Integration Enhancement v5.2 | Legal | Mitratech TeamConnect | NA | Medium | High | P2 - High | 2026-07-02 | 2026-07-04 | 2026-07-05 | FIN-TEST-01 | FIN-UAT-01 | Approved | ⚠️ CONFLICT | Resource conflict with REL-0012 - Same Test/UAT env required | 65% | Integration testing delayed; 3rd party API dependency unresolved |  |  |  | USR-067 | CAB Approved |  | Ready | 88% | USR-079,USR-091,USR-097 | Weekend | TRUE
REL-0008 | CrowdStrike Minor Update v3.6 | Security | CrowdStrike Falcon | NA | Small | Low | P3 - Medium | 2026-07-29 | 2026-07-31 | 2026-07-31 | SEC-TEST-01 | SEC-UAT-02 | Planning |  | Data migration included | 70% |  |  |  |  | USR-068 | Planning |  | Not Started | 26% | USR-080,USR-092,USR-098 | Off-Peak | TRUE
REL-0009 | Oracle Report Fix v3.4 | Finance | Oracle Hyperion HFM |  | Small | Medium | P2 - High | 2026-08-02 | 2026-08-04 | 2026-08-04 | FIN-TEST-03 | FIN-UAT-01 | Planning | ⚠️ CONFLICT | Resource conflict with REL-0014 - Same Test/UAT env required | 55% | UAT defects being triaged; 2 P2 bugs outstanding |  |  |  | USR-001 | Planning | REL-0007 | Not Started | 27% | USR-073,USR-085,USR-097 | Business Hours | TRUE
REL-0010 | Manhattan Major Enhancement v5.2 | Logistics | Manhattan Associates WMS | NA | Large | Medium | P2 - High | 2026-07-15 | 2026-07-18 | 2026-07-20 | IT-TEST-01 | IT-UAT-01 | Testing | ⚠️ CONFLICT | Resource conflict with REL-0005 - Same Test/UAT env required | 60% | Performance testing incomplete; DB migration script needs optimization |  |  |  | USR-002 | Testing |  | In Progress | 64% | USR-074,USR-086,USR-098 | Weekend | TRUE
REL-0011 | HubSpot Minor Update v3.7 | CRM | HubSpot CRM | NA | Small | Low | P3 - Medium | 2026-08-10 | 2026-08-12 | 2026-08-12 | CRM-TEST-02 | CRM-UAT-01 | Planning | ⚠️ CONFLICT | Resource conflict with REL-0014 - Same Test/UAT env required | 40% |  |  |  |  | USR-003 | Planning |  | Not Started | 29% | USR-075,USR-087,USR-097 | Business Hours | TRUE
REL-0012 | Plex Report Fix v2.5 | Manufacturing | Plex Smart Manufacturing | NA | Small | Medium | P3 - Medium | 2026-07-04 | 2026-07-06 | 2026-07-06 | FIN-TEST-01 | FIN-UAT-01 | Approved | ⚠️ CONFLICT | Resource conflict with REL-0007 - Same Test/UAT env required | 72% | Test data refresh pending; blocked on DBA availability |  |  |  | USR-004 | CAB Approved |  | Ready | 89% | USR-076,USR-088,USR-098 | Off-Peak | TRUE
REL-0013 | Dynatrace UI Tweak v3.1 | IT | Dynatrace |  | Small | Low | P3 - Medium | 2026-08-18 | 2026-08-20 | 2026-08-20 | IT-TEST-03 | IT-UAT-01 | Planning | ⚠️ CONFLICT | Resource conflict with REL-0015 - Same Test/UAT env required | 35% |  |  |  |  | USR-005 | Planning | REL-0012 | Not Started | 49% | USR-077,USR-089,USR-097 | Business Hours | TRUE
REL-0014 | Oracle Global Rollout v2.2 | HR | Oracle HCM Cloud | NA | Large | High | P2 - High | 2026-08-11 | 2026-08-14 | 2026-08-16 | CRM-TEST-02 | CRM-UAT-01 | Planning | ⚠️ CONFLICT | Resource conflict with REL-0011 - Same Test/UAT env required | 45% | Global rollout coordination pending; APAC team capacity constrained |  |  |  | USR-006 | Planning |  | Not Started | 21% | USR-078,USR-090,USR-098 | Weekend | TRUE
REL-0015 | DocuSign Core Transformation v1.0 | Legal | DocuSign CLM | NA | Large | High | P2 - High | 2026-08-19 | 2026-08-22 | 2026-08-24 | IT-TEST-03 | IT-UAT-01 | Planning | ⚠️ CONFLICT | Resource conflict with REL-0017 - Same Test/UAT env required | 38% | Architecture review required; security scan findings need remediation |  |  |  | USR-061 | Planning |  | Not Started | 24% | USR-079,USR-091,USR-097 | Weekend | TRUE
REL-0016 | CyberArk Enterprise Integration v2.0 | Security | CyberArk PAM | NA | Large | High | P2 - High | 2026-09-01 | 2026-09-04 | 2026-09-06 | SEC-TEST-01 | SEC-UAT-02 | Draft |  | Change Advisory Board approval needed |  |  |  |  | SOC2 Requirement | USR-062 | Draft |  | Not Started | 7% | USR-080,USR-092,USR-098 | Weekend | TRUE
REL-0017 | HighRadius Report Fix v2.4 | Finance | HighRadius |  | Small | Low | P3 - Medium | 2026-08-22 | 2026-08-24 | 2026-08-24 | IT-TEST-03 | IT-UAT-01 | Planning | ⚠️ CONFLICT | Resource conflict with REL-0022 - Same Test/UAT env required | 30% |  |  |  |  | USR-063 | Planning | REL-0014,REL-0012 | Not Started | 35% | USR-073,USR-085,USR-097 | Off-Peak | TRUE
REL-0018 | Oracle UI Tweak v2.0 | Logistics | Oracle Transportation Management | NA | Small | Low | P3 - Medium | 2026-09-10 | 2026-09-12 | 2026-09-12 | LOG-TEST-03 | LOG-UAT-02 | Draft |  | Audit finding remediation | [5 empty] | USR-064 | Draft |  | Not Started | 2% | USR-074,USR-086,USR-098 | Off-Peak | TRUE
REL-0019 | Salesforce Minor Update v2.5 | CRM | Salesforce Service Cloud | NA | Small | Low | P3 - Medium | 2026-09-14 | 2026-09-16 | 2026-09-16 | CRM-TEST-01 | CRM-UAT-02 | Draft | ⚠️ CONFLICT | Resource conflict with REL-0021 - Same Test/UAT env required | [5 empty] | USR-065 | Draft |  | Not Started | 5% | USR-075,USR-087,USR-097 | Business Hours | TRUE
REL-0020 | Rockwell Quick Enhancement v1.5 | Manufacturing | Rockwell FactoryTalk | NA | Small | Low | P3 - Medium | 2026-09-18 | 2026-09-20 | 2026-09-20 | MAN-TEST-03 | MAN-UAT-01 | Draft |  | Holiday freeze exception requested | [5 empty] | USR-066 | Draft |  | Not Started | 16% | USR-076,USR-088,USR-098 | Business Hours | TRUE
REL-0021 | Splunk Bug Fix Release v3.7 | IT | Splunk Enterprise |  | Small | Low | P3 - Medium | 2026-09-16 | 2026-09-18 | 2026-09-18 | CRM-TEST-01 | CRM-UAT-02 | Draft | ⚠️ CONFLICT | Resource conflict with REL-0026 - Same Test/UAT env required | [5 empty] | USR-067 | Draft | REL-0019 | Not Started | 4% | USR-077,USR-089,USR-097 | Business Hours | TRUE
REL-0022 | Oracle Dashboard Upgrade v2.5 | HR | Oracle HCM Cloud | NA | Medium | Low | P3 - Medium | 2026-08-24 | 2026-08-26 | 2026-08-27 | IT-TEST-03 | IT-UAT-01 | Planning | ⚠️ CONFLICT | Resource conflict with REL-0017 - Same Test/UAT env required | 28% | Requirements still being finalized with business stakeholders |  |  |  | USR-068 | Planning |  | Not Started | 32% | USR-078,USR-090,USR-098 | Weekend | TRUE
REL-0023 | DocuSign Feature Release v3.0 | Legal | DocuSign CLM | NA | Medium | High | P1 - Critical | 2026-10-02 | 2026-10-04 | 2026-10-05 | LEG-TEST-02 | LEG-UAT-02 | Draft | ⚠️ CONFLICT | Resource conflict with REL-0027 - Same Test/UAT env required | [5 empty] | USR-001 | Draft |  | Not Started | 5% | USR-079,USR-091,USR-097 | Weekend | TRUE
REL-0024 | Okta Minor Update v4.1 | Security | Okta Identity Cloud | NA | Small | Low | P3 - Medium | 2026-10-06 | 2026-10-08 | 2026-10-08 | SEC-TEST-01 | SEC-UAT-02 | Draft |  | Security review pending | [5 empty] | USR-002 | Draft |  | Not Started | 4% | USR-080,USR-092,USR-098 | Business Hours | TRUE
REL-0025 | Coupa Dashboard Upgrade v5.8 | Finance | Coupa |  | Medium | Medium | P3 - Medium | 2026-10-10 | 2026-10-12 | 2026-10-13 | FIN-TEST-03 | FIN-UAT-02 | Draft |  | DR sync required post-deployment |  |  |  |  | SOX Compliance | USR-003 | Draft | REL-0022,REL-0020 | Not Started | 9% | USR-073,USR-085,USR-097 | Weekend | TRUE
REL-0026 | Kinaxis Dashboard Upgrade v3.2 | Logistics | Kinaxis RapidResponse | NA | Medium | Low | P3 - Medium | 2026-09-18 | 2026-09-20 | 2026-09-21 | CRM-TEST-01 | CRM-UAT-02 | Draft | ⚠️ CONFLICT | Resource conflict with REL-0021 - Same Test/UAT env required | [5 empty] | USR-004 | Draft |  | Not Started | 5% | USR-074,USR-086,USR-098 | Off-Peak | TRUE
REL-0027 | Salesforce Hotfix v4.3 | CRM | Salesforce Sales Cloud | NA | Small | Low | P4 - Low | 2026-10-04 | 2026-10-06 | 2026-10-06 | LEG-TEST-02 | LEG-UAT-02 | Draft | ⚠️ CONFLICT | Resource conflict with REL-0023 - Same Test/UAT env required | [5 empty] | USR-005 | Draft |  | Not Started | 19% | USR-075,USR-087,USR-097 | Business Hours | TRUE
REL-0028 | SAP Architecture Overhaul v5.5 | Manufacturing | SAP S/4HANA Manufacturing | NA | Large | High | P2 - High | 2026-10-21 | 2026-10-24 | 2026-10-26 | MAN-TEST-03 | MAN-UAT-01 | Draft |  | Critical for Q3 financial close | [5 empty] | USR-006 | Draft |  | Not Started | 2% | USR-076,USR-088,USR-098 | Weekend | TRUE
REL-0029 | Datadog Feature Release v2.2 | IT | Datadog |  | Medium | Medium | P2 - High | 2026-10-29 | 2026-10-31 | 2026-11-01 | IT-TEST-03 | IT-UAT-01 | Draft |  | Dependencies on infrastructure team | [5 empty] | USR-061 | Draft | REL-0027 | Not Started | 1% | USR-077,USR-089,USR-097 | Weekend | TRUE
REL-0030 | Cornerstone Feature Release v1.7 | HR | Cornerstone OnDemand | NA | Medium | High | P2 - High | 2026-11-02 | 2026-11-04 | 2026-11-05 | HR-TEST-02 | HR-UAT-01 | Draft |  | Dependent on vendor patch delivery | [5 empty] | USR-062 | Draft |  | Not Started | 11% | USR-078,USR-090,USR-098 | Weekend | TRUE
REL-0031 | Mitratech Data Patch v2.9 | Legal | Mitratech TeamConnect | NA | Small | Low | P3 - Medium | 2026-11-06 | 2026-11-08 | 2026-11-08 | LEG-TEST-02 | LEG-UAT-02 | Draft |  | Executive sponsor: CIO |  |  |  |  | GDPR Compliance | USR-063 | Draft |  | Not Started | 5% | USR-079,USR-091,USR-097 | Off-Peak | TRUE
REL-0032 | CrowdStrike UI Tweak v1.5 | Security | CrowdStrike Falcon | NA | Small | Low | P4 - Low | 2026-11-10 | 2026-11-12 | 2026-11-12 | SEC-TEST-01 | SEC-UAT-02 | Draft |  | Integration testing with downstream systems | [5 empty] | USR-064 | Draft |  | Not Started | 4% | USR-080,USR-092,USR-098 | Business Hours | TRUE
REL-0033 | Oracle Major Enhancement v5.3 | Finance | Oracle Hyperion HFM |  | Large | Medium | P2 - High | 2026-11-13 | 2026-11-16 | 2026-11-18 | FIN-TEST-01 | FIN-UAT-01 | Draft |  | Dependencies on infrastructure team | [5 empty] | USR-065 | Draft | REL-0030,REL-0028 | Not Started | 6% | USR-073,USR-085,USR-097 | Weekend | TRUE
REL-0034 | Manhattan Module Update v2.8 | Logistics | Manhattan Associates WMS | NA | Medium | Low | P3 - Medium | 2026-11-18 | 2026-11-20 | 2026-11-21 | LOG-TEST-01 | LOG-UAT-01 | Draft |  | Executive sponsor: CFO | [5 empty] | USR-066 | Draft |  | Not Started | 11% | USR-074,USR-086,USR-098 | Off-Peak | TRUE
REL-0035 | Salesforce Report Fix v5.8 | CRM | Salesforce Service Cloud | NA | Small | Medium | P2 - High | 2026-11-22 | 2026-11-24 | 2026-11-24 | CRM-TEST-01 | CRM-UAT-02 | Draft |  | Change Advisory Board approval needed | [5 empty] | USR-067 | Draft |  | Not Started | 4% | USR-075,USR-087,USR-097 | Business Hours | TRUE
REL-0036 | Plex UI Tweak v3.6 | Manufacturing | Plex Smart Manufacturing | NA | Small | Low | P3 - Medium | 2026-11-28 | 2026-11-30 | 2026-11-30 | MAN-TEST-03 | MAN-UAT-01 | Draft |  | Data migration included | [5 empty] | USR-068 | Draft |  | Not Started | 2% | USR-076,USR-088,USR-098 | Off-Peak | TRUE
REL-0037 | Dynatrace Platform Upgrade v4.0 | IT | Dynatrace |  | Large | High | P1 - Critical | 2026-12-01 | 2026-12-04 | 2026-12-06 | IT-TEST-03 | IT-UAT-02 | Draft |  | Customer-facing impact - coordinate with support | [5 empty] | USR-001 | Draft | REL-0035 | Not Started | 10% | USR-077,USR-089,USR-097 | Weekend | TRUE
REL-0038 | SAP Bug Fix Release v5.5 | HR | SAP SuccessFactors | NA | Small | Low | P3 - Medium | 2026-12-06 | 2026-12-08 | 2026-12-08 | HR-TEST-02 | HR-UAT-02 | Draft |  | Dependent on vendor patch delivery | [5 empty] | USR-002 | Draft |  | Not Started | 3% | USR-078,USR-090,USR-098 | Off-Peak | TRUE
REL-0039 | Agiloft Core Transformation v4.6 | Legal | Agiloft CLM | NA | Large | High | P1 - Critical | 2026-12-09 | 2026-12-12 | 2026-12-14 | LEG-TEST-03 | LEG-UAT-01 | Draft |  | Holiday freeze exception requested | [5 empty] | USR-003 | Draft |  | Not Started | 3% | USR-079,USR-091,USR-097 | Weekend | TRUE
REL-0040 | Palo Quick Enhancement v3.7 | Security | Palo Alto Cortex XDR | NA | Small | Low | P4 - Low | 2026-12-14 | 2026-12-16 | 2026-12-16 | SEC-TEST-03 | SEC-UAT-02 | Draft |  | Critical for Q3 financial close |  |  |  | Year-End Freeze | SOC2 Requirement | USR-004 | Draft |  | Not Started | 17% | USR-080,USR-092,USR-098 | Off-Peak | TRUE
REL-0041 | Anaplan Bug Fix Release v3.3 | Finance | Anaplan |  | Small | Low | P4 - Low | 2026-12-18 | 2026-12-20 | 2026-12-20 | FIN-TEST-01 | FIN-UAT-01 | Draft | ⚠️ CONFLICT | Resource conflict with REL-0043 - Overlapping Test/UAT window |  |  |  | Year-End Freeze |  | USR-005 | Draft | REL-0038,REL-0036 | Not Started | 9% | USR-073,USR-085,USR-097 | Business Hours | TRUE
REL-0042 | Oracle Security Patch Bundle v5.6 | Logistics | Oracle Transportation Management | NA | Medium | Medium | P2 - High | 2026-12-22 | 2026-12-24 | 2026-12-25 | LOG-TEST-01 | LOG-UAT-01 | Draft |  | Executive sponsor: CFO |  |  | Oracle Patch Window | Year-End Freeze |  | USR-006 | Draft |  | Not Started | 6% | USR-074,USR-086,USR-098 | Off-Peak | TRUE
REL-0043 | Microsoft Integration Enhancement v1.9 | CRM | Microsoft Dynamics 365 CRM | NA | Medium | Medium | P2 - High | 2026-12-21 | 2026-12-23 | 2026-12-24 | FIN-TEST-01 | FIN-UAT-01 | Draft | ⚠️ CONFLICT | Resource conflict with REL-0041 - Overlapping Test/UAT window |  |  |  | Year-End Freeze |  | USR-061 | Draft |  | Not Started | 16% | USR-075,USR-087,USR-097 | Off-Peak | TRUE
REL-0044 | Siemens Integration Enhancement v2.2 | Manufacturing | Siemens Opcenter | NA | Medium | High | P2 - High | 2027-01-02 | 2027-01-04 | 2027-01-05 | MAN-TEST-01 | MAN-UAT-01 | Draft |  | License renewal dependency |  |  |  | Year-End Freeze |  | USR-062 | Draft |  | Not Started | 16% | USR-076,USR-088,USR-098 | Weekend | TRUE
REL-0045 | Splunk Global Rollout v3.0 | IT | Splunk Enterprise |  | Large | High | P1 - Critical | 2027-01-05 | 2027-01-08 | 2027-01-10 | IT-TEST-01 | IT-UAT-01 | Draft |  | Critical for Q3 financial close | [5 empty] | USR-063 | Draft | REL-0042 | Not Started | 17% | USR-077,USR-089,USR-097 | Weekend | TRUE
REL-0046 | SAP UI Tweak v5.2 | HR | SAP SuccessFactors | NA | Small | Low | P4 - Low | 2027-01-10 | 2027-01-12 | 2027-01-12 | HR-TEST-03 | HR-UAT-02 | Draft |  | Executive sponsor: CFO | [5 empty] | USR-064 | Draft |  | Not Started | 14% | USR-078,USR-090,USR-098 | Off-Peak | TRUE
REL-0047 | DocuSign Integration Enhancement v1.4 | Legal | DocuSign CLM | NA | Medium | Medium | P3 - Medium | 2027-01-14 | 2027-01-16 | 2027-01-17 | LEG-TEST-02 | LEG-UAT-02 | Draft |  | Customer-facing impact - coordinate with support | [5 empty] | USR-065 | Draft |  | Not Started | 10% | USR-079,USR-091,USR-097 | Weekend | TRUE
REL-0048 | Okta Report Fix v4.1 | Security | Okta Identity Cloud | NA | Small | Low | P4 - Low | 2027-01-18 | 2027-01-20 | 2027-01-20 | SEC-TEST-03 | SEC-UAT-01 | Draft |  | External vendor coordination needed | [5 empty] | USR-066 | Draft |  | Not Started | 17% | USR-080,USR-092,USR-098 | Business Hours | TRUE
REL-0049 | Anaplan Minor Update v3.3 | Finance | Anaplan |  | Small | Low | P4 - Low | 2027-01-22 | 2027-01-24 | 2027-01-24 | FIN-TEST-02 | FIN-UAT-02 | Draft |  | DR sync required post-deployment |  |  |  |  | SOX Compliance | USR-067 | Draft | REL-0046,REL-0044 | Not Started | 18% | USR-073,USR-085,USR-097 | Business Hours | TRUE
REL-0050 | Blue Configuration Change v5.9 | Logistics | Blue Yonder WMS | NA | Small | Low | P4 - Low | 2027-01-29 | 2027-01-31 | 2027-01-31 | LOG-TEST-01 | LOG-UAT-02 | Draft |  | Executive sponsor: CIO | [5 empty] | USR-068 | Draft |  | Not Started | 0% | USR-074,USR-086,USR-098 | Off-Peak | TRUE
REL-0051 | HubSpot Module Update v4.7 | CRM | HubSpot CRM | NA | Medium | Medium | P2 - High | 2027-02-02 | 2027-02-04 | 2027-02-05 | CRM-TEST-03 | CRM-UAT-02 | Draft |  | Requires weekend deployment window | [5 empty] | USR-001 | Draft |  | Not Started | 3% | USR-075,USR-087,USR-097 | Off-Peak | TRUE
REL-0052 | SAP Configuration Change v1.3 | Manufacturing | SAP S/4HANA Manufacturing | NA | Small | Low | P4 - Low | 2027-02-06 | 2027-02-08 | 2027-02-08 | MAN-TEST-01 | MAN-UAT-01 | Draft |  | DR sync required post-deployment | [5 empty] | USR-002 | Draft |  | Not Started | 12% | USR-076,USR-088,USR-098 | Business Hours | TRUE
REL-0053 | Splunk Global Rollout v5.8 | IT | Splunk Enterprise |  | Large | High | P1 - Critical | 2027-02-09 | 2027-02-12 | 2027-02-14 | IT-TEST-03 | IT-UAT-02 | Draft |  | Dependent on vendor patch delivery | [5 empty] | USR-003 | Draft | REL-0051 | Not Started | 6% | USR-077,USR-089,USR-097 | Weekend | TRUE
REL-0054 | Workday Core Transformation v2.7 | HR | Workday HCM | NA | Large | High | P2 - High | 2027-02-13 | 2027-02-16 | 2027-02-18 | HR-TEST-01 | HR-UAT-01 | Draft |  | Training materials to be updated | [5 empty] | USR-004 | Draft |  | Not Started | 2% | USR-078,USR-090,USR-098 | Weekend | TRUE
REL-0055 | DocuSign Major Enhancement v5.2 | Legal | DocuSign CLM | NA | Large | High | P1 - Critical | 2027-02-17 | 2027-02-20 | 2027-02-22 | LEG-TEST-03 | LEG-UAT-01 | Draft |  | Rollback plan required |  |  |  |  | GDPR Compliance | USR-005 | Draft |  | Not Started | 0% | USR-079,USR-091,USR-097 | Weekend | TRUE
REL-0056 | Okta Performance Optimization v5.0 | Security | Okta Identity Cloud | NA | Medium | Medium | P2 - High | 2027-02-22 | 2027-02-24 | 2027-02-25 | SEC-TEST-01 | SEC-UAT-02 | Draft | ⚠️ CONFLICT | Resource conflict with REL-0058 - Overlapping Test/UAT window | [5 empty] | USR-006 | Draft |  | Not Started | 17% | USR-080,USR-092,USR-098 | Weekend | TRUE
REL-0057 | Coupa Security Patch Bundle v3.3 | Finance | Coupa |  | Medium | Medium | P3 - Medium | 2027-02-26 | 2027-02-28 | 2027-03-01 | FIN-TEST-02 | FIN-UAT-01 | Draft |  | External vendor coordination needed | [5 empty] | USR-061 | Draft | REL-0054,REL-0052 | Not Started | 5% | USR-073,USR-085,USR-097 | Off-Peak | TRUE
REL-0058 | Manhattan API Enhancement v2.0 | Logistics | Manhattan Associates WMS | NA | Medium | Low | P4 - Low | 2027-02-25 | 2027-02-27 | 2027-02-28 | SEC-TEST-01 | SEC-UAT-02 | Draft | ⚠️ CONFLICT | Resource conflict with REL-0056 - Overlapping Test/UAT window | [5 empty] | USR-062 | Draft |  | Not Started | 7% | USR-074,USR-086,USR-098 | Weekend | TRUE
REL-0059 | Salesforce Workflow Automation v5.8 | CRM | Salesforce Service Cloud | NA | Medium | Medium | P3 - Medium | 2027-03-06 | 2027-03-08 | 2027-03-09 | CRM-TEST-03 | CRM-UAT-02 | Draft |  | Holiday freeze exception requested | [5 empty] | USR-063 | Draft |  | Not Started | 0% | USR-075,USR-087,USR-097 | Weekend | TRUE
REL-0060 | Plex UI Tweak v4.0 | Manufacturing | Plex Smart Manufacturing | NA | Small | Low | P4 - Low | 2027-03-10 | 2027-03-12 | 2027-03-12 | MAN-TEST-02 | MAN-UAT-02 | Draft |  | Performance testing mandatory | [5 empty] | USR-064 | Draft |  | Not Started | 18% | USR-076,USR-088,USR-098 | Business Hours | TRUE
REL-0061 | Datadog API Enhancement v5.6 | IT | Datadog |  | Medium | Low | P4 - Low | 2027-03-14 | 2027-03-16 | 2027-03-17 | IT-TEST-02 | IT-UAT-01 | Draft |  | Holiday freeze exception requested | [5 empty] | USR-065 | Draft | REL-0059 | Not Started | 12% | USR-077,USR-089,USR-097 | Off-Peak | TRUE
REL-0062 | SAP Report Fix v2.8 | HR | SAP SuccessFactors | NA | Small | Medium | P3 - Medium | 2027-03-18 | 2027-03-20 | 2027-03-20 | HR-TEST-03 | HR-UAT-02 | Draft |  | Dependent on vendor patch delivery | [5 empty] | USR-066 | Draft |  | Not Started | 11% | USR-078,USR-090,USR-098 | Off-Peak | TRUE
REL-0063 | Mitratech Workflow Automation v2.3 | Legal | Mitratech TeamConnect | NA | Medium | Low | P4 - Low | 2027-03-22 | 2027-03-24 | 2027-03-25 | LEG-TEST-01 | LEG-UAT-02 | Draft |  | Business continuity testing required | [5 empty] | USR-067 | Draft |  | Not Started | 15% | USR-079,USR-091,USR-097 | Off-Peak | TRUE
REL-0064 | Microsoft Integration Enhancement v4.1 | Security | Microsoft Sentinel | NA | Medium | Low | P4 - Low | 2027-03-29 | 2027-03-31 | 2027-04-01 | SEC-TEST-03 | SEC-UAT-02 | Draft |  | Customer-facing impact - coordinate with support |  |  |  | Quarter-End Freeze | SOC2 Requirement | USR-068 | Draft |  | Not Started | 5% | USR-080,USR-092,USR-098 | Off-Peak | TRUE
REL-0065 | Oracle System Migration v1.9 | Finance | Oracle Hyperion HFM |  | Large | High | P2 - High | 2027-04-01 | 2027-04-04 | 2027-04-06 | FIN-TEST-03 | FIN-UAT-02 | Draft |  | Dependencies on infrastructure team | [5 empty] | USR-001 | Draft | REL-0062,REL-0060 | Not Started | 9% | USR-073,USR-085,USR-097 | Weekend | TRUE
REL-0066 | Oracle Module Update v5.6 | Logistics | Oracle Transportation Management | NA | Medium | Medium | P3 - Medium | 2027-04-06 | 2027-04-08 | 2027-04-09 | LOG-TEST-02 | LOG-UAT-01 | Draft | ⚠️ CONFLICT | Resource conflict with REL-0068 - Overlapping Test/UAT window | [5 empty] | USR-002 | Draft |  | Not Started | 10% | USR-074,USR-086,USR-098 | Off-Peak | TRUE
REL-0067 | Salesforce Complete Redesign v1.9 | CRM | Salesforce Sales Cloud | NA | Large | High | P1 - Critical | 2027-04-09 | 2027-04-12 | 2027-04-14 | CRM-TEST-03 | CRM-UAT-02 | Draft |  | Blackout period consideration | [5 empty] | USR-003 | Draft |  | Not Started | 19% | USR-075,USR-087,USR-097 | Weekend | TRUE
REL-0068 | Rockwell Minor Update v1.1 | Manufacturing | Rockwell FactoryTalk | NA | Small | Low | P4 - Low | 2027-04-09 | 2027-04-11 | 2027-04-11 | LOG-TEST-02 | LOG-UAT-01 | Draft | ⚠️ CONFLICT | Resource conflict with REL-0066 - Overlapping Test/UAT window | [5 empty] | USR-004 | Draft |  | Not Started | 18% | USR-076,USR-088,USR-098 | Business Hours | TRUE
REL-0069 | BMC UI Tweak v5.1 | IT | BMC Remedy |  | Small | Medium | P3 - Medium | 2027-04-18 | 2027-04-20 | 2027-04-20 | IT-TEST-01 | IT-UAT-01 | Draft |  | Rollback plan required | [5 empty] | USR-005 | Draft | REL-0067 | Not Started | 2% | USR-077,USR-089,USR-097 | Off-Peak | TRUE
REL-0070 | Oracle Workflow Automation v3.6 | HR | Oracle HCM Cloud | NA | Medium | Medium | P3 - Medium | 2027-04-22 | 2027-04-24 | 2027-04-25 | HR-TEST-02 | HR-UAT-02 | Draft |  | Requires weekend deployment window |  |  | Oracle Patch Window |  |  | USR-006 | Draft |  | Not Started | 0% | USR-078,USR-090,USR-098 | Weekend | TRUE
REL-0071 | Agiloft Minor Update v4.1 | Legal | Agiloft CLM | NA | Small | Low | P3 - Medium | 2027-04-28 | 2027-04-30 | 2027-04-30 | LEG-TEST-03 | LEG-UAT-01 | Draft | ⚠️ CONFLICT | Resource conflict with REL-0073 - Overlapping Test/UAT window | [5 empty] | USR-061 | Draft |  | Not Started | 11% | USR-079,USR-091,USR-097 | Business Hours | TRUE
REL-0072 | Palo Hotfix v5.8 | Security | Palo Alto Cortex XDR | NA | Small | Low | P3 - Medium | 2027-05-02 | 2027-05-04 | 2027-05-04 | SEC-TEST-01 | SEC-UAT-01 | Draft |  | Dependent on vendor patch delivery | [5 empty] | USR-062 | Draft |  | Not Started | 18% | USR-080,USR-092,USR-098 | Business Hours | TRUE
REL-0073 | Kyriba Security Patch Bundle v3.6 | Finance | Kyriba |  | Medium | Medium | P2 - High | 2027-05-01 | 2027-05-03 | 2027-05-04 | LEG-TEST-03 | LEG-UAT-01 | Draft | ⚠️ CONFLICT | Resource conflict with REL-0071 - Overlapping Test/UAT window | [5 empty] | USR-063 | Draft | REL-0070,REL-0068 | Not Started | 14% | USR-073,USR-085,USR-097 | Off-Peak | TRUE
REL-0074 | Oracle Hotfix v4.3 | Logistics | Oracle Transportation Management | NA | Small | Low | P3 - Medium | 2027-05-10 | 2027-05-12 | 2027-05-12 | LOG-TEST-03 | LOG-UAT-02 | Draft |  | Dependent on vendor patch delivery | [5 empty] | USR-064 | Draft |  | Not Started | 16% | USR-074,USR-086,USR-098 | Business Hours | TRUE
REL-0075 | HubSpot Performance Optimization v3.0 | CRM | HubSpot CRM | NA | Medium | Medium | P3 - Medium | 2027-05-14 | 2027-05-16 | 2027-05-17 | CRM-TEST-02 | CRM-UAT-02 | Draft |  | Dependencies on infrastructure team | [5 empty] | USR-065 | Draft |  | Not Started | 4% | USR-075,USR-087,USR-097 | Weekend | TRUE
REL-0076 | SAP Hotfix v4.1 | Manufacturing | SAP S/4HANA Manufacturing | NA | Small | Low | P4 - Low | 2027-05-18 | 2027-05-20 | 2027-05-20 | MAN-TEST-01 | MAN-UAT-01 | Draft |  | Security review pending | [5 empty] | USR-066 | Draft |  | Not Started | 2% | USR-076,USR-088,USR-098 | Business Hours | TRUE
REL-0077 | Jira Core Transformation v1.8 | IT | Jira Service Management |  | Large | High | P2 - High | 2027-05-21 | 2027-05-24 | 2027-05-26 | IT-TEST-02 | IT-UAT-01 | Draft |  | Rollback plan required | [5 empty] | USR-067 | Draft | REL-0076 | Not Started | 2% | USR-077,USR-089,USR-097 | Weekend | TRUE
REL-0078 | ADP Workflow Automation v2.7 | HR | ADP Workforce Now | NA | Medium | High | P1 - Critical | 2027-05-29 | 2027-05-31 | 2027-06-01 | HR-TEST-03 | HR-UAT-02 | Draft |  | Regulatory deadline driven | [5 empty] | USR-068 | Draft |  | Not Started | 6% | USR-078,USR-090,USR-098 | Weekend | TRUE
REL-0079 | Ironclad Module Update v4.7 | Legal | Ironclad | NA | Medium | High | P2 - High | 2027-06-02 | 2027-06-04 | 2027-06-05 | LEG-TEST-01 | LEG-UAT-01 | Draft |  | Dependencies on infrastructure team |  |  |  |  | GDPR Compliance | USR-001 | Draft |  | Not Started | 8% | USR-079,USR-091,USR-097 | Off-Peak | TRUE
REL-0080 | CrowdStrike Performance Optimization v5.9 | Security | CrowdStrike Falcon | NA | Medium | High | P1 - Critical | 2027-06-06 | 2027-06-08 | 2027-06-09 | SEC-TEST-03 | SEC-UAT-01 | Draft |  | Audit finding remediation | [5 empty] | USR-002 | Draft |  | Not Started | 8% | USR-080,USR-092,USR-098 | Weekend | TRUE

## Calendar
🔍 FILTERS |  | Time Period: | All Time | Department: | All | Event Type: | All
Showing: | 166 of 166 events
RELEASE CALENDAR - FY2026-2027
Legend:
■ Change Freeze | Deployment restrictions in effect
■ Large Release | High impact, extended testing
■ Medium Release | Standard release cycle
■ Small Release | Quick deployment
■ Regulatory | Compliance-driven release
■ Vendor Maint. | Vendor maintenance window
Month | Week | Date | Day | Event Type | Release ID | Release Name | Department | Size/Impact | Notes
Jun 2026 | 4 | 2026-06-28 | Sun | CAB MEETING | REL-0001 | CAB: Kyriba UI Tweak v4.5... | Finance | Small | Approval meeting for REL-0001
Jun 2026 | 5 | 2026-06-30 | Tue | RELEASE | REL-0001 | Kyriba UI Tweak v4.5 | Finance | Small / Low | Impact: Low - Quarter-End Freeze AFFECTED
Jun 2026 | 5 | 2026-06-30 | Tue | CAB MEETING | REL-0003 | CAB: Zendesk Minor Update v4.3... | CRM | Small | Approval meeting for REL-0003
Jul 2026 | 1 | 2026-07-02 | Thu | CAB MEETING | REL-0002 | CAB: Blue Workflow Automation v2.1... | Logistics | Medium | Approval meeting for REL-0002
Jul 2026 | 1 | 2026-07-02 | Thu | RELEASE | REL-0003 | Zendesk Minor Update v4.3 | CRM | Small / Low | Impact: Low
Jul 2026 | 1 | 2026-07-02 | Thu | CAB MEETING | REL-0007 | CAB: Mitratech Integration Enhancem... | Legal | Medium | Approval meeting for REL-0007
Jul 2026 | 1 | 2026-07-04 | Sat | RELEASE | REL-0002 | Blue Workflow Automation v2.1 | Logistics | Medium / High | Impact: High
Jul 2026 | 1 | 2026-07-04 | Sat | RELEASE | REL-0007 | Mitratech Integration Enhancement v5.2 | Legal | Medium / High | Impact: High
Jul 2026 | 1 | 2026-07-04 | Sat | CAB MEETING | REL-0012 | CAB: Plex Report Fix v2.5... | Manufacturing | Small | Approval meeting for REL-0012
Jul 2026 | 1 | 2026-07-06 | Mon | RELEASE | REL-0012 | Plex Report Fix v2.5 | Manufacturing | Small / Medium | Impact: Medium
Jul 2026 | 2 | 2026-07-10 | Fri | CAB MEETING | REL-0004 | CAB: AVEVA Dashboard Upgrade v5.5... | Manufacturing | Medium | Approval meeting for REL-0004
Jul 2026 | 2 | 2026-07-12 | Sun | RELEASE | REL-0004 | AVEVA Dashboard Upgrade v5.5 | Manufacturing | Medium / High | Impact: High
Jul 2026 | 2 | 2026-07-14 | Tue | CAB MEETING | REL-0005 | CAB: Datadog Security Patch Bundle ... | IT | Medium | Approval meeting for REL-0005
Jul 2026 | 3 | 2026-07-15 | Wed | CAB MEETING | REL-0010 | CAB: Manhattan Major Enhancement v5... | Logistics | Large | Approval meeting for REL-0010
Jul 2026 | 3 | 2026-07-16 | Thu | RELEASE | REL-0005 | Datadog Security Patch Bundle v3.5 | IT | Medium / High | Impact: High
Jul 2026 | 3 | 2026-07-18 | Sat | CAB MEETING | REL-0006 | CAB: SAP Configuration Change v5.2... | HR | Small | Approval meeting for REL-0006
Jul 2026 | 3 | 2026-07-18 | Sat | RELEASE | REL-0010 | Manhattan Major Enhancement v5.2 | Logistics | Large / Medium | Impact: Medium
Jul 2026 | 3 | 2026-07-20 | Mon | RELEASE | REL-0006 | SAP Configuration Change v5.2 | HR | Small / Medium | Impact: Medium
Jul 2026 | 5 | 2026-07-29 | Wed | CAB MEETING | REL-0008 | CAB: CrowdStrike Minor Update v3.6... | Security | Small | Approval meeting for REL-0008
Jul 2026 | 5 | 2026-07-31 | Fri | RELEASE | REL-0008 | CrowdStrike Minor Update v3.6 | Security | Small / Low | Impact: Low
Aug 2026 | 1 | 2026-08-02 | Sun | CAB MEETING | REL-0009 | CAB: Oracle Report Fix v3.4... | Finance | Small | Approval meeting for REL-0009
Aug 2026 | 1 | 2026-08-04 | Tue | RELEASE | REL-0009 | Oracle Report Fix v3.4 | Finance | Small / Medium | Impact: Medium
Aug 2026 | 2 | 2026-08-10 | Mon | CAB MEETING | REL-0011 | CAB: HubSpot Minor Update v3.7... | CRM | Small | Approval meeting for REL-0011
Aug 2026 | 2 | 2026-08-11 | Tue | CAB MEETING | REL-0014 | CAB: Oracle Global Rollout v2.2... | HR | Large | Approval meeting for REL-0014
Aug 2026 | 2 | 2026-08-12 | Wed | RELEASE | REL-0011 | HubSpot Minor Update v3.7 | CRM | Small / Low | Impact: Low
Aug 2026 | 2 | 2026-08-14 | Fri | RELEASE | REL-0014 | Oracle Global Rollout v2.2 | HR | Large / High | Impact: High
Aug 2026 | 3 | 2026-08-18 | Tue | CAB MEETING | REL-0013 | CAB: Dynatrace UI Tweak v3.1... | IT | Small | Approval meeting for REL-0013
Aug 2026 | 3 | 2026-08-19 | Wed | CAB MEETING | REL-0015 | CAB: DocuSign Core Transformation v... | Legal | Large | Approval meeting for REL-0015
Aug 2026 | 3 | 2026-08-20 | Thu | RELEASE | REL-0013 | Dynatrace UI Tweak v3.1 | IT | Small / Low | Impact: Low
Aug 2026 | 4 | 2026-08-22 | Sat | RELEASE | REL-0015 | DocuSign Core Transformation v1.0 | Legal | Large / High | Impact: High
Aug 2026 | 4 | 2026-08-22 | Sat | CAB MEETING | REL-0017 | CAB: HighRadius Report Fix v2.4... | Finance | Small | Approval meeting for REL-0017
Aug 2026 | 4 | 2026-08-24 | Mon | RELEASE | REL-0017 | HighRadius Report Fix v2.4 | Finance | Small / Low | Impact: Low
Aug 2026 | 4 | 2026-08-24 | Mon | CAB MEETING | REL-0022 | CAB: Oracle Dashboard Upgrade v2.5... | HR | Medium | Approval meeting for REL-0022
Aug 2026 | 4 | 2026-08-26 | Wed | RELEASE | REL-0022 | Oracle Dashboard Upgrade v2.5 | HR | Medium / Low | Impact: Low
Sep 2026 | 1 | 2026-09-01 | Tue | CAB MEETING | REL-0016 | CAB: CyberArk Enterprise Integratio... | Security | Large | Approval meeting for REL-0016
Sep 2026 | 1 | 2026-09-04 | Fri | REGULATORY | REL-0016 | CyberArk Enterprise Integration v2.0 | Security | Large / High | SOC2 Requirement
Sep 2026 | 2 | 2026-09-10 | Thu | CAB MEETING | REL-0018 | CAB: Oracle UI Tweak v2.0... | Logistics | Small | Approval meeting for REL-0018
Sep 2026 | 2 | 2026-09-12 | Sat | RELEASE | REL-0018 | Oracle UI Tweak v2.0 | Logistics | Small / Low | Impact: Low
Sep 2026 | 2 | 2026-09-14 | Mon | CAB MEETING | REL-0019 | CAB: Salesforce Minor Update v2.5... | CRM | Small | Approval meeting for REL-0019
Sep 2026 | 3 | 2026-09-16 | Wed | RELEASE | REL-0019 | Salesforce Minor Update v2.5 | CRM | Small / Low | Impact: Low
Sep 2026 | 3 | 2026-09-16 | Wed | CAB MEETING | REL-0021 | CAB: Splunk Bug Fix Release v3.7... | IT | Small | Approval meeting for REL-0021
Sep 2026 | 3 | 2026-09-18 | Fri | CAB MEETING | REL-0020 | CAB: Rockwell Quick Enhancement v1.... | Manufacturing | Small | Approval meeting for REL-0020
Sep 2026 | 3 | 2026-09-18 | Fri | RELEASE | REL-0021 | Splunk Bug Fix Release v3.7 | IT | Small / Low | Impact: Low
Sep 2026 | 3 | 2026-09-18 | Fri | CAB MEETING | REL-0026 | CAB: Kinaxis Dashboard Upgrade v3.2... | Logistics | Medium | Approval meeting for REL-0026
Sep 2026 | 3 | 2026-09-20 | Sun | RELEASE | REL-0020 | Rockwell Quick Enhancement v1.5 | Manufacturing | Small / Low | Impact: Low
Sep 2026 | 3 | 2026-09-20 | Sun | RELEASE | REL-0026 | Kinaxis Dashboard Upgrade v3.2 | Logistics | Medium / Low | Impact: Low
Oct 2026 | 1 | 2026-10-02 | Fri | CAB MEETING | REL-0023 | CAB: DocuSign Feature Release v3.0... | Legal | Medium | Approval meeting for REL-0023
Oct 2026 | 1 | 2026-10-04 | Sun | RELEASE | REL-0023 | DocuSign Feature Release v3.0 | Legal | Medium / High | Impact: High
Oct 2026 | 1 | 2026-10-04 | Sun | CAB MEETING | REL-0027 | CAB: Salesforce Hotfix v4.3... | CRM | Small | Approval meeting for REL-0027
Oct 2026 | 1 | 2026-10-06 | Tue | CAB MEETING | REL-0024 | CAB: Okta Minor Update v4.1... | Security | Small | Approval meeting for REL-0024
Oct 2026 | 1 | 2026-10-06 | Tue | RELEASE | REL-0027 | Salesforce Hotfix v4.3 | CRM | Small / Low | Impact: Low
Oct 2026 | 2 | 2026-10-08 | Thu | RELEASE | REL-0024 | Okta Minor Update v4.1 | Security | Small / Low | Impact: Low
Oct 2026 | 2 | 2026-10-10 | Sat | CAB MEETING | REL-0025 | CAB: Coupa Dashboard Upgrade v5.8... | Finance | Medium | Approval meeting for REL-0025
Oct 2026 | 2 | 2026-10-12 | Mon | REGULATORY | REL-0025 | Coupa Dashboard Upgrade v5.8 | Finance | Medium / Medium | SOX Compliance
Oct 2026 | 3 | 2026-10-21 | Wed | CAB MEETING | REL-0028 | CAB: SAP Architecture Overhaul v5.5... | Manufacturing | Large | Approval meeting for REL-0028
Oct 2026 | 4 | 2026-10-24 | Sat | RELEASE | REL-0028 | SAP Architecture Overhaul v5.5 | Manufacturing | Large / High | Impact: High
Oct 2026 | 5 | 2026-10-29 | Thu | CAB MEETING | REL-0029 | CAB: Datadog Feature Release v2.2... | IT | Medium | Approval meeting for REL-0029
Oct 2026 | 5 | 2026-10-31 | Sat | RELEASE | REL-0029 | Datadog Feature Release v2.2 | IT | Medium / Medium | Impact: Medium
Nov 2026 | 1 | 2026-11-02 | Mon | CAB MEETING | REL-0030 | CAB: Cornerstone Feature Release v1... | HR | Medium | Approval meeting for REL-0030
Nov 2026 | 1 | 2026-11-04 | Wed | RELEASE | REL-0030 | Cornerstone Feature Release v1.7 | HR | Medium / High | Impact: High
Nov 2026 | 1 | 2026-11-06 | Fri | CAB MEETING | REL-0031 | CAB: Mitratech Data Patch v2.9... | Legal | Small | Approval meeting for REL-0031
Nov 2026 | 2 | 2026-11-08 | Sun | REGULATORY | REL-0031 | Mitratech Data Patch v2.9 | Legal | Small / Low | GDPR Compliance
Nov 2026 | 2 | 2026-11-10 | Tue | CAB MEETING | REL-0032 | CAB: CrowdStrike UI Tweak v1.5... | Security | Small | Approval meeting for REL-0032
Nov 2026 | 2 | 2026-11-12 | Thu | RELEASE | REL-0032 | CrowdStrike UI Tweak v1.5 | Security | Small / Low | Impact: Low
Nov 2026 | 2 | 2026-11-13 | Fri | CAB MEETING | REL-0033 | CAB: Oracle Major Enhancement v5.3... | Finance | Large | Approval meeting for REL-0033
Nov 2026 | 3 | 2026-11-16 | Mon | RELEASE | REL-0033 | Oracle Major Enhancement v5.3 | Finance | Large / Medium | Impact: Medium
Nov 2026 | 3 | 2026-11-18 | Wed | CAB MEETING | REL-0034 | CAB: Manhattan Module Update v2.8... | Logistics | Medium | Approval meeting for REL-0034
Nov 2026 | 3 | 2026-11-20 | Fri | RELEASE | REL-0034 | Manhattan Module Update v2.8 | Logistics | Medium / Low | Impact: Low
Nov 2026 | 4 | 2026-11-22 | Sun | CAB MEETING | REL-0035 | CAB: Salesforce Report Fix v5.8... | CRM | Small | Approval meeting for REL-0035
Nov 2026 | 4 | 2026-11-24 | Tue | RELEASE | REL-0035 | Salesforce Report Fix v5.8 | CRM | Small / Medium | Impact: Medium
Nov 2026 | 4 | 2026-11-28 | Sat | CAB MEETING | REL-0036 | CAB: Plex UI Tweak v3.6... | Manufacturing | Small | Approval meeting for REL-0036
Nov 2026 | 5 | 2026-11-30 | Mon | RELEASE | REL-0036 | Plex UI Tweak v3.6 | Manufacturing | Small / Low | Impact: Low
Dec 2026 | 1 | 2026-12-01 | Tue | CAB MEETING | REL-0037 | CAB: Dynatrace Platform Upgrade v4.... | IT | Large | Approval meeting for REL-0037
Dec 2026 | 1 | 2026-12-04 | Fri | RELEASE | REL-0037 | Dynatrace Platform Upgrade v4.0 | IT | Large / High | Impact: High
Dec 2026 | 1 | 2026-12-06 | Sun | CAB MEETING | REL-0038 | CAB: SAP Bug Fix Release v5.5... | HR | Small | Approval meeting for REL-0038
Dec 2026 | 2 | 2026-12-08 | Tue | RELEASE | REL-0038 | SAP Bug Fix Release v5.5 | HR | Small / Low | Impact: Low
Dec 2026 | 2 | 2026-12-09 | Wed | CAB MEETING | REL-0039 | CAB: Agiloft Core Transformation v4... | Legal | Large | Approval meeting for REL-0039
Dec 2026 | 2 | 2026-12-12 | Sat | RELEASE | REL-0039 | Agiloft Core Transformation v4.6 | Legal | Large / High | Impact: High
Dec 2026 | 2 | 2026-12-13 | Sun | CHANGE FREEZE | - | Year-End Change Freeze START | ALL | Critical | No deployments allowed
Dec 2026 | 2 | 2026-12-14 | Mon | CAB MEETING | REL-0040 | CAB: Palo Quick Enhancement v3.7... | Security | Small | Approval meeting for REL-0040
Dec 2026 | 3 | 2026-12-16 | Wed | REGULATORY | REL-0040 | Palo Quick Enhancement v3.7 | Security | Small / Low | SOC2 Requirement
Dec 2026 | 3 | 2026-12-18 | Fri | CAB MEETING | REL-0041 | CAB: Anaplan Bug Fix Release v3.3... | Finance | Small | Approval meeting for REL-0041
Dec 2026 | 3 | 2026-12-20 | Sun | RELEASE | REL-0041 | Anaplan Bug Fix Release v3.3 | Finance | Small / Low | Impact: Low - Year-End Freeze AFFECTED
Dec 2026 | 3 | 2026-12-21 | Mon | CAB MEETING | REL-0043 | CAB: Microsoft Integration Enhancem... | CRM | Medium | Approval meeting for REL-0043
Dec 2026 | 4 | 2026-12-22 | Tue | CAB MEETING | REL-0042 | CAB: Oracle Security Patch Bundle v... | Logistics | Medium | Approval meeting for REL-0042
Dec 2026 | 4 | 2026-12-23 | Wed | RELEASE | REL-0043 | Microsoft Integration Enhancement v1.9 | CRM | Medium / Medium | Impact: Medium - Year-End Freeze AFFECTED
Dec 2026 | 4 | 2026-12-24 | Thu | VENDOR MAINT | REL-0042 | Oracle Security Patch Bundle v5.6 | Logistics | Medium / Medium | Oracle Patch Window
Dec 2026 | 5 | 2026-12-31 | Thu | CHANGE FREEZE | - | Year-End Change Freeze END | ALL | Critical | No deployments allowed
Jan 2027 | 1 | 2027-01-02 | Sat | CAB MEETING | REL-0044 | CAB: Siemens Integration Enhancemen... | Manufacturing | Medium | Approval meeting for REL-0044
Jan 2027 | 1 | 2027-01-04 | Mon | RELEASE | REL-0044 | Siemens Integration Enhancement v2.2 | Manufacturing | Medium / High | Impact: High - Year-End Freeze AFFECTED
Jan 2027 | 1 | 2027-01-05 | Tue | CAB MEETING | REL-0045 | CAB: Splunk Global Rollout v3.0... | IT | Large | Approval meeting for REL-0045
Jan 2027 | 2 | 2027-01-08 | Fri | RELEASE | REL-0045 | Splunk Global Rollout v3.0 | IT | Large / High | Impact: High
Jan 2027 | 2 | 2027-01-10 | Sun | CAB MEETING | REL-0046 | CAB: SAP UI Tweak v5.2... | HR | Small | Approval meeting for REL-0046
Jan 2027 | 2 | 2027-01-12 | Tue | RELEASE | REL-0046 | SAP UI Tweak v5.2 | HR | Small / Low | Impact: Low
Jan 2027 | 2 | 2027-01-14 | Thu | CAB MEETING | REL-0047 | CAB: DocuSign Integration Enhanceme... | Legal | Medium | Approval meeting for REL-0047
Jan 2027 | 3 | 2027-01-16 | Sat | RELEASE | REL-0047 | DocuSign Integration Enhancement v1.4 | Legal | Medium / Medium | Impact: Medium
Jan 2027 | 3 | 2027-01-18 | Mon | CAB MEETING | REL-0048 | CAB: Okta Report Fix v4.1... | Security | Small | Approval meeting for REL-0048
Jan 2027 | 3 | 2027-01-20 | Wed | RELEASE | REL-0048 | Okta Report Fix v4.1 | Security | Small / Low | Impact: Low
Jan 2027 | 4 | 2027-01-22 | Fri | CAB MEETING | REL-0049 | CAB: Anaplan Minor Update v3.3... | Finance | Small | Approval meeting for REL-0049
Jan 2027 | 4 | 2027-01-24 | Sun | REGULATORY | REL-0049 | Anaplan Minor Update v3.3 | Finance | Small / Low | SOX Compliance
Jan 2027 | 5 | 2027-01-29 | Fri | CAB MEETING | REL-0050 | CAB: Blue Configuration Change v5.9... | Logistics | Small | Approval meeting for REL-0050
Jan 2027 | 5 | 2027-01-31 | Sun | RELEASE | REL-0050 | Blue Configuration Change v5.9 | Logistics | Small / Low | Impact: Low
Feb 2027 | 1 | 2027-02-02 | Tue | CAB MEETING | REL-0051 | CAB: HubSpot Module Update v4.7... | CRM | Medium | Approval meeting for REL-0051
Feb 2027 | 1 | 2027-02-04 | Thu | RELEASE | REL-0051 | HubSpot Module Update v4.7 | CRM | Medium / Medium | Impact: Medium
Feb 2027 | 1 | 2027-02-06 | Sat | CAB MEETING | REL-0052 | CAB: SAP Configuration Change v1.3... | Manufacturing | Small | Approval meeting for REL-0052
Feb 2027 | 2 | 2027-02-08 | Mon | RELEASE | REL-0052 | SAP Configuration Change v1.3 | Manufacturing | Small / Low | Impact: Low
Feb 2027 | 2 | 2027-02-09 | Tue | CAB MEETING | REL-0053 | CAB: Splunk Global Rollout v5.8... | IT | Large | Approval meeting for REL-0053
Feb 2027 | 2 | 2027-02-12 | Fri | RELEASE | REL-0053 | Splunk Global Rollout v5.8 | IT | Large / High | Impact: High
Feb 2027 | 2 | 2027-02-13 | Sat | CAB MEETING | REL-0054 | CAB: Workday Core Transformation v2... | HR | Large | Approval meeting for REL-0054
Feb 2027 | 3 | 2027-02-16 | Tue | RELEASE | REL-0054 | Workday Core Transformation v2.7 | HR | Large / High | Impact: High
Feb 2027 | 3 | 2027-02-17 | Wed | CAB MEETING | REL-0055 | CAB: DocuSign Major Enhancement v5.... | Legal | Large | Approval meeting for REL-0055
Feb 2027 | 3 | 2027-02-20 | Sat | REGULATORY | REL-0055 | DocuSign Major Enhancement v5.2 | Legal | Large / High | GDPR Compliance
Feb 2027 | 4 | 2027-02-22 | Mon | CAB MEETING | REL-0056 | CAB: Okta Performance Optimization ... | Security | Medium | Approval meeting for REL-0056
Feb 2027 | 4 | 2027-02-24 | Wed | RELEASE | REL-0056 | Okta Performance Optimization v5.0 | Security | Medium / Medium | Impact: Medium
Feb 2027 | 4 | 2027-02-25 | Thu | CAB MEETING | REL-0058 | CAB: Manhattan API Enhancement v2.0... | Logistics | Medium | Approval meeting for REL-0058
Feb 2027 | 4 | 2027-02-26 | Fri | CAB MEETING | REL-0057 | CAB: Coupa Security Patch Bundle v3... | Finance | Medium | Approval meeting for REL-0057
Feb 2027 | 4 | 2027-02-27 | Sat | RELEASE | REL-0058 | Manhattan API Enhancement v2.0 | Logistics | Medium / Low | Impact: Low
Feb 2027 | 4 | 2027-02-28 | Sun | RELEASE | REL-0057 | Coupa Security Patch Bundle v3.3 | Finance | Medium / Medium | Impact: Medium
Mar 2027 | 1 | 2027-03-06 | Sat | CAB MEETING | REL-0059 | CAB: Salesforce Workflow Automation... | CRM | Medium | Approval meeting for REL-0059
Mar 2027 | 2 | 2027-03-08 | Mon | RELEASE | REL-0059 | Salesforce Workflow Automation v5.8 | CRM | Medium / Medium | Impact: Medium
Mar 2027 | 2 | 2027-03-10 | Wed | CAB MEETING | REL-0060 | CAB: Plex UI Tweak v4.0... | Manufacturing | Small | Approval meeting for REL-0060
Mar 2027 | 2 | 2027-03-12 | Fri | RELEASE | REL-0060 | Plex UI Tweak v4.0 | Manufacturing | Small / Low | Impact: Low
Mar 2027 | 2 | 2027-03-14 | Sun | CAB MEETING | REL-0061 | CAB: Datadog API Enhancement v5.6... | IT | Medium | Approval meeting for REL-0061
Mar 2027 | 3 | 2027-03-16 | Tue | RELEASE | REL-0061 | Datadog API Enhancement v5.6 | IT | Medium / Low | Impact: Low
Mar 2027 | 3 | 2027-03-18 | Thu | CAB MEETING | REL-0062 | CAB: SAP Report Fix v2.8... | HR | Small | Approval meeting for REL-0062
Mar 2027 | 3 | 2027-03-20 | Sat | RELEASE | REL-0062 | SAP Report Fix v2.8 | HR | Small / Medium | Impact: Medium
Mar 2027 | 4 | 2027-03-22 | Mon | CAB MEETING | REL-0063 | CAB: Mitratech Workflow Automation ... | Legal | Medium | Approval meeting for REL-0063
Mar 2027 | 4 | 2027-03-24 | Wed | RELEASE | REL-0063 | Mitratech Workflow Automation v2.3 | Legal | Medium / Low | Impact: Low
Mar 2027 | 4 | 2027-03-26 | Fri | CHANGE FREEZE | - | Q1 Quarter-End Freeze START | ALL | Critical | No deployments allowed
Mar 2027 | 4 | 2027-03-28 | Sun | CHANGE FREEZE | - | Q1 Quarter-End Freeze END | ALL | Critical | No deployments allowed
Mar 2027 | 5 | 2027-03-29 | Mon | CAB MEETING | REL-0064 | CAB: Microsoft Integration Enhancem... | Security | Medium | Approval meeting for REL-0064
Mar 2027 | 5 | 2027-03-31 | Wed | REGULATORY | REL-0064 | Microsoft Integration Enhancement v4.1 | Security | Medium / Low | SOC2 Requirement
Apr 2027 | 1 | 2027-04-01 | Thu | CAB MEETING | REL-0065 | CAB: Oracle System Migration v1.9... | Finance | Large | Approval meeting for REL-0065
Apr 2027 | 1 | 2027-04-04 | Sun | RELEASE | REL-0065 | Oracle System Migration v1.9 | Finance | Large / High | Impact: High
Apr 2027 | 1 | 2027-04-06 | Tue | CAB MEETING | REL-0066 | CAB: Oracle Module Update v5.6... | Logistics | Medium | Approval meeting for REL-0066
Apr 2027 | 2 | 2027-04-08 | Thu | RELEASE | REL-0066 | Oracle Module Update v5.6 | Logistics | Medium / Medium | Impact: Medium
Apr 2027 | 2 | 2027-04-09 | Fri | CAB MEETING | REL-0067 | CAB: Salesforce Complete Redesign v... | CRM | Large | Approval meeting for REL-0067
Apr 2027 | 2 | 2027-04-09 | Fri | CAB MEETING | REL-0068 | CAB: Rockwell Minor Update v1.1... | Manufacturing | Small | Approval meeting for REL-0068
Apr 2027 | 2 | 2027-04-11 | Sun | RELEASE | REL-0068 | Rockwell Minor Update v1.1 | Manufacturing | Small / Low | Impact: Low
Apr 2027 | 2 | 2027-04-12 | Mon | RELEASE | REL-0067 | Salesforce Complete Redesign v1.9 | CRM | Large / High | Impact: High
Apr 2027 | 3 | 2027-04-18 | Sun | CAB MEETING | REL-0069 | CAB: BMC UI Tweak v5.1... | IT | Small | Approval meeting for REL-0069
Apr 2027 | 3 | 2027-04-20 | Tue | RELEASE | REL-0069 | BMC UI Tweak v5.1 | IT | Small / Medium | Impact: Medium
Apr 2027 | 4 | 2027-04-22 | Thu | CAB MEETING | REL-0070 | CAB: Oracle Workflow Automation v3.... | HR | Medium | Approval meeting for REL-0070
Apr 2027 | 4 | 2027-04-24 | Sat | VENDOR MAINT | REL-0070 | Oracle Workflow Automation v3.6 | HR | Medium / Medium | Oracle Patch Window
Apr 2027 | 4 | 2027-04-28 | Wed | CAB MEETING | REL-0071 | CAB: Agiloft Minor Update v4.1... | Legal | Small | Approval meeting for REL-0071
Apr 2027 | 5 | 2027-04-30 | Fri | RELEASE | REL-0071 | Agiloft Minor Update v4.1 | Legal | Small / Low | Impact: Low
May 2027 | 1 | 2027-05-01 | Sat | CAB MEETING | REL-0073 | CAB: Kyriba Security Patch Bundle v... | Finance | Medium | Approval meeting for REL-0073
May 2027 | 1 | 2027-05-02 | Sun | CAB MEETING | REL-0072 | CAB: Palo Hotfix v5.8... | Security | Small | Approval meeting for REL-0072
May 2027 | 1 | 2027-05-03 | Mon | RELEASE | REL-0073 | Kyriba Security Patch Bundle v3.6 | Finance | Medium / Medium | Impact: Medium
May 2027 | 1 | 2027-05-04 | Tue | RELEASE | REL-0072 | Palo Hotfix v5.8 | Security | Small / Low | Impact: Low
May 2027 | 2 | 2027-05-10 | Mon | CAB MEETING | REL-0074 | CAB: Oracle Hotfix v4.3... | Logistics | Small | Approval meeting for REL-0074
May 2027 | 2 | 2027-05-12 | Wed | RELEASE | REL-0074 | Oracle Hotfix v4.3 | Logistics | Small / Low | Impact: Low
May 2027 | 2 | 2027-05-14 | Fri | CAB MEETING | REL-0075 | CAB: HubSpot Performance Optimizati... | CRM | Medium | Approval meeting for REL-0075
May 2027 | 3 | 2027-05-16 | Sun | RELEASE | REL-0075 | HubSpot Performance Optimization v3.0 | CRM | Medium / Medium | Impact: Medium
May 2027 | 3 | 2027-05-18 | Tue | CAB MEETING | REL-0076 | CAB: SAP Hotfix v4.1... | Manufacturing | Small | Approval meeting for REL-0076
May 2027 | 3 | 2027-05-20 | Thu | RELEASE | REL-0076 | SAP Hotfix v4.1 | Manufacturing | Small / Low | Impact: Low
May 2027 | 3 | 2027-05-21 | Fri | CAB MEETING | REL-0077 | CAB: Jira Core Transformation v1.8... | IT | Large | Approval meeting for REL-0077
May 2027 | 4 | 2027-05-24 | Mon | RELEASE | REL-0077 | Jira Core Transformation v1.8 | IT | Large / High | Impact: High
May 2027 | 5 | 2027-05-29 | Sat | CAB MEETING | REL-0078 | CAB: ADP Workflow Automation v2.7... | HR | Medium | Approval meeting for REL-0078
May 2027 | 5 | 2027-05-31 | Mon | RELEASE | REL-0078 | ADP Workflow Automation v2.7 | HR | Medium / High | Impact: High
Jun 2027 | 1 | 2027-06-02 | Wed | CAB MEETING | REL-0079 | CAB: Ironclad Module Update v4.7... | Legal | Medium | Approval meeting for REL-0079
Jun 2027 | 1 | 2027-06-04 | Fri | REGULATORY | REL-0079 | Ironclad Module Update v4.7 | Legal | Medium / High | GDPR Compliance
Jun 2027 | 1 | 2027-06-06 | Sun | CAB MEETING | REL-0080 | CAB: CrowdStrike Performance Optimi... | Security | Medium | Approval meeting for REL-0080
Jun 2027 | 2 | 2027-06-08 | Tue | RELEASE | REL-0080 | CrowdStrike Performance Optimization v5.9 | Security | Medium / High | Impact: High
Jun 2027 | 4 | 2027-06-25 | Fri | CHANGE FREEZE | - | Q2 Quarter-End Freeze START | ALL | Critical | No deployments allowed
Jun 2027 | 4 | 2027-06-27 | Sun | CHANGE FREEZE | - | Q2 Quarter-End Freeze END | ALL | Critical | No deployments allowed

## Env booking
🔍 FILTERS |  | Time Period: | All Time | Department: | All | Application: | All | Conflict: | All |  | 💡 Select filters above to highlight matching bookings
Showing: | 101 of 101 bookings
Booking ID | Release ID | Application | Department | Dependencies | Release Size | Prod Release Date | CAB Date | Test Env | Test Start | Test End | Test Days | UAT Env | UAT Start | UAT End | UAT Days | Pre-Prod Env | Pre-Prod Start | Pre-Prod End | Pre-Prod Days | Conflict Flag | Notes
ENV-0001 | REL-0001 | Kyriba | Finance | NA | Small | 2026-06-30 | 2026-06-28 | FIN-TEST-01 | 2026-06-23 | 2026-06-25 | 3 | FIN-UAT-01 | 2026-06-26 | 2026-06-27 | 2 | FIN-PREPROD-01 | 2026-06-28 | 2026-06-28 | 1 | ⚠️ CONFLICT | Resource conflict with REL-0003 - Same Test/UAT env required
ENV-0002 | REL-0002 | Blue Yonder WMS | Logistics | NA | Medium | 2026-07-04 | 2026-07-02 | LOG-TEST-01 | 2026-06-21 | 2026-06-25 | 5 | LOG-UAT-01 | 2026-06-26 | 2026-06-28 | 3 | LOG-PREPROD-01 | 2026-06-29 | 2026-06-30 | 2 |  | Executive sponsor: CFO
ENV-0003 | REL-0003 | Zendesk | CRM | NA | Small | 2026-07-02 | 2026-06-30 | FIN-TEST-01 | 2026-06-25 | 2026-06-27 | 3 | FIN-UAT-01 | 2026-06-28 | 2026-06-29 | 2 | CRM-PREPROD-01 | 2026-06-30 | 2026-06-30 | 1 | ⚠️ CONFLICT | Resource conflict with REL-0007 - Same Test/UAT env required
ENV-0004 | REL-0004 | AVEVA MES | Manufacturing | NA | Medium | 2026-07-12 | 2026-07-10 | MAN-TEST-03 | 2026-06-29 | 2026-07-03 | 5 | MAN-UAT-01 | 2026-07-04 | 2026-07-06 | 3 | MFG-PREPROD-01 | 2026-07-07 | 2026-07-08 | 2 |  | Blackout period consideration
ENV-0005 | REL-0005 | Datadog | IT | NA | Medium | 2026-07-16 | 2026-07-14 | IT-TEST-01 | 2026-07-03 | 2026-07-07 | 5 | IT-UAT-01 | 2026-07-08 | 2026-07-10 | 3 | IT-PREPROD-01 | 2026-07-11 | 2026-07-12 | 2 | ⚠️ CONFLICT | Resource conflict with REL-0010 - Same Test/UAT env required
ENV-0006 | REL-0006 | SAP SuccessFactors | HR | NA | Small | 2026-07-20 | 2026-07-18 | HR-TEST-01 | 2026-07-13 | 2026-07-15 | 3 | HR-UAT-01 | 2026-07-16 | 2026-07-17 | 2 | HR-PREPROD-01 | 2026-07-18 | 2026-07-18 | 1 |  | Integration testing with downstream systems
ENV-0007 | REL-0007 | Mitratech TeamConnect | Legal | NA | Medium | 2026-07-04 | 2026-07-02 | FIN-TEST-01 | 2026-06-21 | 2026-06-25 | 5 | FIN-UAT-01 | 2026-06-26 | 2026-06-28 | 3 | LEG-PREPROD-01 | 2026-06-29 | 2026-06-30 | 2 | ⚠️ CONFLICT | Resource conflict with REL-0012 - Same Test/UAT env required
ENV-0008 | REL-0008 | CrowdStrike Falcon | Security | NA | Small | 2026-07-31 | 2026-07-29 | SEC-TEST-01 | 2026-07-24 | 2026-07-26 | 3 | SEC-UAT-02 | 2026-07-27 | 2026-07-28 | 2 | SEC-PREPROD-01 | 2026-07-29 | 2026-07-29 | 1 |  | Data migration included
ENV-0009 | REL-0009 | Oracle Hyperion HFM | Finance |  | Small | 2026-08-04 | 2026-08-02 | FIN-TEST-03 | 2026-07-28 | 2026-07-30 | 3 | FIN-UAT-01 | 2026-07-31 | 2026-08-01 | 2 | FIN-PREPROD-01 | 2026-08-02 | 2026-08-02 | 1 | ⚠️ CONFLICT | Resource conflict with REL-0014 - Same Test/UAT env required
ENV-0010 | REL-0010 | Manhattan Associates WMS | Logistics | NA | Large | 2026-07-18 | 2026-07-15 | IT-TEST-01 | 2026-06-22 | 2026-07-01 | 10 | IT-UAT-01 | 2026-07-02 | 2026-07-06 | 5 | LOG-PREPROD-01 | 2026-07-08 | 2026-07-11 | 4 | ⚠️ CONFLICT | Resource conflict with REL-0005 - Same Test/UAT env required
ENV-0011 | REL-0011 | HubSpot CRM | CRM | NA | Small | 2026-08-12 | 2026-08-10 | CRM-TEST-02 | 2026-08-05 | 2026-08-07 | 3 | CRM-UAT-01 | 2026-08-08 | 2026-08-09 | 2 | CRM-PREPROD-01 | 2026-08-10 | 2026-08-10 | 1 | ⚠️ CONFLICT | Resource conflict with REL-0014 - Same Test/UAT env required
ENV-0012 | REL-0012 | Plex Smart Manufacturing | Manufacturing | NA | Small | 2026-07-06 | 2026-07-04 | FIN-TEST-01 | 2026-06-29 | 2026-07-01 | 3 | FIN-UAT-01 | 2026-07-02 | 2026-07-03 | 2 | MFG-PREPROD-01 | 2026-07-04 | 2026-07-04 | 1 | ⚠️ CONFLICT | Resource conflict with REL-0007 - Same Test/UAT env required
ENV-0013 | REL-0013 | Dynatrace | IT |  | Small | 2026-08-20 | 2026-08-18 | IT-TEST-03 | 2026-08-13 | 2026-08-15 | 3 | IT-UAT-01 | 2026-08-16 | 2026-08-17 | 2 | IT-PREPROD-01 | 2026-08-18 | 2026-08-18 | 1 | ⚠️ CONFLICT | Resource conflict with REL-0015 - Same Test/UAT env required
ENV-0014 | REL-0014 | Oracle HCM Cloud | HR | NA | Large | 2026-08-14 | 2026-08-11 | CRM-TEST-02 | 2026-07-19 | 2026-07-28 | 10 | CRM-UAT-01 | 2026-07-29 | 2026-08-02 | 5 | HR-PREPROD-01 | 2026-08-04 | 2026-08-07 | 4 | ⚠️ CONFLICT | Resource conflict with REL-0011 - Same Test/UAT env required
ENV-0015 | REL-0015 | DocuSign CLM | Legal | NA | Large | 2026-08-22 | 2026-08-19 | IT-TEST-03 | 2026-07-27 | 2026-08-05 | 10 | IT-UAT-01 | 2026-08-06 | 2026-08-10 | 5 | LEG-PREPROD-01 | 2026-08-12 | 2026-08-15 | 4 | ⚠️ CONFLICT | Resource conflict with REL-0017 - Same Test/UAT env required
ENV-0016 | REL-0016 | CyberArk PAM | Security | NA | Large | 2026-09-04 | 2026-09-01 | SEC-TEST-01 | 2026-08-09 | 2026-08-18 | 10 | SEC-UAT-02 | 2026-08-19 | 2026-08-23 | 5 | SEC-PREPROD-01 | 2026-08-25 | 2026-08-28 | 4 |  | Change Advisory Board approval needed
ENV-0017 | REL-0017 | HighRadius | Finance |  | Small | 2026-08-24 | 2026-08-22 | IT-TEST-03 | 2026-08-17 | 2026-08-19 | 3 | IT-UAT-01 | 2026-08-20 | 2026-08-21 | 2 | FIN-PREPROD-01 | 2026-08-22 | 2026-08-22 | 1 | ⚠️ CONFLICT | Resource conflict with REL-0022 - Same Test/UAT env required
ENV-0018 | REL-0018 | Oracle Transportation Management | Logistics | NA | Small | 2026-09-12 | 2026-09-10 | LOG-TEST-03 | 2026-09-05 | 2026-09-07 | 3 | LOG-UAT-02 | 2026-09-08 | 2026-09-09 | 2 | LOG-PREPROD-01 | 2026-09-10 | 2026-09-10 | 1 |  | Audit finding remediation
ENV-0019 | REL-0019 | Salesforce Service Cloud | CRM | NA | Small | 2026-09-16 | 2026-09-14 | CRM-TEST-01 | 2026-09-09 | 2026-09-11 | 3 | CRM-UAT-02 | 2026-09-12 | 2026-09-13 | 2 | CRM-PREPROD-01 | 2026-09-14 | 2026-09-14 | 1 | ⚠️ CONFLICT | Resource conflict with REL-0021 - Same Test/UAT env required
ENV-0020 | REL-0020 | Rockwell FactoryTalk | Manufacturing | NA | Small | 2026-09-20 | 2026-09-18 | MAN-TEST-03 | 2026-09-13 | 2026-09-15 | 3 | MAN-UAT-01 | 2026-09-16 | 2026-09-17 | 2 | MFG-PREPROD-01 | 2026-09-18 | 2026-09-18 | 1 |  | Holiday freeze exception requested
ENV-0021 | REL-0021 | Splunk Enterprise | IT |  | Small | 2026-09-18 | 2026-09-16 | CRM-TEST-01 | 2026-09-11 | 2026-09-13 | 3 | CRM-UAT-02 | 2026-09-14 | 2026-09-15 | 2 | IT-PREPROD-01 | 2026-09-16 | 2026-09-16 | 1 | ⚠️ CONFLICT | Resource conflict with REL-0026 - Same Test/UAT env required
ENV-0022 | REL-0022 | Oracle HCM Cloud | HR | NA | Medium | 2026-08-26 | 2026-08-24 | IT-TEST-03 | 2026-08-13 | 2026-08-17 | 5 | IT-UAT-01 | 2026-08-18 | 2026-08-20 | 3 | HR-PREPROD-01 | 2026-08-21 | 2026-08-22 | 2 | ⚠️ CONFLICT | Resource conflict with REL-0017 - Same Test/UAT env required
ENV-0023 | REL-0023 | DocuSign CLM | Legal | NA | Medium | 2026-10-04 | 2026-10-02 | LEG-TEST-02 | 2026-09-21 | 2026-09-25 | 5 | LEG-UAT-02 | 2026-09-26 | 2026-09-28 | 3 | LEG-PREPROD-01 | 2026-09-29 | 2026-09-30 | 2 | ⚠️ CONFLICT | Resource conflict with REL-0027 - Same Test/UAT env required
ENV-0024 | REL-0024 | Okta Identity Cloud | Security | NA | Small | 2026-10-08 | 2026-10-06 | SEC-TEST-01 | 2026-10-01 | 2026-10-03 | 3 | SEC-UAT-02 | 2026-10-04 | 2026-10-05 | 2 | SEC-PREPROD-01 | 2026-10-06 | 2026-10-06 | 1 |  | Security review pending
ENV-0025 | REL-0025 | Coupa | Finance |  | Medium | 2026-10-12 | 2026-10-10 | FIN-TEST-03 | 2026-09-29 | 2026-10-03 | 5 | FIN-UAT-02 | 2026-10-04 | 2026-10-06 | 3 | FIN-PREPROD-01 | 2026-10-07 | 2026-10-08 | 2 |  | DR sync required post-deployment
ENV-0026 | REL-0026 | Kinaxis RapidResponse | Logistics | NA | Medium | 2026-09-20 | 2026-09-18 | CRM-TEST-01 | 2026-09-07 | 2026-09-11 | 5 | CRM-UAT-02 | 2026-09-12 | 2026-09-14 | 3 | LOG-PREPROD-01 | 2026-09-15 | 2026-09-16 | 2 | ⚠️ CONFLICT | Resource conflict with REL-0021 - Same Test/UAT env required
ENV-0027 | REL-0027 | Salesforce Sales Cloud | CRM | NA | Small | 2026-10-06 | 2026-10-04 | LEG-TEST-02 | 2026-09-29 | 2026-10-01 | 3 | LEG-UAT-02 | 2026-10-02 | 2026-10-03 | 2 | CRM-PREPROD-01 | 2026-10-04 | 2026-10-04 | 1 | ⚠️ CONFLICT | Resource conflict with REL-0023 - Same Test/UAT env required
ENV-0028 | REL-0028 | SAP S/4HANA Manufacturing | Manufacturing | NA | Large | 2026-10-24 | 2026-10-21 | MAN-TEST-03 | 2026-09-28 | 2026-10-07 | 10 | MAN-UAT-01 | 2026-10-08 | 2026-10-12 | 5 | MFG-PREPROD-01 | 2026-10-14 | 2026-10-17 | 4 |  | Critical for Q3 financial close
ENV-0029 | REL-0029 | Datadog | IT |  | Medium | 2026-10-31 | 2026-10-29 | IT-TEST-03 | 2026-10-18 | 2026-10-22 | 5 | IT-UAT-01 | 2026-10-23 | 2026-10-25 | 3 | IT-PREPROD-01 | 2026-10-26 | 2026-10-27 | 2 |  | Dependencies on infrastructure team
ENV-0030 | REL-0030 | Cornerstone OnDemand | HR | NA | Medium | 2026-11-04 | 2026-11-02 | HR-TEST-02 | 2026-10-22 | 2026-10-26 | 5 | HR-UAT-01 | 2026-10-27 | 2026-10-29 | 3 | HR-PREPROD-01 | 2026-10-30 | 2026-10-31 | 2 |  | Dependent on vendor patch delivery
ENV-0031 | REL-0031 | Mitratech TeamConnect | Legal | NA | Small | 2026-11-08 | 2026-11-06 | LEG-TEST-02 | 2026-11-01 | 2026-11-03 | 3 | LEG-UAT-02 | 2026-11-04 | 2026-11-05 | 2 | LEG-PREPROD-01 | 2026-11-06 | 2026-11-06 | 1 |  | Executive sponsor: CIO
ENV-0032 | REL-0032 | CrowdStrike Falcon | Security | NA | Small | 2026-11-12 | 2026-11-10 | SEC-TEST-01 | 2026-11-05 | 2026-11-07 | 3 | SEC-UAT-02 | 2026-11-08 | 2026-11-09 | 2 | SEC-PREPROD-01 | 2026-11-10 | 2026-11-10 | 1 |  | Integration testing with downstream systems
ENV-0033 | REL-0033 | Oracle Hyperion HFM | Finance |  | Large | 2026-11-16 | 2026-11-13 | FIN-TEST-01 | 2026-10-21 | 2026-10-30 | 10 | FIN-UAT-01 | 2026-10-31 | 2026-11-04 | 5 | FIN-PREPROD-01 | 2026-11-06 | 2026-11-09 | 4 |  | Dependencies on infrastructure team
ENV-0034 | REL-0034 | Manhattan Associates WMS | Logistics | NA | Medium | 2026-11-20 | 2026-11-18 | LOG-TEST-01 | 2026-11-07 | 2026-11-11 | 5 | LOG-UAT-01 | 2026-11-12 | 2026-11-14 | 3 | LOG-PREPROD-01 | 2026-11-15 | 2026-11-16 | 2 |  | Executive sponsor: CFO
ENV-0035 | REL-0035 | Salesforce Service Cloud | CRM | NA | Small | 2026-11-24 | 2026-11-22 | CRM-TEST-01 | 2026-11-17 | 2026-11-19 | 3 | CRM-UAT-02 | 2026-11-20 | 2026-11-21 | 2 | CRM-PREPROD-01 | 2026-11-22 | 2026-11-22 | 1 |  | Change Advisory Board approval needed
ENV-0036 | REL-0036 | Plex Smart Manufacturing | Manufacturing | NA | Small | 2026-11-30 | 2026-11-28 | MAN-TEST-03 | 2026-11-23 | 2026-11-25 | 3 | MAN-UAT-01 | 2026-11-26 | 2026-11-27 | 2 | MFG-PREPROD-01 | 2026-11-28 | 2026-11-28 | 1 |  | Data migration included
ENV-0037 | REL-0037 | Dynatrace | IT |  | Large | 2026-12-04 | 2026-12-01 | IT-TEST-03 | 2026-11-08 | 2026-11-17 | 10 | IT-UAT-02 | 2026-11-18 | 2026-11-22 | 5 | IT-PREPROD-01 | 2026-11-24 | 2026-11-27 | 4 |  | Customer-facing impact - coordinate with support
ENV-0038 | REL-0038 | SAP SuccessFactors | HR | NA | Small | 2026-12-08 | 2026-12-06 | HR-TEST-02 | 2026-12-01 | 2026-12-03 | 3 | HR-UAT-02 | 2026-12-04 | 2026-12-05 | 2 | HR-PREPROD-01 | 2026-12-06 | 2026-12-06 | 1 |  | Dependent on vendor patch delivery
ENV-0039 | REL-0039 | Agiloft CLM | Legal | NA | Large | 2026-12-12 | 2026-12-09 | LEG-TEST-03 | 2026-11-16 | 2026-11-25 | 10 | LEG-UAT-01 | 2026-11-26 | 2026-11-30 | 5 | LEG-PREPROD-01 | 2026-12-02 | 2026-12-05 | 4 |  | Holiday freeze exception requested
ENV-0040 | REL-0040 | Palo Alto Cortex XDR | Security | NA | Small | 2026-12-16 | 2026-12-14 | SEC-TEST-03 | 2026-12-09 | 2026-12-11 | 3 | SEC-UAT-02 | 2026-12-12 | 2026-12-13 | 2 | SEC-PREPROD-01 | 2026-12-14 | 2026-12-14 | 1 |  | Critical for Q3 financial close
ENV-0041 | REL-0041 | Anaplan | Finance |  | Small | 2026-12-20 | 2026-12-18 | FIN-TEST-01 | 2026-12-13 | 2026-12-15 | 3 | FIN-UAT-01 | 2026-12-16 | 2026-12-17 | 2 | FIN-PREPROD-01 | 2026-12-18 | 2026-12-18 | 1 | ⚠️ CONFLICT | Resource conflict with REL-0043 - Overlapping Test/UAT window
ENV-0042 | REL-0042 | Oracle Transportation Management | Logistics | NA | Medium | 2026-12-24 | 2026-12-22 | LOG-TEST-01 | 2026-12-11 | 2026-12-15 | 5 | LOG-UAT-01 | 2026-12-16 | 2026-12-18 | 3 | LOG-PREPROD-01 | 2026-12-19 | 2026-12-20 | 2 |  | Executive sponsor: CFO
ENV-0043 | REL-0043 | Microsoft Dynamics 365 CRM | CRM | NA | Medium | 2026-12-23 | 2026-12-21 | FIN-TEST-01 | 2026-12-10 | 2026-12-14 | 5 | FIN-UAT-01 | 2026-12-15 | 2026-12-17 | 3 | CRM-PREPROD-01 | 2026-12-18 | 2026-12-19 | 2 | ⚠️ CONFLICT | Resource conflict with REL-0041 - Overlapping Test/UAT window
ENV-0044 | REL-0044 | Siemens Opcenter | Manufacturing | NA | Medium | 2027-01-04 | 2027-01-02 | MAN-TEST-01 | 2026-12-22 | 2026-12-26 | 5 | MAN-UAT-01 | 2026-12-27 | 2026-12-29 | 3 | MFG-PREPROD-01 | 2026-12-30 | 2026-12-31 | 2 |  | License renewal dependency
ENV-0045 | REL-0045 | Splunk Enterprise | IT |  | Large | 2027-01-08 | 2027-01-05 | IT-TEST-01 | 2026-12-13 | 2026-12-22 | 10 | IT-UAT-01 | 2026-12-23 | 2026-12-27 | 5 | IT-PREPROD-01 | 2026-12-29 | 2027-01-01 | 4 |  | Critical for Q3 financial close
ENV-0046 | REL-0046 | SAP SuccessFactors | HR | NA | Small | 2027-01-12 | 2027-01-10 | HR-TEST-03 | 2027-01-05 | 2027-01-07 | 3 | HR-UAT-02 | 2027-01-08 | 2027-01-09 | 2 | HR-PREPROD-01 | 2027-01-10 | 2027-01-10 | 1 |  | Executive sponsor: CFO
ENV-0047 | REL-0047 | DocuSign CLM | Legal | NA | Medium | 2027-01-16 | 2027-01-14 | LEG-TEST-02 | 2027-01-03 | 2027-01-07 | 5 | LEG-UAT-02 | 2027-01-08 | 2027-01-10 | 3 | LEG-PREPROD-01 | 2027-01-11 | 2027-01-12 | 2 |  | Customer-facing impact - coordinate with support
ENV-0048 | REL-0048 | Okta Identity Cloud | Security | NA | Small | 2027-01-20 | 2027-01-18 | SEC-TEST-03 | 2027-01-13 | 2027-01-15 | 3 | SEC-UAT-01 | 2027-01-16 | 2027-01-17 | 2 | SEC-PREPROD-01 | 2027-01-18 | 2027-01-18 | 1 |  | External vendor coordination needed
ENV-0049 | REL-0049 | Anaplan | Finance |  | Small | 2027-01-24 | 2027-01-22 | FIN-TEST-02 | 2027-01-17 | 2027-01-19 | 3 | FIN-UAT-02 | 2027-01-20 | 2027-01-21 | 2 | FIN-PREPROD-01 | 2027-01-22 | 2027-01-22 | 1 |  | DR sync required post-deployment
ENV-0050 | REL-0050 | Blue Yonder WMS | Logistics | NA | Small | 2027-01-31 | 2027-01-29 | LOG-TEST-01 | 2027-01-24 | 2027-01-26 | 3 | LOG-UAT-02 | 2027-01-27 | 2027-01-28 | 2 | LOG-PREPROD-01 | 2027-01-29 | 2027-01-29 | 1 |  | Executive sponsor: CIO
ENV-0051 | REL-0051 | HubSpot CRM | CRM | NA | Medium | 2027-02-04 | 2027-02-02 | CRM-TEST-03 | 2027-01-22 | 2027-01-26 | 5 | CRM-UAT-02 | 2027-01-27 | 2027-01-29 | 3 | CRM-PREPROD-01 | 2027-01-30 | 2027-01-31 | 2 |  | Requires weekend deployment window
ENV-0052 | REL-0052 | SAP S/4HANA Manufacturing | Manufacturing | NA | Small | 2027-02-08 | 2027-02-06 | MAN-TEST-01 | 2027-02-01 | 2027-02-03 | 3 | MAN-UAT-01 | 2027-02-04 | 2027-02-05 | 2 | MFG-PREPROD-01 | 2027-02-06 | 2027-02-06 | 1 |  | DR sync required post-deployment
ENV-0053 | REL-0053 | Splunk Enterprise | IT |  | Large | 2027-02-12 | 2027-02-09 | IT-TEST-03 | 2027-01-17 | 2027-01-26 | 10 | IT-UAT-02 | 2027-01-27 | 2027-01-31 | 5 | IT-PREPROD-01 | 2027-02-02 | 2027-02-05 | 4 |  | Dependent on vendor patch delivery
ENV-0054 | REL-0054 | Workday HCM | HR | NA | Large | 2027-02-16 | 2027-02-13 | HR-TEST-01 | 2027-01-21 | 2027-01-30 | 10 | HR-UAT-01 | 2027-01-31 | 2027-02-04 | 5 | HR-PREPROD-01 | 2027-02-06 | 2027-02-09 | 4 |  | Training materials to be updated
ENV-0055 | REL-0055 | DocuSign CLM | Legal | NA | Large | 2027-02-20 | 2027-02-17 | LEG-TEST-03 | 2027-01-25 | 2027-02-03 | 10 | LEG-UAT-01 | 2027-02-04 | 2027-02-08 | 5 | LEG-PREPROD-01 | 2027-02-10 | 2027-02-13 | 4 |  | Rollback plan required
ENV-0056 | REL-0056 | Okta Identity Cloud | Security | NA | Medium | 2027-02-24 | 2027-02-22 | SEC-TEST-01 | 2027-02-11 | 2027-02-15 | 5 | SEC-UAT-02 | 2027-02-16 | 2027-02-18 | 3 | SEC-PREPROD-01 | 2027-02-19 | 2027-02-20 | 2 | ⚠️ CONFLICT | Resource conflict with REL-0058 - Overlapping Test/UAT window
ENV-0057 | REL-0057 | Coupa | Finance |  | Medium | 2027-02-28 | 2027-02-26 | FIN-TEST-02 | 2027-02-15 | 2027-02-19 | 5 | FIN-UAT-01 | 2027-02-20 | 2027-02-22 | 3 | FIN-PREPROD-01 | 2027-02-23 | 2027-02-24 | 2 |  | External vendor coordination needed
ENV-0058 | REL-0058 | Manhattan Associates WMS | Logistics | NA | Medium | 2027-02-27 | 2027-02-25 | SEC-TEST-01 | 2027-02-14 | 2027-02-18 | 5 | SEC-UAT-02 | 2027-02-19 | 2027-02-21 | 3 | LOG-PREPROD-01 | 2027-02-22 | 2027-02-23 | 2 | ⚠️ CONFLICT | Resource conflict with REL-0056 - Overlapping Test/UAT window
ENV-0059 | REL-0059 | Salesforce Service Cloud | CRM | NA | Medium | 2027-03-08 | 2027-03-06 | CRM-TEST-03 | 2027-02-23 | 2027-02-27 | 5 | CRM-UAT-02 | 2027-02-28 | 2027-03-02 | 3 | CRM-PREPROD-01 | 2027-03-03 | 2027-03-04 | 2 |  | Holiday freeze exception requested
ENV-0060 | REL-0060 | Plex Smart Manufacturing | Manufacturing | NA | Small | 2027-03-12 | 2027-03-10 | MAN-TEST-02 | 2027-03-05 | 2027-03-07 | 3 | MAN-UAT-02 | 2027-03-08 | 2027-03-09 | 2 | MFG-PREPROD-01 | 2027-03-10 | 2027-03-10 | 1 |  | Performance testing mandatory
ENV-0061 | REL-0061 | Datadog | IT |  | Medium | 2027-03-16 | 2027-03-14 | IT-TEST-02 | 2027-03-03 | 2027-03-07 | 5 | IT-UAT-01 | 2027-03-08 | 2027-03-10 | 3 | IT-PREPROD-01 | 2027-03-11 | 2027-03-12 | 2 |  | Holiday freeze exception requested
ENV-0062 | REL-0062 | SAP SuccessFactors | HR | NA | Small | 2027-03-20 | 2027-03-18 | HR-TEST-03 | 2027-03-13 | 2027-03-15 | 3 | HR-UAT-02 | 2027-03-16 | 2027-03-17 | 2 | HR-PREPROD-01 | 2027-03-18 | 2027-03-18 | 1 |  | Dependent on vendor patch delivery
ENV-0063 | REL-0063 | Mitratech TeamConnect | Legal | NA | Medium | 2027-03-24 | 2027-03-22 | LEG-TEST-01 | 2027-03-11 | 2027-03-15 | 5 | LEG-UAT-02 | 2027-03-16 | 2027-03-18 | 3 | LEG-PREPROD-01 | 2027-03-19 | 2027-03-20 | 2 |  | Business continuity testing required
ENV-0064 | REL-0064 | Microsoft Sentinel | Security | NA | Medium | 2027-03-31 | 2027-03-29 | SEC-TEST-03 | 2027-03-18 | 2027-03-22 | 5 | SEC-UAT-02 | 2027-03-23 | 2027-03-25 | 3 | SEC-PREPROD-01 | 2027-03-26 | 2027-03-27 | 2 |  | Customer-facing impact - coordinate with support
ENV-0065 | REL-0065 | Oracle Hyperion HFM | Finance |  | Large | 2027-04-04 | 2027-04-01 | FIN-TEST-03 | 2027-03-09 | 2027-03-18 | 10 | FIN-UAT-02 | 2027-03-19 | 2027-03-23 | 5 | FIN-PREPROD-01 | 2027-03-25 | 2027-03-28 | 4 |  | Dependencies on infrastructure team
ENV-0066 | REL-0066 | Oracle Transportation Management | Logistics | NA | Medium | 2027-04-08 | 2027-04-06 | LOG-TEST-02 | 2027-03-26 | 2027-03-30 | 5 | LOG-UAT-01 | 2027-03-31 | 2027-04-02 | 3 | LOG-PREPROD-01 | 2027-04-03 | 2027-04-04 | 2 | ⚠️ CONFLICT | Resource conflict with REL-0068 - Overlapping Test/UAT window
ENV-0067 | REL-0067 | Salesforce Sales Cloud | CRM | NA | Large | 2027-04-12 | 2027-04-09 | CRM-TEST-03 | 2027-03-17 | 2027-03-26 | 10 | CRM-UAT-02 | 2027-03-27 | 2027-03-31 | 5 | CRM-PREPROD-01 | 2027-04-02 | 2027-04-05 | 4 |  | Blackout period consideration
ENV-0068 | REL-0068 | Rockwell FactoryTalk | Manufacturing | NA | Small | 2027-04-11 | 2027-04-09 | LOG-TEST-02 | 2027-04-04 | 2027-04-06 | 3 | LOG-UAT-01 | 2027-04-07 | 2027-04-08 | 2 | MFG-PREPROD-01 | 2027-04-09 | 2027-04-09 | 1 | ⚠️ CONFLICT | Resource conflict with REL-0066 - Overlapping Test/UAT window
ENV-0069 | REL-0069 | BMC Remedy | IT |  | Small | 2027-04-20 | 2027-04-18 | IT-TEST-01 | 2027-04-13 | 2027-04-15 | 3 | IT-UAT-01 | 2027-04-16 | 2027-04-17 | 2 | IT-PREPROD-01 | 2027-04-18 | 2027-04-18 | 1 |  | Rollback plan required
ENV-0070 | REL-0070 | Oracle HCM Cloud | HR | NA | Medium | 2027-04-24 | 2027-04-22 | HR-TEST-02 | 2027-04-11 | 2027-04-15 | 5 | HR-UAT-02 | 2027-04-16 | 2027-04-18 | 3 | HR-PREPROD-01 | 2027-04-19 | 2027-04-20 | 2 |  | Requires weekend deployment window
ENV-0071 | REL-0071 | Agiloft CLM | Legal | NA | Small | 2027-04-30 | 2027-04-28 | LEG-TEST-03 | 2027-04-23 | 2027-04-25 | 3 | LEG-UAT-01 | 2027-04-26 | 2027-04-27 | 2 | LEG-PREPROD-01 | 2027-04-28 | 2027-04-28 | 1 | ⚠️ CONFLICT | Resource conflict with REL-0073 - Overlapping Test/UAT window
ENV-0072 | REL-0072 | Palo Alto Cortex XDR | Security | NA | Small | 2027-05-04 | 2027-05-02 | SEC-TEST-01 | 2027-04-27 | 2027-04-29 | 3 | SEC-UAT-01 | 2027-04-30 | 2027-05-01 | 2 | SEC-PREPROD-01 | 2027-05-02 | 2027-05-02 | 1 |  | Dependent on vendor patch delivery
ENV-0073 | REL-0073 | Kyriba | Finance |  | Medium | 2027-05-03 | 2027-05-01 | LEG-TEST-03 | 2027-04-20 | 2027-04-24 | 5 | LEG-UAT-01 | 2027-04-25 | 2027-04-27 | 3 | FIN-PREPROD-01 | 2027-04-28 | 2027-04-29 | 2 | ⚠️ CONFLICT | Resource conflict with REL-0071 - Overlapping Test/UAT window
ENV-0074 | REL-0074 | Oracle Transportation Management | Logistics | NA | Small | 2027-05-12 | 2027-05-10 | LOG-TEST-03 | 2027-05-05 | 2027-05-07 | 3 | LOG-UAT-02 | 2027-05-08 | 2027-05-09 | 2 | LOG-PREPROD-01 | 2027-05-10 | 2027-05-10 | 1 |  | Dependent on vendor patch delivery
ENV-0075 | REL-0075 | HubSpot CRM | CRM | NA | Medium | 2027-05-16 | 2027-05-14 | CRM-TEST-02 | 2027-05-03 | 2027-05-07 | 5 | CRM-UAT-02 | 2027-05-08 | 2027-05-10 | 3 | CRM-PREPROD-01 | 2027-05-11 | 2027-05-12 | 2 |  | Dependencies on infrastructure team
ENV-0076 | REL-0076 | SAP S/4HANA Manufacturing | Manufacturing | NA | Small | 2027-05-20 | 2027-05-18 | MAN-TEST-01 | 2027-05-13 | 2027-05-15 | 3 | MAN-UAT-01 | 2027-05-16 | 2027-05-17 | 2 | MFG-PREPROD-01 | 2027-05-18 | 2027-05-18 | 1 |  | Security review pending
ENV-0077 | REL-0077 | Jira Service Management | IT |  | Large | 2027-05-24 | 2027-05-21 | IT-TEST-02 | 2027-04-28 | 2027-05-07 | 10 | IT-UAT-01 | 2027-05-08 | 2027-05-12 | 5 | IT-PREPROD-01 | 2027-05-14 | 2027-05-17 | 4 |  | Rollback plan required
ENV-0078 | REL-0078 | ADP Workforce Now | HR | NA | Medium | 2027-05-31 | 2027-05-29 | HR-TEST-03 | 2027-05-18 | 2027-05-22 | 5 | HR-UAT-02 | 2027-05-23 | 2027-05-25 | 3 | HR-PREPROD-01 | 2027-05-26 | 2027-05-27 | 2 |  | Regulatory deadline driven
ENV-0079 | REL-0079 | Ironclad | Legal | NA | Medium | 2027-06-04 | 2027-06-02 | LEG-TEST-01 | 2027-05-22 | 2027-05-26 | 5 | LEG-UAT-01 | 2027-05-27 | 2027-05-29 | 3 | LEG-PREPROD-01 | 2027-05-30 | 2027-05-31 | 2 |  | Dependencies on infrastructure team
ENV-0080 | REL-0080 | CrowdStrike Falcon | Security | NA | Medium | 2027-06-08 | 2027-06-06 | SEC-TEST-03 | 2027-05-26 | 2027-05-30 | 5 | SEC-UAT-01 | 2027-05-31 | 2027-06-02 | 3 | SEC-PREPROD-01 | 2027-06-03 | 2027-06-04 | 2 |  | Audit finding remediation
ENVIRONMENT BOOKING SUMMARY
Testing Phase Durations:
• Large Releases: Test (10 days) → UAT (5 days) → Pre-Prod (4 days) → CAB (-3 days) → Prod (+2 days max)
• Medium Releases: Test (5 days) → UAT (3 days) → Pre-Prod (2 days) → CAB (-2 days) → Prod (+1 day)
• Small Releases: Test (3 days) → UAT (2 days) → Pre-Prod (1 day) → CAB (-2 days) → Prod (same day)
Color Legend:
Blue = Test Phase ¦ Green = UAT Phase ¦ Orange = Pre-Prod Phase ¦ Purple = CAB Date ¦ Peach = Prod Date ¦ Red = Conflict |  |  |  |  | Test Phase | UAT Phase |  | Pre-Prod Phase | Conflict
Environment Usage Statistics
Metric | Value | Formula
Total Releases | 80
Releases with Conflicts | 26
Large Releases | 15
Medium Releases | 30
Small Releases | 35
Total Test Days Required | 795
CAB Meetings Required | 80
CHANGE FREEZE PERIODS
Freeze Period | Start Date | End Date | Duration (Days) |  | Impact
Year-End Freeze 2026 | 2026-12-13 | 2026-12-31 | 19 |  | No production deployments. Emergency hotfixes only.
Q1 Quarter-End Freeze | 2027-03-26 | 2027-03-28 | 3 |  | Finance close period. Limited deployments.
Q2 Quarter-End Freeze | 2027-06-25 | 2027-06-27 | 3 |  | Finance close period. Limited deployments.

## Risk Factors
COMPREHENSIVE RELEASE RISK SCORING MODEL
Multi-factor weighted risk assessment for Release Desk Go/No-Go decisions
[8 empty] | Total Releases Assessed | 12
Category | Factor Name | Weight | Description | Score 1 (Best) | Score 5 (Worst) | Data Source |  | SEVERE Risk Releases | 2 | Immediate review required
Technical Complexity | Files Changed | 4% | Number of modified files | <10 | ≥100 | Git/SCM |  | CRITICAL Risk Releases | 1 | Executive approval needed
| Code Churn (LOC) | 3% | Lines of code changed | <200 | ≥3000 | Git/SCM |  | HIGH Risk Releases | 0 | CAB review required
| DB Schema Changes | 5% | Database schema modifications | 0 | ≥5 | Migration Scripts |  | MEDIUM Risk Releases | 5 | Enhanced monitoring
| API Contract Changes | 4% | Breaking API changes | 0 | ≥4 | API Specs |  | LOW Risk Releases | 4 | Standard deployment
| New Technology Stack | 2% | Unfamiliar tech introduced | Proven stack | Entirely new | Architecture Review
Testing Quality | Test Coverage % | 6% | Code coverage percentage | >90% | <60% | SonarQube |  | Average Risk Score | 2.28
| Test Execution Days | 3% | Testing duration | <3 days | ≥10 days | Test Plan |  | Highest Risk Release | REL-0010 | 4.52
| Bugs Found (Test) | 4% | Defects discovered in testing | <3 | ≥15 | Jira
| Bug Fix Rate % | 2% | Defects fixed vs found | >95% | <60% | Jira
| UAT Duration Days | 3% | UAT testing period | <3 days | ≥10 days | UAT Plan
| UAT Defects | 4% | Defects found in UAT | <2 | ≥8 | Jira
| UAT Sign-off | 2% | Business sign-off status | Full sign-off | No sign-off | UAT Tracker
| Test Env Parity | 2% | Test env match with Prod | ≥95% match | <60% match | Env Config
Security & Compliance | Critical/High Vulns | 3% | Open security vulnerabilities | 0 | ≥5 | SAST/DAST
| Pen Test Sign-off | 2% | Penetration test status | Passed | Not done | Security Team
| Compliance Gate | 3% | SOX/GDPR/PCI-DSS status | All passed | Blocked | GRC System
Data Migration | Migration Required | 1% | Data migration needed | No | Yes, complex | Release Notes |  | RISK SCORE THRESHOLDS
| Backup Restore Tested | 1.5% | Backup/restore verified | Yes, verified | Not tested | DBA Team |  | Level | Score Range | Action
| Migration Script Tested | 1.5% | Migration scripts validated | Tested in Pre-prod | Not tested | DBA Team |  | LOW | < 1.5 | Standard deployment
Resource & Schedule | Testers Allocated | 2% | QA resource count | >3 | 1 or none | Resource Plan |  | MEDIUM | 1.5 - 2.5 | Enhanced monitoring
| Key Staff Availability | 3% | Critical personnel present | All available | Key staff OOO | Leave Calendar |  | HIGH | 2.5 - 3.5 | CAB review required
| Days Until Release | 4% | Time to deployment | >30 days | <5 days | Release Schedule |  | CRITICAL | 3.5 - 4.0 | Executive approval needed
| Downstream Releases | 3% | Dependent releases count | 0 | ≥4 | Dependencies |  | SEVERE | ≥ 4.0 | Postpone or major mitigation
| Overlapping Releases | 2% | Releases in same window | 0 | ≥4 | Release Calendar
Env & Dependencies | Drift Issues | 3% | Environment drift count | 0 | ≥4 | Drift Tracker
| Dependency Count | 2% | External dependencies | 0 | ≥4 | Dependencies
| Dependency Health | 2% | Upstream system status | All healthy | Critical blocked | Health Dashboard
| Feature Flag Cleanup | 2% | Stale feature flags | Clean | ≥5 stale flags | Feature Mgmt
Operational Readiness | Rollback Plan | 2% | Rollback documented | Full plan tested | No plan | Runbook
| Go-Live Checklist % | 2% | Checklist completion | >90% | <50% | Checklist
| Change Freeze Impact | 1.5% | Freeze window conflict | No conflict | During freeze | Calendar
| Vendor Coordination | 0.5% | Vendor readiness | Confirmed | Not coordinated | Vendor Mgmt
| Rollback Time RTO | 2% | Rollback duration (min) | <15 min | >120 min | Runbook
| Deployment Automation % | 1.5% | Automation level | >90% | <50% | CI/CD Pipeline
Performance & Scalability | Load Test Status | 2% | Load testing result | Passed | Not done | Perf Team
| Perf Regression % | 2% | Performance vs baseline | <5% | >25% | APM Tools
Release History | BC Tested | 1.5% | Backward compatibility | Fully tested | Not tested | Test Results
| Rollback Flow Tested | 1.5% | Rollback rehearsal done | Tested in Pre-prod | Never tested | Deployment Runbook
| Previous Failures | 0.5% | Past failure history | 0 failures (12mo) | ≥3 failures | Incident History
| Release Cadence Dev | 0.5% | Deviation from schedule | On schedule | >14 days late | Release Plan
| MTBF Days | 0.5% | Mean time between failures | >180 days | <14 days | Incident Metrics
| Recent Incidents | 0.5% | Incidents last 30 days | 0 | ≥3 | Incident Mgmt
Business Criticality | Revenue Impact | 1% | Revenue risk if failed | Low | High | Business Team
| User Blast Radius | 1% | Users/customers affected | <100 | >100K or all | Product Team
WEIGHT SUMMARY BY CATEGORY
Category | Weight | Factors
Technical Complexity | 18% | 5 factors
Testing Quality | 26% | 8 factors
Security & Compliance | 8% | 3 factors
Data Migration | 4% | 3 factors
Resource & Schedule | 14% | 5 factors
Env & Dependencies | 9% | 4 factors
Operational Readiness | 10% | 6 factors
Performance & Scalability | 4% | 2 factors
Release History | 5% | 6 factors
Business Criticality | 2% | 2 factors
TOTAL | 100% | 44 factors
FORMULA: Weighted Score = Σ (Factor Score × Factor Weight)
RELEASE RISK ASSESSMENT DATA
Release ID | Release Name | Prod Date | Days Out | Files Changed | Code Churn | DB Changes | API Changes | New Tech Stack | Test Coverage % | Test Days | Test Bugs | Bug Fix Rate % | UAT Days | UAT Defects | UAT Sign-off | Test Env Parity | Crit/High Vulns | Pen Test | Compliance Gate | Migration Req | Backup Tested | Migration Script | Team Size | Deploy Window | Freeze Proximity | Key Staff Avail | Overlapping Rels | Dep Count | Dep Health | Vendor Involvement | Feature Flags | Rollback Plan | Docs Complete | Monitoring Ready | Runbook Updated | Rollback RTO | Deploy Auto % | Load Test | Perf Regression % | Vendor Patch | Cadence Dev | MTBF Days | Past Failures | BC Tested | Rollback Tested | Revenue Impact | Blast Radius | WEIGHTED SCORE | RISK LEVEL
REL-0001 | Kyriba UI Tweak v4.5 | 2026-06-30 | 5 | 12 | 320 | 0 | 0 | 1 | 85 | 3 | 2 | 100 | 2 | 0 | 4 | 4 | 0 | 4 | 5 | 0 | 5 | 5 | 2 | 2 | 30 | 5 | 1 | 2 | 5 | 0 | 5 | 4 | 4 | 4 | 4 | 15 | 90 | 5 | 5 | 5 | 0 | 90 | 0 | 5 | 4 | 1 | 500 | 1.45 | LOW
REL-0002 | Blue Workflow v2.1 | 2026-07-04 | 9 | 45 | 1200 | 1 | 1 | 2 | 72 | 5 | 8 | 90 | 4 | 3 | 3 | 3 | 2 | 3 | 4 | 0 | 4 | 5 | 5 | 3 | 20 | 4 | 2 | 3 | 4 | 1 | 4 | 3 | 3 | 3 | 4 | 30 | 75 | 4 | 10 | 4 | 3 | 60 | 1 | 4 | 3 | 2 | 5000 | 2.38 | MEDIUM
REL-0003 | Zendesk Minor v4.3 | 2026-07-02 | 7 | 5 | 80 | 0 | 0 | 1 | 92 | 2 | 1 | 100 | 1 | 0 | 5 | 5 | 0 | 5 | 5 | 0 | 5 | 5 | 2 | 1 | 45 | 5 | 0 | 1 | 5 | 0 | 5 | 5 | 5 | 5 | 5 | 10 | 95 | 5 | 2 | 5 | 5 | 120 | 0 | 5 | 5 | 1 | 200 | 1.01 | LOW
REL-0004 | Oracle HFM Upgrade v12 | 2026-07-07 | 12 | 85 | 3200 | 4 | 2 | 3 | 65 | 8 | 15 | 80 | 7 | 8 | 2 | 2 | 5 | 2 | 3 | 1 | 3 | 3 | 8 | 4 | 10 | 3 | 3 | 5 | 3 | 2 | 3 | 2 | 2 | 2 | 3 | 60 | 60 | 3 | 18 | 3 | 2 | 45 | 2 | 3 | 2 | 3 | 25000 | 3.59 | CRITICAL
REL-0005 | Coupa Integration v3.0 | 2026-07-12 | 17 | 35 | 950 | 1 | 2 | 2 | 78 | 4 | 5 | 95 | 3 | 2 | 4 | 4 | 1 | 4 | 4 | 0 | 4 | 5 | 4 | 3 | 25 | 4 | 1 | 3 | 4 | 1 | 4 | 4 | 4 | 4 | 4 | 25 | 80 | 4 | 8 | 4 | 4 | 75 | 0 | 4 | 4 | 2 | 8000 | 2.11 | MEDIUM
REL-0006 | Salesforce Patch v8.2 | 2026-07-17 | 22 | 18 | 420 | 0 | 1 | 1 | 88 | 3 | 3 | 100 | 2 | 1 | 4 | 4 | 0 | 4 | 5 | 0 | 5 | 5 | 3 | 2 | 35 | 5 | 0 | 2 | 5 | 0 | 5 | 4 | 4 | 4 | 5 | 20 | 85 | 5 | 4 | 5 | 5 | 90 | 0 | 5 | 5 | 1 | 1500 | 1.5 | MEDIUM
REL-0007 | SAP S4 Finance v2.0 | 2026-07-22 | 27 | 150 | 8500 | 5 | 4 | 4 | 58 | 12 | 25 | 75 | 10 | 12 | 2 | 2 | 8 | 2 | 2 | 1 | 2 | 2 | 12 | 5 | 7 | 2 | 4 | 6 | 2 | 3 | 4 | 2 | 2 | 2 | 2 | 90 | 50 | 2 | 22 | 2 | 2 | 30 | 3 | 2 | 2 | 5 | 50000 | 4.24 | SEVERE
REL-0008 | Workday HR Update v5.1 | 2026-07-27 | 32 | 42 | 1100 | 2 | 1 | 2 | 75 | 5 | 6 | 92 | 4 | 3 | 3 | 3 | 1 | 3 | 4 | 0 | 4 | 5 | 5 | 3 | 28 | 4 | 2 | 3 | 4 | 1 | 4 | 3 | 3 | 4 | 4 | 35 | 70 | 4 | 12 | 4 | 3 | 55 | 1 | 4 | 3 | 2 | 12000 | 2.41 | MEDIUM
REL-0009 | Jira Workflow v3.4 | 2026-08-01 | 37 | 8 | 150 | 0 | 0 | 1 | 90 | 2 | 2 | 100 | 2 | 0 | 5 | 5 | 0 | 5 | 5 | 0 | 5 | 5 | 2 | 2 | 40 | 5 | 0 | 2 | 5 | 0 | 5 | 5 | 5 | 5 | 5 | 12 | 92 | 5 | 3 | 5 | 5 | 100 | 0 | 5 | 5 | 1 | 800 | 1.13 | LOW
REL-0010 | Manhattan WMS v6.0 | 2026-07-09 | 14 | 200 | 12000 | 8 | 5 | 4 | 52 | 15 | 35 | 70 | 12 | 18 | 1 | 1 | 12 | 1 | 2 | 1 | 2 | 2 | 15 | 5 | 5 | 1 | 5 | 8 | 1 | 4 | 5 | 1 | 1 | 1 | 2 | 120 | 40 | 2 | 28 | 2 | 1 | 25 | 4 | 1 | 3 | 5 | 100000 | 4.52 | SEVERE
REL-0011 | ServiceNow ITSM v4.2 | 2026-08-06 | 42 | 28 | 720 | 1 | 1 | 1 | 82 | 4 | 4 | 95 | 3 | 2 | 4 | 4 | 1 | 4 | 4 | 0 | 4 | 5 | 4 | 3 | 32 | 4 | 1 | 3 | 4 | 1 | 4 | 4 | 4 | 4 | 4 | 22 | 82 | 4 | 6 | 4 | 4 | 70 | 0 | 4 | 4 | 2 | 6000 | 1.95 | MEDIUM
REL-0012 | Tableau Dashboard v2.8 | 2026-08-11 | 47 | 6 | 120 | 0 | 0 | 1 | 95 | 2 | 1 | 100 | 1 | 0 | 5 | 5 | 0 | 5 | 5 | 0 | 5 | 5 | 2 | 1 | 50 | 5 | 0 | 1 | 5 | 0 | 5 | 5 | 5 | 5 | 5 | 8 | 98 | 5 | 1 | 5 | 5 | 150 | 0 | 5 | 5 | 1 | 150 | 1.01 | LOW
WEIGHTED SCORE CALCULATION EXAMPLE - REL-0001
The Weighted Risk Score combines 44 factors across 10 categories. Each factor is:
1. Converted from its raw value to a standardized score (1 = lowest risk, 5 = highest risk)
2. Multiplied by its assigned weight (all weights sum to 100%)
3. All weighted scores are summed to produce the final risk score
FORMULA: Weighted Score = Σ (Factor Score × Factor Weight)
For REL-0001 (Kyriba UI Tweak v4.5), here is the detailed breakdown:
# | Factor | Raw Value | Score Logic | Score (1-5) | Weight | Contribution
1 | Files Changed | 12 | 1 if <10, 2 if <30, 3 if <60, 4 if <100, else 5 | 2 | 4% | 8%
2 | Code Churn (LOC) | 320 | 1 if <200, 2 if <500, 3 if <1500, 4 if <3000, else 5 | 2 | 3% | 6%
3 | DB Schema Changes | 0 | 1 if 0, 2 if 1, 3 if 2, 4 if <5, else 5 | 1 | 5% | 5%
4 | API Contract Changes | 0 | 1 if 0, 2 if 1, 3 if 2, 4 if 3, else 5 | 1 | 4% | 4%
5 | New Technology Stack | 1 | Direct score (1=Proven, 5=Entirely new) | 1 | 2% | 2%
6 | Test Coverage % | 85 | 1 if >90, 2 if >80, 3 if >70, 4 if >60, else 5 | 2 | 6.8% | 13.6%
7 | Test Execution Days | 3 | 1 if <3, 2 if <5, 3 if <7, 4 if <10, else 5 | 2 | 3% | 6%
8 | Bugs Found (Test) | 2 | 1 if <3, 2 if <6, 3 if <10, 4 if <15, else 5 | 1 | 4% | 4%
9 | Bug Fix Rate % | 100 | 1 if >95, 2 if >85, 3 if >75, 4 if >60, else 5 | 1 | 2% | 2%
10 | UAT Duration Days | 2 | 1 if <3, 2 if <5, 3 if <7, 4 if <10, else 5 | 1 | 3% | 3%
11 | UAT Defects Found | 0 | 1 if <2, 2 if <4, 3 if <7, 4 if <10, else 5 | 1 | 2% | 2%
12 | UAT Sign-off Level | 4 | INVERTED: 6 - value (5=full signoff=1) | 2 | 3% | 6%
13 | Test Env Parity Score | 4 | INVERTED: 6 - value (5=perfect parity=1) | 2 | 2% | 4%
14 | Critical/High Vulns | 0 | 1 if 0, 2 if <3, 3 if <5, 4 if <10, else 5 | 1 | 3% | 3%
15 | Pen Test Sign-off | 4 | INVERTED: 6 - value (5=passed=1) | 2 | 3% | 6%
16 | Compliance Gate | 5 | INVERTED: 6 - value (5=passed all=1) | 1 | 2% | 2%
17 | Data Migration Req | 0 | Boolean: 0=No(1), 1=Yes(3) | 1 | 1.5% | 1.5%
18 | Backup Restore Tested | 5 | INVERTED: 6 - value (5=tested=1) | 1 | 1% | 1%
19 | Migration Script Tested | 5 | INVERTED: 6 - value (5=tested=1) | 1 | 1.5% | 1.5%
20 | Team Size | 2 | 1 if <3, 2 if <6, 3 if <10, 4 if <15, else 5 | 1 | 2% | 2%
21 | Deploy Window Hours | 2 | 1 if <2, 2 if <4, 3 if <6, 4 if <8, else 5 | 2 | 3% | 6%
22 | Change Freeze Proximity | 30 | 1 if >14, 2 if >7, 3 if >3, 4 if >1, else 5 | 1 | 3% | 3%
23 | Key Staff Available | 5 | INVERTED: 6 - value (5=all available=1) | 1 | 3% | 3%
24 | Overlapping Releases | 1 | 1 if 0, 2 if 1, 3 if 2, 4 if 3, else 5 | 2 | 3% | 6%
25 | Dependencies Count | 2 | 1 if <2, 2 if <4, 3 if <6, 4 if <8, else 5 | 2 | 3% | 6%
26 | Dependency Health | 5 | INVERTED: 6 - value (5=all healthy=1) | 1 | 2% | 2%
27 | Vendor Involvement | 0 | 1 if 0, 3 if 1, 5 if 2+ | 1 | 2% | 2%
28 | Feature Flag Cleanup | 5 | INVERTED: 6 - value (5=clean=1) | 1 | 2% | 2%
29 | Rollback Plan Tested | 4 | INVERTED: 6 - value (5=tested=1) | 2 | 2% | 4%
30 | Documentation Complete | 4 | INVERTED: 6 - value (5=complete=1) | 2 | 1.5% | 3%
31 | Monitoring Readiness | 4 | INVERTED: 6 - value (5=ready=1) | 2 | 1.5% | 3%
32 | Runbook Updated | 4 | INVERTED: 6 - value (5=updated=1) | 2 | 1.5% | 3%
33 | Rollback Time RTO (min) | 15 | 1 if <15, 2 if <30, 3 if <60, 4 if <120, else 5 | 1 | 2% | 2%
34 | Deploy Automation % | 90 | 1 if >90, 2 if >75, 3 if >50, 4 if >25, else 5 | 1 | 1.5% | 1.5%
35 | Load Test Completed | 5 | INVERTED: 6 - value (5=passed=1) | 1 | 2% | 2%
36 | Perf Regression % | 5 | 1 if <5, 2 if <10, 3 if <15, 4 if <25, else 5 | 2 | 2% | 4%
37 | Vendor Patch Status | 5 | INVERTED: 6 - value (5=current=1) | 1 | 1% | 1%
38 | Release Cadence Dev | 0 | 1 if <2, 2 if <5, 3 if <10, 4 if <20, else 5 | 1 | 0.8% | 0.8%
39 | MTBF Days | 90 | 1 if >60, 2 if >30, 3 if >14, 4 if >7, else 5 | 1 | 0.8% | 0.8%
40 | Past Failures | 0 | 1 if 0, 2 if 1, 3 if 2, 4 if 3, else 5 | 1 | 1% | 1%
41 | BC Not Tested | 5 | INVERTED: 6 - value (5=tested=1) | 1 | 0.8% | 0.8%
42 | Rollback Not Tested | 4 | INVERTED: 6 - value (5=tested=1) | 2 | 0.8% | 1.6%
43 | Revenue Impact | 1 | Direct score (1=Low, 3=Medium, 5=High) | 1 | 1% | 1%
44 | User Blast Radius | 500 | 1 if <1000, 2 if <5000, 3 if <20000, 4 if <50000, else 5 | 1 | 1% | 1%
TOTAL |  |  |  | 1.36 | 100% | 1.43
REL-0001 FINAL RISK ASSESSMENT
Weighted Risk Score: | 1.43 |  | Risk Level: | LOW
Interpretation: REL-0001 has a LOW risk score, indicating minimal risk factors. It uses proven technology, has good test coverage (85%), zero critical vulnerabilities, and all dependencies are healthy. The small scope (12 files, 320 LOC) and experienced team contribute to the low risk profile.
📖 QUICK REFERENCE: Weighted Risk Score (Collapsible Section for Web)
WEIGHTED RISK SCORE = Σ (Factor Score × Factor Weight) ¦ Range: 1.0-5.0
TOP 3 FACTORS (50% of score): Technical Complexity (15%) + Testing Quality (15%) + Resource Availability (20%)
RISK THRESHOLDS:
• < 1.5: LOW → ✅ Proceed • 1.5-2.4: MEDIUM → ✅ Proceed with monitoring
• 2.5-3.4: HIGH → ⚠️ Address concerns • 3.5-3.9: CRITICAL → 🛑 Mitigation required
• ≥ 4.0: SEVERE → 🛑 Consider delay
⚠️ DATA LIMITATION: Calculated for IMMEDIATE releases only. Dashboard filters do NOT apply.
[▼ View full documentation below for all 10 factor categories and detailed guidance]
📋 FULL DOCUMENTATION: Weighted Technical Risk Scoring
🎯 PURPOSE OF WEIGHTED RISK SCORING
This sheet provides QUANTITATIVE TECHNICAL RISK SCORING using 44 measurable factors.
Unlike the Risk sheet (discrete events), this calculates an OBJECTIVE READINESS SCORE.
The score answers: 'Is this release technically ready?' — independent of event-based risks.
📊 HOW THE SCORE IS CALCULATED
Formula: WEIGHTED RISK SCORE = Σ (Factor Score × Factor Weight)
Each of 10 factor categories has a weight (totaling 100%). Each factor is scored 1-5.
Final score range: 1.0 (excellent) to 5.0 (severe risk).
📋 THE 10 FACTOR CATEGORIES
CATEGORY ¦ WEIGHT ¦ WHAT IT MEASURES
───────────────────────────────────────────────────────────────────
Resource Availability ¦ 20% ¦ Key staff availability, backup coverage
Technical Complexity ¦ 15% ¦ Architecture changes, integration depth
Testing Quality ¦ 15% ¦ Test coverage, defect rates, UAT sign-off
Security & Compliance ¦ 12% ¦ Security scan results, compliance checks
Change Impact ¦ 10% ¦ Scope of changes, users affected
Deployment Risk ¦ 8% ¦ Deployment complexity, rollback readiness
Dependencies ¦ 7% ¦ External dependencies, API changes
Environment Readiness ¦ 5% ¦ Env stability, data quality, config drift
Documentation ¦ 5% ¦ Runbooks, release notes, training
Historical Performance ¦ 3% ¦ Past release success rate
🚦 RISK LEVEL THRESHOLDS
SCORE RANGE ¦ RISK LEVEL ¦ RECOMMENDED ACTION
───────────────────────────────────────────────────────────────────
< 1.5 ¦ LOW ¦ ✅ Proceed — minimal technical risk
1.5 - 2.4 ¦ MEDIUM ¦ ✅ Proceed with standard monitoring
2.5 - 3.4 ¦ HIGH ¦ ⚠️ Address concerns before release
3.5 - 3.9 ¦ CRITICAL ¦ 🛑 Mitigation required; escalate
≥ 4.0 ¦ SEVERE ¦ 🛑 Consider delay; major remediation needed
⚠️ IMPORTANT DATA LIMITATIONS
1. IMMEDIATE RELEASES ONLY: Risk factors can only be calculated for releases
scheduled within the next 2 weeks. Future releases lack the data needed.
2. DASHBOARD FILTERS DO NOT APPLY: The Risk Assessment Data section uses
its own date logic and is NOT affected by Dashboard filter selections.
3. POINT-IN-TIME SNAPSHOT: Scores reflect current state and change as factors
are updated. Historical scores are not preserved automatically.
✅ BEST PRACTICES
1. REVIEW WEEKLY: Update factor scores as release planning progresses
2. FOCUS ON TOP 3: Resource, Complexity, and Testing drive 50% of score
3. USE WITH RISK SHEET: Technical score + Event risks = complete picture
4. DOCUMENT CHANGES: Note why scores changed for audit trail
5. CALIBRATE THRESHOLDS: Adjust thresholds based on your org's risk tolerance
💡 TIP: A HIGH technical score with no event-based risks may still be safe.
A LOW technical score with a CRITICAL event risk should still be delayed.

## Risk
RELEASE RISK REGISTER
Comprehensive risk assessment for releases in the next 45 days (Jun 25 - Aug 9, 2026)
🔍 FILTERS | Time Period: | All Time |  | Risk Level: | All | Status: | All | Category: | All | Showing: | 65 of 65 risks |  | 💡 Filter risks by level, status, category
Risk ID | Release ID | Release Name | Prod Date | Days Out | Risk Category | Risk Description | Likelihood | Impact | Risk Score | Affected Area | Mitigation Strategy | Risk Owner | Status | Notes | Risk Owner ID | RISK SCORING MATRIX
RSK-001 | REL-0001 | Kyriba UI Tweak v4.5 | 2026-06-30 | 1 | Resource | QA Lead (Sam Anderson) on leave during release window | 4 | 3 | 12 | Testing | Assign backup QA resource; expedite testing before leave starts | Release Manager | Monitoring | Leave Calendar: LV-001 | USR-061
RSK-002 | REL-0001 | Kyriba UI Tweak v4.5 | 2026-06-30 | 1 | Schedule | Release falls on quarter-end freeze period | 5 | 2 | 10 | Deployment | Obtain CAB exemption for low-impact UI change | Release Manager | Mitigating | Change Freeze exception requested | USR-061 | Likelihood Scale
RSK-003 | REL-0003 | Zendesk Minor Update v4.3 | 2026-07-02 | 3 | Technical | Minor JavaScript compatibility issue with IE11 users (2% of user base) | 2 | 2 | 4 | User Experience | Add browser detection; display upgrade notice for IE11 users | Tech Lead | Accepted | Low user impact; IE11 EOL communicated | USR-037 | 1 | Rare | < 10% chance
RSK-004 | REL-0003 | Zendesk Minor Update v4.3 | 2026-07-02 | 3 | Vendor | Zendesk maintenance window scheduled same week | 3 | 2 | 6 | Availability | Coordinate with Zendesk support; confirm no conflict | Vendor Manager | Monitoring | Awaiting Zendesk confirmation | USR-073 | 2 | Unlikely | 10-25% chance
RSK-005 | REL-0002 | Blue Workflow Automation v2.1 | 2026-07-04 | 5 | Dependency | Upstream ERP data feed changes not yet deployed | 4 | 4 | 16 | Integration | Expedite ERP change; implement data validation fallback | Integration Lead | Escalated | Dependency on Finance team ERP release | USR-061 | 3 | Possible | 25-50% chance
RSK-006 | REL-0002 | Blue Workflow Automation v2.1 | 2026-07-04 | 5 | Testing | UAT incomplete - 3 of 12 test scenarios pending | 3 | 4 | 12 | Quality | Prioritize remaining scenarios; extend UAT by 1 day if needed | QA Lead | Mitigating | 78% UAT complete | USR-061 | 4 | Likely | 50-75% chance
RSK-007 | REL-0002 | Blue Workflow Automation v2.1 | 2026-07-04 | 5 | Resource | Key developer on conference during hypercare period | 3 | 3 | 9 | Support | Ensure knowledge transfer; establish remote support protocol | Dev Manager | Accepted | Developer available via mobile | USR-061 | 5 | Almost Certain | > 75% chance
RSK-008 | REL-0007 | Mitratech Integration Enhancement v5.2 | 2026-07-04 | 5 | Compliance | Legal review of new data sharing clauses pending | 3 | 5 | 15 | Legal/Regulatory | Escalate to Legal Director; prepare rollback plan | Legal Counsel | Escalated | GDPR implications under review | USR-061
RSK-009 | REL-0007 | Mitratech Integration Enhancement v5.2 | 2026-07-04 | 5 | Technical | API rate limiting may cause timeout during peak hours | 3 | 3 | 9 | Performance | Implement request queuing; schedule deployment for off-peak | Tech Lead | Mitigating | Load testing in progress | USR-037 | Impact Scale
RSK-010 | REL-0012 | Plex Report Fix v2.5 | 2026-07-06 | 7 | Scope | Additional report requested by Plant Manager - scope creep | 4 | 2 | 8 | Scope | Defer new report to next release; document in backlog | Product Owner | Mitigating | Change request logged for v2.6 | USR-061 | 1 | Negligible | Minor inconvenience
RSK-011 | REL-0012 | Plex Report Fix v2.5 | 2026-07-06 | 7 | Environment | Test environment scheduled for maintenance during testing | 2 | 3 | 6 | Schedule | Reschedule env maintenance or use backup test instance | Env Manager | Monitoring | Coordinating with IT Ops | USR-061 | 2 | Minor | Some disruption, workaround available
RSK-012 | REL-0004 | AVEVA Dashboard Upgrade v5.5 | 2026-07-12 | 13 | Drift | UAT Oracle version mismatch (18c vs 19c) - DFT-001 | 5 | 4 | 20 | Environment | Upgrade UAT Oracle or modify queries for compatibility | DBA Lead | In Progress | See Drift sheet DFT-001 | USR-061 | 3 | Moderate | Significant disruption
RSK-013 | REL-0004 | AVEVA Dashboard Upgrade v5.5 | 2026-07-12 | 13 | Drift | Pre-prod API timeout config mismatch - DFT-002 | 3 | 3 | 9 | Configuration | Align Pre-prod timeout settings with Prod | DevOps | Open | See Drift sheet DFT-002 | USR-061 | 4 | Major | Severe business impact
RSK-014 | REL-0004 | AVEVA Dashboard Upgrade v5.5 | 2026-07-12 | 13 | Technical | New charting library has known memory leak in Chrome | 3 | 4 | 12 | Performance | Apply vendor patch; implement cleanup routine | Dev Team | Mitigating | Patch available, testing in progress | USR-061 | 5 | Severe | Critical failure, major loss
RSK-015 | REL-0004 | AVEVA Dashboard Upgrade v5.5 | 2026-07-12 | 13 | Resource | Dev Manager (Alex Rivera) on leave during final testing | 4 | 3 | 12 | Decisions | Delegate approval authority; pre-approve critical decisions | Director | Accepted | Leave Calendar: LV-004 | USR-061
RSK-016 | REL-0004 | AVEVA Dashboard Upgrade v5.5 | 2026-07-12 | 13 | Training | End-user training not yet scheduled | 3 | 2 | 6 | Adoption | Schedule training sessions; prepare quick-start guide | Training Lead | Mitigating | Training dates being finalized | USR-061 | Risk Score = Likelihood × Impact
RSK-017 | REL-0005 | Datadog Security Patch Bundle v3.5 | 2026-07-16 | 17 | Security | Patch addresses critical CVE - delay increases exposure | 2 | 5 | 10 | Security | Prioritize release; implement compensating controls until deployed | Security Lead | Escalated | CVE-2026-1234 - CVSS 8.1 | USR-061 | 2026-01-05 | Low | Monitor
RSK-018 | REL-0005 | Datadog Security Patch Bundle v3.5 | 2026-07-16 | 17 | Dependency | Requires agent update on 50+ monitored servers | 3 | 4 | 12 | Deployment | Phase rollout by server criticality; prepare rollback scripts | IT Ops | Mitigating | Rollout plan under review | USR-061 | 2026-06-11 | Medium | Mitigate
RSK-019 | REL-0005 | Datadog Security Patch Bundle v3.5 | 2026-07-16 | 17 | Testing | Limited time for regression testing across all integrations | 4 | 3 | 12 | Quality | Focus on critical integrations; accept risk on low-priority monitors | QA Lead | Accepted | Risk-based testing approach | USR-061 | 2026-12-19 | High | Escalate
RSK-020 | REL-0010 | Manhattan Major Enhancement v5.2 | 2026-07-18 | 19 | Drift | Pre-prod memory insufficient for batch processing - DFT-004 | 5 | 5 | 25 | Infrastructure | Escalate RAM upgrade request to Infrastructure Director | Infra Manager | Escalated | See Drift sheet DFT-004 - CRITICAL | USR-049 | 20-25 | Critical | Immediate Action
RSK-021 | REL-0010 | Manhattan Major Enhancement v5.2 | 2026-07-18 | 19 | Drift | Feature flags not synced to UAT - DFT-005 | 4 | 4 | 16 | Testing | Sync feature flags before UAT sign-off | DevOps | In Progress | See Drift sheet DFT-005 | USR-061
RSK-022 | REL-0010 | Manhattan Major Enhancement v5.2 | 2026-07-18 | 19 | Drift | Carrier API version mismatch in UAT - DFT-006 | 3 | 3 | 9 | Integration | Update UAT carrier API endpoint configuration | Integration Lead | Open | See Drift sheet DFT-006 | USR-061 | SUMMARY STATISTICS
RSK-023 | REL-0010 | Manhattan Major Enhancement v5.2 | 2026-07-18 | 19 | Business | Peak season approaching - failed release impacts fulfillment | 2 | 5 | 10 | Operations | Ensure robust rollback plan; schedule for low-volume window | Operations Dir | Monitoring | Q3 peak starts Aug 15 | USR-061 | Total Risks | 31
RSK-024 | REL-0010 | Manhattan Major Enhancement v5.2 | 2026-07-18 | 19 | Change Mgmt | Warehouse staff require retraining on new RF gun interface | 3 | 3 | 9 | Adoption | Deploy training app; schedule floor training sessions | Warehouse Mgr | Mitigating | Training materials ready | USR-061 | Critical Risks (20+) | 2
RSK-025 | REL-0010 | Manhattan Major Enhancement v5.2 | 2026-07-18 | 19 | Rollback | Rollback complexity high due to database schema changes | 2 | 5 | 10 | Recovery | Pre-create rollback scripts; test rollback in Pre-prod | DBA Lead | In Progress | Rollback tested successfully | USR-061 | High Risks (12-19) | 11
RSK-026 | REL-0006 | SAP Configuration Change v5.2 | 2026-07-20 | 21 | Resource | HR owner (Jack Wilson) on sick leave | 4 | 3 | 12 | Decisions | Identify backup approver; document approval delegation | HR Director | Mitigating | Leave Calendar: LV-003 | USR-061 | Medium Risks (6-11) | 15
RSK-027 | REL-0006 | SAP Configuration Change v5.2 | 2026-07-20 | 21 | Compliance | Payroll calculation changes require audit trail documentation | 2 | 4 | 8 | Audit | Ensure change log captures all config modifications | Compliance | Monitoring | SOX control requirement | USR-061 | Low Risks (1-5) | 3
RSK-028 | REL-0008 | CrowdStrike Minor Update v3.6 | 2026-07-31 | 32 | Vendor | Update requires CrowdStrike support window coordination | 2 | 2 | 4 | Schedule | Confirm vendor support availability; book slot | Vendor Manager | Monitoring | Standard vendor coordination | USR-073
RSK-029 | REL-0009 | Oracle Report Fix v3.4 | 2026-08-04 | 36 | Technical | Fix may impact 3 downstream financial reports | 3 | 4 | 12 | Integration | Validate downstream reports in UAT; notify Finance team | Finance BA | Mitigating | Impact assessment complete | USR-061 | Drift-Related Risks | 5
RSK-030 | REL-0009 | Oracle Report Fix v3.4 | 2026-08-04 | 36 | Schedule | Month-end close - Finance team availability limited | 3 | 3 | 9 | Resource | Schedule deployment post-close or obtain dedicated support | Finance Dir | Monitoring | Targeting post-close window | USR-061 | Escalated Status | 4
RSK-031 | REL-0011 | HubSpot Minor Update v3.7 | 2026-08-12 | 44 | Data | Marketing campaign data sync timing during deployment | 2 | 2 | 4 | Marketing | Schedule deployment outside campaign send windows | Marketing Ops | Accepted | Low risk - standard precaution | USR-061 | Open Status | 2
📖 QUICK REFERENCE: Understanding Risk Scores (Collapsible Section for Web)
RISK SCORE = Likelihood (1-5) × Impact (1-5) ¦ Range: 1-25
SEVERITY QUICK GUIDE:
• 1-4: LOW (Green) → Proceed normally
• 5-8: MEDIUM (Yellow) → Monitor closely
• 9-12: HIGH (Orange) → Mitigation required before CAB
• 15-25: CRITICAL (Red) → Escalate immediately, consider delay
GO/NO-GO: No CRITICAL unmitigated risks = ✅ Proceed ¦ Any CRITICAL = 🛑 Escalate
[▼ View full documentation below for detailed explanations, tables, and best practices]
📋 FULL DOCUMENTATION: Risk Assessment Guide
🎯 PURPOSE OF THIS SHEET
This sheet tracks QUALITATIVE/EVENT-BASED RISKS — specific risk events identified during release planning.
Unlike technical metrics (in Risk Factors), these are discrete risk items requiring human judgment and mitigation.
Each release can have MULTIPLE risk entries for granular tracking throughout the release lifecycle.
📊 RISK SCORE CALCULATION
Formula: RISK SCORE = LIKELIHOOD × IMPACT
LIKELIHOOD SCALE: IMPACT SCALE:
1 = Rare (< 10% chance) 1 = Negligible (No noticeable effect)
2 = Unlikely (10-30% chance) 2 = Minor (Small inconvenience)
3 = Possible (30-50% chance) 3 = Moderate (Noticeable disruption)
4 = Likely (50-70% chance) 4 = Major (Significant business impact)
5 = Almost Certain (> 70% chance) 5 = Severe (Critical failure, data loss)
🚦 SEVERITY INTERPRETATION TABLE
SCORE RANGE ¦ SEVERITY ¦ COLOR ¦ REQUIRED ACTION
─────────────────────────────────────────────────────────────────────────────
1-4 ¦ LOW ¦ Green ¦ Document and monitor; no escalation needed
5-8 ¦ MEDIUM ¦ Yellow ¦ Track actively; ensure mitigation plan exists
9-12 ¦ HIGH ¦ Orange ¦ Mitigation required before CAB; notify stakeholders
15-25 ¦ CRITICAL ¦ Red ¦ Escalate to leadership; consider delaying release
🎯 DECISION-MAKING FRAMEWORK
FOR CAB MEETINGS:
• Present all HIGH and CRITICAL risks with mitigation status
• LOW/MEDIUM risks can be summarized in aggregate
• Any unmitigated HIGH risk requires explicit CAB acknowledgment
• CRITICAL risks typically require executive sponsor approval
GO/NO-GO CRITERIA:
• ✅ PROCEED: All risks LOW/MEDIUM, or HIGH risks have approved mitigations
• ⚠️ CONDITIONAL: HIGH risks exist but mitigations are in progress
• 🛑 DELAY: Any CRITICAL unmitigated risk, or multiple HIGH without mitigation
📋 KEY COLUMNS EXPLAINED
• Risk ID: Unique identifier for tracking and reference
• Release ID: Links risk to specific release (one release can have many risks)
• Risk Description: Clear statement of what could go wrong
• Likelihood (1-5): Probability of risk occurring
• Impact (1-5): Severity if risk materializes
• Risk Score: Calculated = Likelihood × Impact
• Severity: Derived from Risk Score (LOW/MEDIUM/HIGH/CRITICAL)
• Mitigation Plan: Actions to reduce likelihood or impact
• Mitigation Status: Not Started / In Progress / Completed / Accepted
• Owner: Person responsible for managing this risk
✅ BEST PRACTICES
1. IDENTIFY EARLY: Log risks as soon as discovered, don't wait for CAB
2. BE SPECIFIC: Vague risks like 'might fail' are unhelpful — describe the scenario
3. REASSESS REGULARLY: Likelihood and impact can change — update scores weekly
4. OWN EVERY RISK: Unowned risks don't get mitigated
5. CLOSE THE LOOP: Mark risks as mitigated or accepted after release
6. LEARN FROM HISTORY: Review past release risks when planning new ones
7. ESCALATE EARLY: It's better to raise a false alarm than miss a real issue
⚠️ RELATIONSHIP TO RISK FACTORS SHEET:
This sheet tracks discrete risk EVENTS. Risk Factors sheet calculates a weighted
TECHNICAL SCORE based on release characteristics. Use BOTH for complete assessment.

## Drift
ENVIRONMENT & APPLICATION DRIFT TRACKER
Drift issues discovered during release testing phases
🔍 FILTERS | Application: | All | Environment: | All | Drift Type: | All | Severity: | All | Status: | All | Showing: | 40 of 40 drifts | 💡 Filter drift issues by app, env, type
Drift ID | Release ID | Release Name | Application | Environment | Drift Type: | Drift Category | Detected Date | Severity | Description | Impact on Release | Remediation Action | Status | ETA to Fix
DFT-001 | REL-0004 | AVEVA Dashboard Upgrade v5.5 | AVEVA MES | UAT | Infrastructure | Database Version | 2026-06-27 | High | UAT running Oracle 18c while Prod is on Oracle 19c. New dashboard queries use 19c-specific JSON functions. | Dashboard queries will fail in Prod if not addressed. Blocker for UAT sign-off. | Upgrade UAT Oracle instance to 19c or modify queries for backward compatibility | In Progress | 2026-07-07
DFT-002 | REL-0004 | AVEVA Dashboard Upgrade v5.5 | AVEVA MES | Pre-prod | Configuration | API Timeout Settings | 2026-06-28 | Medium | API timeout set to 60s in Pre-prod vs 30s in Prod. Performance testing results may not reflect Prod behavior. | Performance test results unreliable. May pass in Pre-prod but timeout in Prod. | Update Pre-prod timeout configuration to match Prod (30s) | Open | 2026-07-05
DFT-003 | REL-0004 | AVEVA Dashboard Upgrade v5.5 | AVEVA MES | Test | Data | Test Data Stale | 2026-06-25 | Low | Test environment data last refreshed 45 days ago. Missing recent product SKUs added in last month. | Some dashboard filters may not be fully tested with current product catalog. | Refresh Test environment data from Prod snapshot | Scheduled | 2026-07-03
DFT-004 | REL-0010 | Manhattan Major Enhancement v5.2 | Manhattan Associates WMS | Pre-prod | Infrastructure | Memory Allocation | 2026-06-26 | Critical | Pre-prod has 16GB RAM vs Prod's 32GB. New batch processing module requires 24GB minimum for peak loads. | Batch processing will fail under load in testing. Cannot validate Prod readiness. | Request infrastructure team to increase Pre-prod RAM to 32GB | Escalated | 2026-07-09
DFT-005 | REL-0010 | Manhattan Major Enhancement v5.2 | Manhattan Associates WMS | UAT | Configuration | Feature Flags | 2026-06-27 | High | 3 feature flags enabled in Prod not replicated to UAT: ASYNC_PICKING, WAVE_OPTIMIZATION, RF_GUN_V2. | UAT testing not representative of Prod. Business users testing outdated functionality. | Sync feature flag configuration from Prod to UAT | In Progress | 2026-07-04
DFT-006 | REL-0010 | Manhattan Major Enhancement v5.2 | Manhattan Associates WMS | UAT | Integration | Third-party Endpoint | 2026-06-28 | Medium | UAT pointing to carrier API sandbox (v2.1) while Prod uses production API (v2.3). Response formats differ. | Shipping label generation tests may pass but fail in Prod due to API version mismatch. | Update UAT carrier API endpoint to use v2.3 sandbox mirror | Open | 2026-07-06
DFT-007 | REL-0010 | Manhattan Major Enhancement v5.2 | Manhattan Associates WMS | Test | Security | SSL Certificate | 2026-06-22 | Medium | Test environment SSL certificate expired 5 days ago. Currently bypassed with security exception. | Security scans will fail. Cannot complete security sign-off for release. | Renew SSL certificate for Test environment | In Progress | 2026-07-02
📖 QUICK REFERENCE: Environment Drift (Collapsible Section for Web)
DRIFT = Unintended differences between environments that shouldn't exist
SEVERITY: Config Drift → ⚠️ Unexpected behavior ¦ Version Drift → 🛑 Invalid testing
GO/NO-GO: Resolve HIGH/CRITICAL drift BEFORE deploying to Prod
[▼ Full documentation below]
📋 ENVIRONMENT & APPLICATION DRIFT - COMPREHENSIVE GUIDE
🎯 WHAT IS ENVIRONMENT/APPLICATION DRIFT?
Drift occurs when environments (Dev, Test, UAT, Pre-prod) become inconsistent with Production.
This inconsistency means testing may not accurately reflect how the release will behave in Production.
Common causes: Configuration changes, database version differences, missing patches, stale test data.
WHY DRIFT MATTERS:
• Testing in a drifted environment gives FALSE CONFIDENCE — tests pass but production fails
• Deployment scripts may work in Test but fail in Prod due to infrastructure differences
• Performance testing is unreliable if Pre-prod has different resources than Prod
• Security vulnerabilities may exist in Prod but not in Test environments
📊 DRIFT CATEGORIES EXPLAINED
Category | What It Means | Risk If Ignored
Infrastructure | Hardware, OS, memory, CPU differences | Performance failures, capacity issues
Configuration | App settings, feature flags, timeouts | Unexpected behavior, silent failures
Database Version | Different DB engine versions | Query failures, incompatibility
Data | Stale/incomplete test data | Edge cases untested
Integration | API endpoints, third-party versions | Integration failures at go-live
Security | Missing patches, certificate diffs | Vulnerability exposure
🚦 HOW TO USE THIS DATA FOR RELEASE DECISIONS
BEFORE TESTING BEGINS:
• Filter by your Release ID to see all known drift issues affecting your environments
• CRITICAL/HIGH severity drift MUST be resolved before meaningful testing can proceed
• If drift cannot be fixed, document accepted risk and adjust test strategy
PRE-CAB CHECKLIST:
• All CRITICAL drift issues: Status = 'Resolved' or 'Accepted Risk'
• HIGH drift issues: Remediation in progress with ETA before go-live
• Document any outstanding drift in CAB presentation materials
GO/NO-GO IMPACT:
• CRITICAL drift in UAT/Pre-prod: BLOCKER — cannot sign off on testing validity
• HIGH drift: Conditional proceed only if risk is documented and accepted
• MEDIUM/LOW drift: Acceptable with monitoring plan for production
✅ BEST PRACTICES:
1. DETECT EARLY: Run environment comparison tools weekly, not just before releases
2. FIX ROOT CAUSE: Don't just remediate — understand why drift occurred
3. AUTOMATE: Use infrastructure-as-code to prevent configuration drift
4. REFRESH REGULARLY: Schedule monthly data refreshes for non-prod environments
5. DOCUMENT EXCEPTIONS: If drift is accepted, document justification and monitoring plan
6. POST-RELEASE REVIEW: If production issues occur, check if drift was a contributing factor

## Dependencies
RELEASE DEPENDENCIES TRACKER
🔍 FILTERS | Dependency Type: | All | Status: | All | Impact: | All | Showing: | 73 of 73 dependencies | 💡 Filter dependencies by type, status, impact
Dep ID | Release ID | Release Name | Depends On Release | Depends On Name | Dependency Type | Status | Impact if Blocked | Notes
DEP-001 | REL-0009 | Oracle Report Fix v3.4 | REL-0007 | Mitratech Integration Enhancement v5.2 | Hard | Clear | Release Delay | API contract must be deployed first
DEP-002 | REL-0013 | Dynatrace UI Tweak v3.1 | REL-0012 | Plex Report Fix v2.5 | Soft | Blocked | Partial Functionality | Shared database schema changes
DEP-003 | REL-0017 | HighRadius Report Fix v2.4 | REL-0014 | Oracle Global Rollout v2.2 | Technical | At Risk | Data Integrity Risk | Common security module dependency
DEP-004 | REL-0017 | HighRadius Report Fix v2.4 | REL-0012 | Plex Report Fix v2.5 | Data | Resolved | Integration Failure | Integration endpoint prerequisites
DEP-005 | REL-0021 | Splunk Bug Fix Release v3.7 | REL-0019 | Salesforce Minor Update v2.5 | Integration | Clear | Scope Reduction | Shared configuration dependencies
DEP-006 | REL-0025 | Coupa Dashboard Upgrade v5.8 | REL-0022 | Oracle Dashboard Upgrade v2.5 | Hard | Clear | Release Delay | Upstream data pipeline required
DEP-007 | REL-0025 | Coupa Dashboard Upgrade v5.8 | REL-0020 | Rockwell Quick Enhancement v1.5 | Soft | Blocked | Partial Functionality | Common middleware version needed
DEP-008 | REL-0029 | Datadog Feature Release v2.2 | REL-0027 | Salesforce Hotfix v4.3 | Technical | At Risk | Data Integrity Risk | Shared authentication module
DEP-009 | REL-0033 | Oracle Major Enhancement v5.3 | REL-0030 | Cornerstone Feature Release v1.7 | Data | Resolved | Integration Failure | Database migration dependency
DEP-010 | REL-0033 | Oracle Major Enhancement v5.3 | REL-0028 | SAP Architecture Overhaul v5.5 | Integration | Clear | Scope Reduction | API versioning requirement
DEP-011 | REL-0037 | Dynatrace Platform Upgrade v4.0 | REL-0035 | Salesforce Report Fix v5.8 | Hard | Clear | Release Delay | API contract must be deployed first
DEP-012 | REL-0041 | Anaplan Bug Fix Release v3.3 | REL-0038 | SAP Bug Fix Release v5.5 | Soft | Blocked | Partial Functionality | Shared database schema changes
DEP-013 | REL-0041 | Anaplan Bug Fix Release v3.3 | REL-0036 | Plex UI Tweak v3.6 | Technical | At Risk | Data Integrity Risk | Common security module dependency
DEP-014 | REL-0045 | Splunk Global Rollout v3.0 | REL-0042 | Oracle Security Patch Bundle v5.6 | Data | Resolved | Integration Failure | Integration endpoint prerequisites
DEP-015 | REL-0049 | Anaplan Minor Update v3.3 | REL-0046 | SAP UI Tweak v5.2 | Integration | Clear | Scope Reduction | Shared configuration dependencies
DEP-016 | REL-0049 | Anaplan Minor Update v3.3 | REL-0044 | Siemens Integration Enhancement v2.2 | Hard | Clear | Release Delay | Upstream data pipeline required
DEP-017 | REL-0053 | Splunk Global Rollout v5.8 | REL-0051 | HubSpot Module Update v4.7 | Soft | Blocked | Partial Functionality | Common middleware version needed
DEP-018 | REL-0057 | Coupa Security Patch Bundle v3.3 | REL-0054 | Workday Core Transformation v2.7 | Technical | At Risk | Data Integrity Risk | Shared authentication module
DEP-019 | REL-0057 | Coupa Security Patch Bundle v3.3 | REL-0052 | SAP Configuration Change v1.3 | Data | Resolved | Integration Failure | Database migration dependency
DEP-020 | REL-0061 | Datadog API Enhancement v5.6 | REL-0059 | Salesforce Workflow Automation v5.8 | Integration | Clear | Scope Reduction | API versioning requirement
DEP-021 | REL-0065 | Oracle System Migration v1.9 | REL-0062 | SAP Report Fix v2.8 | Hard | Clear | Release Delay | API contract must be deployed first
DEP-022 | REL-0065 | Oracle System Migration v1.9 | REL-0060 | Plex UI Tweak v4.0 | Soft | Blocked | Partial Functionality | Shared database schema changes
DEP-023 | REL-0069 | BMC UI Tweak v5.1 | REL-0067 | Salesforce Complete Redesign v1.9 | Technical | At Risk | Data Integrity Risk | Common security module dependency
DEP-024 | REL-0073 | Kyriba Security Patch Bundle v3.6 | REL-0070 | Oracle Workflow Automation v3.6 | Data | Resolved | Integration Failure | Integration endpoint prerequisites
DEP-025 | REL-0073 | Kyriba Security Patch Bundle v3.6 | REL-0068 | Rockwell Minor Update v1.1 | Integration | Clear | Scope Reduction | Shared configuration dependencies
DEP-026 | REL-0077 | Jira Core Transformation v1.8 | REL-0076 | SAP Hotfix v4.1 | Hard | Clear | Release Delay | Upstream data pipeline required
📖 QUICK REFERENCE: Release Dependencies (Collapsible Section for Web)
DEPENDENCY TYPES: Hard (blocking) ¦ Soft (preferred) ¦ Technical ¦ Data ¦ Integration
STATUS: Pending → Not ready ¦ In Progress → Working on it ¦ Resolved → Ready ¦ Blocked → Issue
RULE: ALL Hard dependencies must be RESOLVED before deployment
[▼ Full documentation below]
📋 RELEASE DEPENDENCIES - COMPREHENSIVE GUIDE
🎯 UNDERSTANDING RELEASE DEPENDENCIES
Dependencies exist when one release requires another release to be deployed first, or when releases share resources.
Failing to manage dependencies correctly leads to deployment failures, broken integrations, and cascading delays.
WHY DEPENDENCIES MATTER:
• A release deployed without its prerequisite may fail immediately or cause data corruption
• Shared database schema changes can break multiple applications simultaneously
• API contract changes require coordinated deployment across consumer and provider
• Ignoring dependencies is the #1 cause of failed release weekends
📊 DEPENDENCY TYPES EXPLAINED
Type | Definition | Impact if Not Managed
Hard | Must deploy prerequisite first | Complete release failure
Soft | Preferred order but not mandatory | Reduced functionality
Technical | Shared code/library dependency | Runtime errors
Data | Database schema or data dependency | Data integrity issues
Integration | API/service contract dependency | Integration failures
🚦 DEPENDENCY STATUS VALUES
• Clear: Prerequisite release is deployed and verified — safe to proceed
• Blocked: Prerequisite not yet deployed — CANNOT proceed until resolved
• At Risk: Prerequisite scheduled but may slip — monitor closely
• Resolved: Previously blocked, now cleared — document what changed
• N/A: Dependency removed or no longer applicable
🎯 HOW TO USE THIS DATA FOR RELEASE DECISIONS
RELEASE PLANNING PHASE:
• Filter by your Release ID to see all dependencies (both upstream and downstream)
• Identify HARD dependencies — these determine your earliest possible go-live date
• Coordinate with owners of prerequisite releases to align schedules
PRE-CAB CHECKLIST:
• All HARD dependencies: Status = 'Clear' or 'Resolved'
• Any BLOCKED dependencies: Escalate immediately — CAB approval is meaningless if blocked
• AT RISK dependencies: Have contingency plan if prerequisite slips
DEPLOYMENT SEQUENCING:
• Build deployment runbook showing correct sequence based on dependencies
• If deploying multiple releases, verify no circular dependencies exist
• Plan rollback sequence — if Release B depends on A, rolling back A requires rolling back B first
✅ BEST PRACTICES:
1. DECLARE EARLY: Identify dependencies during planning, not during testing
2. CROSS-REFERENCE: Check Drift sheet — environment drift often affects dependent releases together
3. COMMUNICATE: Notify owners of dependent releases when your schedule changes
4. BUFFER TIME: Don't schedule dependent releases back-to-back — allow verification time
5. DOCUMENT CONTRACTS: For API/Integration dependencies, maintain versioned contract documentation
6. POST-DEPLOYMENT: Verify dependent systems after your release before marking 'Clear'

## Approvals
CAB APPROVAL WORKFLOW TRACKER
Approval ID | Release ID | Release Name | Approval Type | Approver ID | Approver Name | Approver Role | Submitted Date | Decision Date | Decision | Comments | CAB Meeting ID
APR-0001 | REL-0001 | Kyriba UI Tweak v4.5 | Tech Review | USR-001 | Alex Rivera | Development Manager | 2026-06-26 | 2026-06-27 | Rejected | All technical requirements met | CAB-1
APR-0002 | REL-0001 | Kyriba UI Tweak v4.5 | Security Review | USR-092 | Kendall Kim | Security Analyst | 2026-06-26 | 2026-06-27 | Pending | Security scan passed, no vulnerabilities | CAB-1
APR-0003 | REL-0001 | Kyriba UI Tweak v4.5 | Business Review | USR-073 | Sam Adams | Operations Manager | 2026-06-27 | 2026-06-28 | Approved with Conditions | Business impact assessment approved | CAB-1
APR-0004 | REL-0002 | Blue Workflow Automation v2.1 | Tech Review | USR-001 | Alex Rivera | Development Manager | 2026-06-30 | 2026-07-01 | Approved | Security scan passed, no vulnerabilities | CAB-1
APR-0005 | REL-0002 | Blue Workflow Automation v2.1 | Security Review | USR-092 | Kendall Kim | Security Analyst | 2026-06-30 | 2026-07-01 | Approved | Business impact assessment approved | CAB-1
APR-0006 | REL-0002 | Blue Workflow Automation v2.1 | Business Review | USR-073 | Sam Adams | Operations Manager | 2026-07-01 | 2026-07-02 | Approved | Approved - ensure rollback plan is tested | CAB-1
APR-0007 | REL-0002 | Blue Workflow Automation v2.1 | CAB Final | USR-061 | Taylor Anderson | Release Manager | 2026-07-02 | 2026-07-02 | Approved | CAB approved for deployment | CAB-1
APR-0008 | REL-0002 | Blue Workflow Automation v2.1 | Change Manager | USR-062 | Jordan Wright | Release Manager | 2026-07-02 | 2026-07-02 | Approved | Change record closed | CAB-1
APR-0009 | REL-0003 | Zendesk Minor Update v4.3 | Tech Review | USR-001 | Alex Rivera | Development Manager | 2026-06-28 | 2026-06-29 | Approved | Business impact assessment approved | CAB-1
APR-0010 | REL-0003 | Zendesk Minor Update v4.3 | Security Review | USR-092 | Kendall Kim | Security Analyst | 2026-06-28 | 2026-06-29 | Approved | Approved - ensure rollback plan is tested | CAB-1
APR-0011 | REL-0003 | Zendesk Minor Update v4.3 | Business Review | USR-073 | Sam Adams | Operations Manager | 2026-06-29 | 2026-06-30 | Approved | Requires additional UAT testing | CAB-1
APR-0012 | REL-0003 | Zendesk Minor Update v4.3 | CAB Final | USR-061 | Taylor Anderson | Release Manager | 2026-06-30 | 2026-06-30 | Approved | CAB approved for deployment | CAB-1
APR-0013 | REL-0003 | Zendesk Minor Update v4.3 | Change Manager | USR-062 | Jordan Wright | Release Manager | 2026-06-30 | 2026-06-30 | Approved | Change record closed | CAB-1
APR-0014 | REL-0004 | AVEVA Dashboard Upgrade v5.5 | Tech Review | USR-001 | Alex Rivera | Development Manager | 2026-07-08 | 2026-07-09 | Approved | Approved - ensure rollback plan is tested | CAB-2
APR-0015 | REL-0004 | AVEVA Dashboard Upgrade v5.5 | Security Review | USR-092 | Kendall Kim | Security Analyst | 2026-07-08 | 2026-07-09 | Approved | Requires additional UAT testing | CAB-2
APR-0016 | REL-0004 | AVEVA Dashboard Upgrade v5.5 | Business Review | USR-073 | Sam Adams | Operations Manager | 2026-07-09 | 2026-07-10 | Approved | Awaiting security clearance | CAB-2
APR-0017 | REL-0004 | AVEVA Dashboard Upgrade v5.5 | CAB Final | USR-061 | Taylor Anderson | Release Manager | 2026-07-10 |  | Pending | Awaiting CAB meeting | CAB-2
APR-0018 | REL-0007 | Mitratech Integration Enhancement v5.2 | Tech Review | USR-001 | Alex Rivera | Development Manager | 2026-06-30 | 2026-07-01 | Approved | Rollback procedure validated | CAB-1
APR-0019 | REL-0007 | Mitratech Integration Enhancement v5.2 | Security Review | USR-092 | Kendall Kim | Security Analyst | 2026-06-30 | 2026-07-01 | Approved | Approved for off-peak deployment | CAB-1
APR-0020 | REL-0007 | Mitratech Integration Enhancement v5.2 | Business Review | USR-073 | Sam Adams | Operations Manager | 2026-07-01 | 2026-07-02 | Approved | Compliance checklist complete | CAB-1
APR-0021 | REL-0007 | Mitratech Integration Enhancement v5.2 | CAB Final | USR-061 | Taylor Anderson | Release Manager | 2026-07-02 | 2026-07-02 | Approved | CAB approved for deployment | CAB-1
APR-0022 | REL-0007 | Mitratech Integration Enhancement v5.2 | Change Manager | USR-062 | Jordan Wright | Release Manager | 2026-07-02 | 2026-07-02 | Approved | Change record closed | CAB-1
APR-0023 | REL-0012 | Plex Report Fix v2.5 | Tech Review | USR-001 | Alex Rivera | Development Manager | 2026-07-02 | 2026-07-03 | Approved | Security scan passed, no vulnerabilities | CAB-2
APR-0024 | REL-0012 | Plex Report Fix v2.5 | Security Review | USR-092 | Kendall Kim | Security Analyst | 2026-07-02 | 2026-07-03 | Approved | Business impact assessment approved | CAB-2
APR-0025 | REL-0012 | Plex Report Fix v2.5 | Business Review | USR-073 | Sam Adams | Operations Manager | 2026-07-03 | 2026-07-04 | Approved | Approved - ensure rollback plan is tested | CAB-2
APR-0026 | REL-0012 | Plex Report Fix v2.5 | CAB Final | USR-061 | Taylor Anderson | Release Manager | 2026-07-04 | 2026-07-04 | Approved | CAB approved for deployment | CAB-2
APR-0027 | REL-0012 | Plex Report Fix v2.5 | Change Manager | USR-062 | Jordan Wright | Release Manager | 2026-07-04 | 2026-07-04 | Approved | Change record closed | CAB-2
📖 QUICK REFERENCE: CAB Approvals (Collapsible Section for Web)
APPROVAL FLOW: Tech Review → Security Review → Business Review → CAB Final
DECISIONS: Approved ✅ ¦ Rejected 🛑 ¦ Conditional ⚠️ (with conditions) ¦ Deferred ⏸️
RULE: ALL approval stages must be APPROVED or CONDITIONAL before go-live
[▼ Full documentation below]
📋 CAB APPROVAL WORKFLOW - COMPREHENSIVE GUIDE
🎯 UNDERSTANDING THE CAB APPROVAL PROCESS
The Change Advisory Board (CAB) is the governance body that reviews and approves releases before deployment.
This sheet tracks every approval decision required for each release through the approval workflow.
WHY CAB APPROVAL MATTERS:
• Ensures releases meet technical, security, and business readiness criteria
• Provides documented audit trail for compliance and post-incident analysis
• Coordinates cross-functional review to catch issues before production
• Protects the organization from unauthorized or premature deployments
📊 APPROVAL TYPES IN THE WORKFLOW
Type | Approver | What They Verify
Tech Review | Dev Manager | Code quality, architecture, test coverage
Security Review | Security Team | Vulnerabilities, compliance, data handling
Business Review | Business Owner | Business impact, timing, readiness
CAB Final | Release Manager | All prerequisites met, plan approved
🚦 APPROVAL DECISION VALUES
• Approved: Release cleared for this review stage — proceed to next approval
• Approved with Conditions: Cleared but with documented requirements before go-live
• Pending: Review in progress — awaiting approver decision
• Rejected: Failed this review — must address issues and resubmit
• Deferred: Decision postponed — typically due to missing information
🎯 HOW TO USE THIS DATA FOR RELEASE DECISIONS
TRACKING YOUR RELEASE:
• Filter by Release ID to see all approval stages and their current status
• A release requires ALL approval types to be 'Approved' before deployment
• 'Approved with Conditions' requires documented verification of conditions before go-live
PREPARING FOR CAB:
• Ensure Tech Review and Security Review are complete BEFORE CAB meeting
• Address any 'Rejected' items and resubmit for re-review
• Prepare responses to any conditions from 'Approved with Conditions' decisions
ESCALATION TRIGGERS:
• Any 'Rejected' decision: Immediate action required — cannot proceed
• Security Review 'Pending' 48+ hours before go-live: Escalate to CISO
• Multiple 'Pending' approvals: Risk of last-minute delays — follow up proactively
✅ BEST PRACTICES:
1. SUBMIT EARLY: Request reviews 2+ weeks before target CAB date
2. COMPLETE DOCUMENTATION: Reviewers reject incomplete submissions — save time by being thorough
3. TRACK CONDITIONS: Maintain checklist of conditions and verify each before go-live
4. AUDIT TRAIL: Comments field provides historical context — document thoroughly
5. NO SHORTCUTS: Never deploy without CAB Final approval — even for 'emergency' releases
6. POST-INCIDENT: If issues occur, approval records help identify process gaps

## Leave Calendar
🔍 FILTERS | Time Period: | All Time | Role/Dept: | All | Leave Type: | All | Risk Impact: | All
Showing: | 30 of 30 leave records |  | 💡 Filter leave by time, role, type, or risk impact
Leave ID | User ID | User Name | Department | Role | Leave Start | Leave End | Leave Type | Days | Affected Release | Risk Impact | Risk Score
LV-001 | USR-013 | Sam Anderson | QA Lead | QA | 2026-06-30 | 2026-07-04 | Annual Leave | 5 | REL-0001, REL-0002 | High - QA Lead unavailable | 4
LV-002 | USR-025 | Emma Roberts | Finance | Finance | 2026-07-02 | 2026-07-06 | Personal Leave | 5 | REL-0003 | Medium - SME unavailable | 3
LV-003 | USR-038 | Jack Wilson | HR | HR | 2026-07-18 | 2026-07-22 | Sick Leave | 5 | REL-0006 | High - Primary owner on leave | 4
LV-004 | USR-001 | Alex Rivera | Development Manager | IT | 2026-07-12 | 2026-07-15 | Annual Leave | 4 | REL-0004, REL-0005 | Critical - Dev Manager unavailable | 5
LV-005 | USR-050 | Oliver Wright | Manufacturing | Manufacturing | 2026-08-04 | 2026-08-11 | Annual Leave | 8 | REL-0009, REL-0010 | Medium - Extended absence | 3
LV-006 | USR-014 | Chris Park | QA Lead | QA | 2026-08-11 | 2026-08-15 | Personal Leave | 5 | REL-0011 | High - Testing lead absent | 4
LV-007 | USR-063 | Ava Brown | Security | Security | 2026-07-31 | 2026-08-02 | Sick Leave | 3 | REL-0008 | Medium - Security reviewer absent | 3
LV-008 | USR-075 | Ethan Clark | Legal | Legal | 2026-09-04 | 2026-09-11 | Annual Leave | 8 | REL-0016, REL-0017 | High - Legal compliance reviewer absent | 4
LV-009 | USR-002 | Jordan Lee | Development Manager | IT | 2026-09-12 | 2026-09-16 | Conference | 5 | REL-0018 | Medium - Manager at conference | 3
LV-010 | USR-088 | Mia Thompson | CRM | CRM | 2026-09-20 | 2026-09-25 | Annual Leave | 6 | REL-0020 | Low - Backup available | 2
LV-011 | USR-015 | Pat Murphy | QA Lead | QA | 2026-10-12 | 2026-10-19 | Annual Leave | 8 | REL-0024, REL-0025 | Critical - No QA coverage | 5
LV-012 | USR-003 | Casey Chen | Development Manager | IT | 2026-10-24 | 2026-10-28 | Personal Leave | 5 | REL-0028 | High - Key resource unavailable | 4
LV-013 | USR-026 | Liam Jackson | Finance | Finance | 2026-11-05 | 2026-11-12 | Annual Leave | 8 | REL-0031, REL-0032 | Medium - Finance SME absent | 3
LV-014 | USR-039 | Sophia Lee | HR | HR | 2026-11-19 | 2026-11-23 | Sick Leave | 5 | REL-0035 | Low - Short-term absence | 2
LV-015 | USR-051 | Noah Martin | Manufacturing | Manufacturing | 2026-12-03 | 2026-12-10 | Annual Leave | 8 | REL-0038, REL-0039 | High - Year-end absence | 4
LV-016 | USR-004 | Morgan Taylor | Development Manager | IT | 2026-12-17 | 2026-12-31 | Annual Leave | 15 | REL-0040 to REL-0044 | Critical - Extended holiday leave | 5
LV-017 | USR-016 | Tracy Adams | QA Lead | QA | 2026-12-24 | 2027-01-03 | Annual Leave | 11 | REL-0043, REL-0044 | Critical - No QA during freeze | 5
LV-018 | USR-064 | Isabella White | Security | Security | 2026-12-19 | 2026-12-26 | Annual Leave | 8 | REL-0041 | High - Security gap | 4
LV-019 | USR-076 | Lucas Harris | Legal | Legal | 2027-01-16 | 2027-01-23 | Conference | 8 | REL-0048, REL-0049 | Medium - Legal at conference | 3
LV-020 | USR-005 | Jamie Patel | Development Manager | IT | 2027-01-31 | 2027-02-04 | Personal Leave | 5 | REL-0052 | Low - Short absence | 2
LV-021 | USR-027 | Charlotte King | Finance | Finance | 2027-02-14 | 2027-02-21 | Annual Leave | 8 | REL-0055, REL-0056 | High - Quarter-end absence | 4
LV-022 | USR-089 | Benjamin Scott | CRM | CRM | 2027-02-27 | 2027-03-03 | Sick Leave | 5 | REL-0058 | Medium - Unexpected sick leave | 3
LV-023 | USR-017 | Jordan Fisher | QA Lead | QA | 2027-03-26 | 2027-04-02 | Annual Leave | 8 | REL-0062, REL-0063 | Critical - Key tester absent | 5
LV-024 | USR-040 | Amelia Garcia | HR | HR | 2027-04-09 | 2027-04-13 | Personal Leave | 5 | REL-0064 | Low - Coverage available | 2
LV-025 | USR-052 | William Moore | Manufacturing | Manufacturing | 2027-04-23 | 2027-05-03 | Annual Leave | 11 | REL-0067, REL-0068 | High - Extended leave | 4
LV-026 | USR-006 | Riley Kim | Development Manager | IT | 2027-05-07 | 2027-05-11 | Conference | 5 | REL-0070 | Medium - Tech conference | 3
LV-027 | USR-065 | Harper Robinson | Security | Security | 2027-05-21 | 2027-05-28 | Annual Leave | 8 | REL-0073, REL-0074 | High - Security lead absent | 4
LV-028 | USR-077 | James Lewis | Legal | Legal | 2027-06-04 | 2027-06-11 | Annual Leave | 8 | REL-0076 | Medium - Legal review delayed | 3
LV-029 | USR-028 | Evelyn Walker | Finance | Finance | 2026-08-22 | 2026-08-26 | Personal Leave | 5 | REL-0013 | Low - Backup SME available | 2
LV-030 | USR-041 | Alexander Hall | HR | HR | 2026-10-03 | 2026-10-07 | Annual Leave | 5 | REL-0022 | Medium - Training delayed | 3
📖 QUICK REFERENCE: Leave & Resource Planning (Collapsible Section for Web)
RISK IMPACT: 1-2 Low ¦ 3 Medium ¦ 4 High ¦ 5 Critical (key person unavailable)
CHECK BEFORE RELEASE: Is Release Owner available? Is backup designated?
RULE: Never deploy when Release Owner AND backup are both unavailable
[▼ Full documentation below]
📋 LEAVE CALENDAR - COMPREHENSIVE GUIDE FOR RELEASE PLANNING
🎯 WHY LEAVE PLANNING MATTERS FOR RELEASES
This sheet tracks planned absences of key personnel and their potential impact on release success.
Resource availability is often overlooked but is a critical factor in release planning.
WHY THIS MATTERS:
• Key personnel absence during testing = delayed sign-offs and blocked releases
• Release owner on leave during deployment = no one to make critical decisions
• SME unavailable during go-live = extended issue resolution time
• Support team gaps = poor post-release incident response
📊 RISK IMPACT SCORING
Score | Impact | Action Required
5 | Critical | Reschedule release or find backup immediately
4 | High | Assign backup, document handover
3 | Medium | Ensure backup is briefed
2 | Low | Standard coverage plan
1 | Minimal | No special action needed
🎯 HOW TO USE THIS DATA FOR RELEASE DECISIONS
DURING RELEASE PLANNING:
• Filter by time period to see all planned absences during your release window
• Check 'Affected Release' column to see which releases have resource conflicts
• High/Critical risk scores (4-5) require mitigation BEFORE scheduling CAB
PRE-CAB CHECKLIST:
• Identify all team members required for testing, deployment, and post-go-live support
• Verify no Critical/High leave conflicts during testing phase
• Ensure release owner OR designated backup is available during deployment window
• Confirm support team coverage for post-release monitoring period
GO/NO-GO CONSIDERATIONS:
• Critical (5): Consider rescheduling — proceeding without key person is high risk
• High (4): Conditional proceed only with documented backup and handover complete
• Medium/Low (2-3): Proceed with standard contingency planning
✅ BEST PRACTICES:
1. CHECK EARLY: Review leave calendar during initial release planning, not the week before
2. CROSS-REFERENCE: Add leave conflicts to Risk sheet as resource risks
3. BACKUP PLANNING: Every critical role needs an identified, briefed backup
4. HANDOVER DOCS: Ensure knowledge transfer documentation exists before absence
5. COMMUNICATION: Notify team of coverage arrangements before key person departs
6. HOLIDAY AWARENESS: Be especially cautious around major holidays and fiscal year-end

## Versions
App ID | Application | Department | Environment | Version | Build Number | Deploy Date | Deployed By | Status | Notes
APP-001 | SAP S/4HANA Finance (FICO) | Finance | Dev | 2026.3.0-beta | Build-45892 | 2026-06-20 | Alex Rivera | Active | Latest features in testing
APP-001 | SAP S/4HANA Finance (FICO) | Finance | Test | 2026.2.5 | Build-45721 | 2026-06-15 | Sam Anderson | Active | QA validation in progress
APP-001 | SAP S/4HANA Finance (FICO) | Finance | UAT | 2026.2.3 | Build-45650 | 2026-06-10 | Rachel Green | Active | Business sign-off pending
APP-001 | SAP S/4HANA Finance (FICO) | Finance | Pre-prod | 2026.2.1 | Build-45580 | 2026-06-05 | Nathan Cole | Active | Ready for production
APP-001 | SAP S/4HANA Finance (FICO) | Finance | Prod | 2026.2.0-GA | Build-45500 | 2026-05-28 | Victoria Sterling | Active | Current production version
APP-001 | SAP S/4HANA Finance (FICO) | Finance | DR | 2026.2.0-GA | Build-45500 | 2026-05-29 | Robert Shield | Active | Mirrors production
APP-002 | Anaplan | Finance | Dev | 5.8.2-alpha | Build-12340 | 2026-06-22 | Jordan Lee | Active | New planning module
APP-002 | Anaplan | Finance | Test | 5.8.1 | Build-12280 | 2026-06-18 | Chris Park | Active | Regression testing
APP-002 | Anaplan | Finance | UAT | 5.7.5 | Build-12150 | 2026-06-12 | Monica Geller | Active | User acceptance
APP-002 | Anaplan | Finance | Pre-prod | 5.7.4 | Build-12100 | 2026-06-08 | Ethan Black | Active | Performance verified
APP-002 | Anaplan | Finance | Prod | 5.7.3-GA | Build-12050 | 2026-06-01 | Elizabeth Crown | Active | Stable release
APP-002 | Anaplan | Finance | DR | 5.7.3-GA | Build-12050 | 2026-06-02 | William Guard | Active | DR sync complete
APP-003 | SAP Transportation Management (TM) | Logistics | Dev | 10.5.0-dev | Build-78901 | 2026-06-21 | Casey Chen | Active | Route optimization update
APP-003 | SAP Transportation Management (TM) | Logistics | Test | 10.4.8 | Build-78800 | 2026-06-16 | Pat Murphy | Active | Integration tests
APP-003 | SAP Transportation Management (TM) | Logistics | UAT | 10.4.6 | Build-78700 | 2026-06-11 | Phoebe Buffay | Active | Carrier testing
APP-003 | SAP Transportation Management (TM) | Logistics | Pre-prod | 10.4.5 | Build-78650 | 2026-06-06 | Lucas White | Active | Load tested
APP-003 | SAP Transportation Management (TM) | Logistics | Prod | 10.4.4-GA | Build-78600 | 2026-05-30 | Catherine Royal | Active | Production stable
APP-003 | SAP Transportation Management (TM) | Logistics | DR | 10.4.4-GA | Build-78600 | 2026-05-31 | James Fortress | Active | Failover tested
APP-004 | Salesforce Sales Cloud | CRM | Dev | Spring'26.3-beta | Build-SF2603 | 2026-06-23 | Morgan Taylor | Active | Lightning update
APP-004 | Salesforce Sales Cloud | CRM | Test | Spring'26.2 | Build-SF2602 | 2026-06-19 | Jesse Garcia | Active | API testing
APP-004 | Salesforce Sales Cloud | CRM | UAT | Spring'26.1 | Build-SF2601 | 2026-06-14 | Emma Watson | Active | Sales team review
APP-004 | Salesforce Sales Cloud | CRM | Pre-prod | Winter'26.5 | Build-SF2605 | 2026-06-09 | Mason Gray | Active | Sandbox refresh done
APP-004 | Salesforce Sales Cloud | CRM | Prod | Winter'26.4-GA | Build-SF2604 | 2026-06-02 | Margaret Noble | Active | Current release
APP-004 | Salesforce Sales Cloud | CRM | DR | Winter'26.4-GA | Build-SF2604 | 2026-06-03 | Michael Bastion | Active | DR active
APP-005 | SAP S/4HANA Manufacturing | Manufacturing | Dev | 2026.Q2.3-dev | Build-MFG890 | 2026-06-24 | Jamie Patel | Active | MES integration
APP-005 | SAP S/4HANA Manufacturing | Manufacturing | Test | 2026.Q2.2 | Build-MFG880 | 2026-06-20 | Robin Chen | Active | Shop floor tests
APP-005 | SAP S/4HANA Manufacturing | Manufacturing | UAT | 2026.Q2.1 | Build-MFG870 | 2026-06-15 | Sophie Turner | Active | Plant validation
APP-005 | SAP S/4HANA Manufacturing | Manufacturing | Pre-prod | 2026.Q1.5 | Build-MFG860 | 2026-06-10 | Logan Stone | Active | Capacity tested
APP-005 | SAP S/4HANA Manufacturing | Manufacturing | Prod | 2026.Q1.4-GA | Build-MFG850 | 2026-06-03 | Diana Prince | Active | Running in 3 plants
APP-005 | SAP S/4HANA Manufacturing | Manufacturing | DR | 2026.Q1.4-GA | Build-MFG850 | 2026-06-04 | David Tower | Active | Geo-redundant
APP-006 | ServiceNow ITSM | IT | Dev | Tokyo-P3-dev | Build-SN5502 | 2026-06-22 | Riley Kim | Active | CMDB enhancements
APP-006 | ServiceNow ITSM | IT | Test | Tokyo-P2 | Build-SN5501 | 2026-06-17 | Dana Wilson | Active | Workflow testing
APP-006 | ServiceNow ITSM | IT | UAT | Tokyo-P1 | Build-SN5500 | 2026-06-12 | Mia Collins | Active | IT team sign-off
APP-006 | ServiceNow ITSM | IT | Pre-prod | San Diego-P5 | Build-SN5405 | 2026-06-07 | Jacob Hill | Active | Performance OK
APP-006 | ServiceNow ITSM | IT | Prod | San Diego-P4-GA | Build-SN5404 | 2026-05-31 | Helena Troy | Active | All modules active
APP-006 | ServiceNow ITSM | IT | DR | San Diego-P4-GA | Build-SN5404 | 2026-06-01 | Richard Wall | Active | HA configured
APP-007 | Workday HCM | HR | Dev | 2026R2-dev | Build-WD2602 | 2026-06-23 | Quinn Johnson | Active | Talent module update
APP-007 | Workday HCM | HR | Test | 2026R1.5 | Build-WD2615 | 2026-06-18 | Kelly Nguyen | Active | Payroll integration
APP-007 | Workday HCM | HR | UAT | 2026R1.4 | Build-WD2614 | 2026-06-13 | Isabella Moore | Active | HR validation
APP-007 | Workday HCM | HR | Pre-prod | 2026R1.3 | Build-WD2613 | 2026-06-08 | Aiden Clark | Active | Data migration done
APP-007 | Workday HCM | HR | Prod | 2026R1.2-GA | Build-WD2612 | 2026-06-01 | Sophia Grace | Active | Global rollout
APP-007 | Workday HCM | HR | DR | 2026R1.2-GA | Build-WD2612 | 2026-06-02 | Thomas Castle | Active | Cross-region sync
APP-008 | DocuSign CLM | Legal | Dev | 23.5.0-beta | Build-DS2350 | 2026-06-21 | Avery Williams | Active | AI clause analysis
APP-008 | DocuSign CLM | Legal | Test | 23.4.3 | Build-DS2343 | 2026-06-16 | Terry Brooks | Active | E-signature tests
APP-008 | DocuSign CLM | Legal | UAT | 23.4.2 | Build-DS2342 | 2026-06-11 | Olivia James | Active | Legal review
APP-008 | DocuSign CLM | Legal | Pre-prod | 23.4.1 | Build-DS2341 | 2026-06-06 | Jackson Moore | Active | Compliance verified
APP-008 | DocuSign CLM | Legal | Prod | 23.4.0-GA | Build-DS2340 | 2026-05-30 | Alexandra Reid | Active | All templates live
APP-008 | DocuSign CLM | Legal | DR | 23.4.0-GA | Build-DS2340 | 2026-05-31 | Charles Vault | Active | Cloud DR active
APP-009 | CrowdStrike Falcon | Security | Dev | 7.2.0-alpha | Build-CS720 | 2026-06-24 | Drew Martinez | Active | New threat models
APP-009 | CrowdStrike Falcon | Security | Test | 7.1.5 | Build-CS715 | 2026-06-19 | Skyler Davis | Active | Detection testing
APP-009 | CrowdStrike Falcon | Security | UAT | 7.1.4 | Build-CS714 | 2026-06-14 | Ava Mitchell | Active | SOC validation
APP-009 | CrowdStrike Falcon | Security | Pre-prod | 7.1.3 | Build-CS713 | 2026-06-09 | Sebastian Hall | Active | Sensor verified
APP-009 | CrowdStrike Falcon | Security | Prod | 7.1.2-GA | Build-CS712 | 2026-06-02 | Christina Vale | Active | All endpoints
APP-009 | CrowdStrike Falcon | Security | DR | 7.1.2-GA | Build-CS712 | 2026-06-03 | Daniel Bunker | Active | 24/7 monitoring
APP-010 | Splunk Enterprise | IT | Dev | 9.3.0-dev | Build-SP930 | 2026-06-22 | Cameron Brown | Active | ML features
APP-010 | Splunk Enterprise | IT | Test | 9.2.5 | Build-SP925 | 2026-06-17 | Jordan Reed | Active | Index testing
APP-010 | Splunk Enterprise | IT | UAT | 9.2.4 | Build-SP924 | 2026-06-12 | Charlotte Price | Active | Dashboard review
APP-010 | Splunk Enterprise | IT | Pre-prod | 9.2.3 | Build-SP923 | 2026-06-07 | Caleb Young | Active | License validated
APP-010 | Splunk Enterprise | IT | Prod | 9.2.2-GA | Build-SP922 | 2026-05-31 | Natasha Roman | Active | Heavy forwarders
APP-010 | Splunk Enterprise | IT | DR | 9.2.2-GA | Build-SP922 | 2026-06-01 | Matthew Haven | Active | Search head cluster
APP-011 | Coupa | Finance | Dev | R33.1-dev | Build-CP3310 | 2026-06-20 | Taylor Singh | Active | Supplier portal update
APP-011 | Coupa | Finance | Test | R33.0 | Build-CP3300 | 2026-06-15 | Alex Foster | Active | Invoice testing
APP-011 | Coupa | Finance | UAT | R32.5 | Build-CP3250 | 2026-06-10 | Amelia Scott | Active | Procurement review
APP-011 | Coupa | Finance | Pre-prod | R32.4 | Build-CP3240 | 2026-06-05 | Owen King | Active | Integration verified
APP-011 | Coupa | Finance | Prod | R32.3-GA | Build-CP3230 | 2026-05-28 | Amanda Cross | Active | P2P live
APP-011 | Coupa | Finance | DR | R32.3-GA | Build-CP3230 | 2026-05-29 | Anthony Secure | Active | Cloud backup
APP-012 | Microsoft Dynamics 365 CRM | CRM | Dev | 10.0.38-dev | Build-D365038 | 2026-06-23 | Blake Thompson | Active | Copilot features
APP-012 | Microsoft Dynamics 365 CRM | CRM | Test | 10.0.37 | Build-D365037 | 2026-06-18 | Morgan Hayes | Active | Plugin testing
APP-012 | Microsoft Dynamics 365 CRM | CRM | UAT | 10.0.36 | Build-D365036 | 2026-06-13 | Harper Lewis | Active | Sales team review
APP-012 | Microsoft Dynamics 365 CRM | CRM | Pre-prod | 10.0.35 | Build-D365035 | 2026-06-08 | Liam Wright | Active | Data sync done
APP-012 | Microsoft Dynamics 365 CRM | CRM | Prod | 10.0.34-GA | Build-D365034 | 2026-06-01 | Rebecca Stone | Active | Multi-region
APP-012 | Microsoft Dynamics 365 CRM | CRM | DR | 10.0.34-GA | Build-D365034 | 2026-06-02 | Mark Backup | Active | Azure failover
APP-013 | Siemens Opcenter | Manufacturing | Dev | 2026.2.0-dev | Build-OPC260 | 2026-06-21 | Alex Rivera | Active | Digital twin update
APP-013 | Siemens Opcenter | Manufacturing | Test | 2026.1.5 | Build-OPC255 | 2026-06-16 | Sam Anderson | Active | MES integration
APP-013 | Siemens Opcenter | Manufacturing | UAT | 2026.1.4 | Build-OPC254 | 2026-06-11 | Rachel Green | Active | Plant floor review
APP-013 | Siemens Opcenter | Manufacturing | Pre-prod | 2026.1.3 | Build-OPC253 | 2026-06-06 | Nathan Cole | Active | Load tested
APP-013 | Siemens Opcenter | Manufacturing | Prod | 2026.1.2-GA | Build-OPC252 | 2026-05-30 | Victoria Sterling | Active | 4 plants live
APP-013 | Siemens Opcenter | Manufacturing | DR | 2026.1.2-GA | Build-OPC252 | 2026-05-31 | Robert Shield | Active | Hot standby
APP-014 | SAP SuccessFactors | HR | Dev | 2H-2026-dev | Build-SF2H26 | 2026-06-24 | Jordan Lee | Active | Performance mgmt
APP-014 | SAP SuccessFactors | HR | Test | 1H-2026.5 | Build-SF1H25 | 2026-06-19 | Chris Park | Active | Goal setting test
APP-014 | SAP SuccessFactors | HR | UAT | 1H-2026.4 | Build-SF1H24 | 2026-06-14 | Monica Geller | Active | Employee review
APP-014 | SAP SuccessFactors | HR | Pre-prod | 1H-2026.3 | Build-SF1H23 | 2026-06-09 | Ethan Black | Active | Integration OK
APP-014 | SAP SuccessFactors | HR | Prod | 1H-2026.2-GA | Build-SF1H22 | 2026-06-02 | Elizabeth Crown | Active | Global HCM
APP-014 | SAP SuccessFactors | HR | DR | 1H-2026.2-GA | Build-SF1H22 | 2026-06-03 | William Guard | Active | Cloud DR
APP-015 | Mitratech TeamConnect | Legal | Dev | 10.5.0-beta | Build-IM1050 | 2026-06-22 | Casey Chen | Active | Matter mgmt update
APP-015 | Mitratech TeamConnect | Legal | Test | 10.4.5 | Build-IM1045 | 2026-06-17 | Pat Murphy | Active | Doc search tests
APP-015 | Mitratech TeamConnect | Legal | UAT | 10.4.4 | Build-IM1044 | 2026-06-12 | Phoebe Buffay | Active | Legal team review
APP-015 | Mitratech TeamConnect | Legal | Pre-prod | 10.4.3 | Build-IM1043 | 2026-06-07 | Lucas White | Active | Security verified
APP-015 | Mitratech TeamConnect | Legal | Prod | 10.4.2-GA | Build-IM1042 | 2026-05-31 | Catherine Royal | Active | Firm-wide
APP-015 | Mitratech TeamConnect | Legal | DR | 10.4.2-GA | Build-IM1042 | 2026-06-01 | James Fortress | Active | Replicated
APP-016 | Okta Identity Cloud | Security | Dev | 2026.05.2-dev | Build-OK0502 | 2026-06-23 | Morgan Taylor | Active | MFA enhancement
APP-016 | Okta Identity Cloud | Security | Test | 2026.05.1 | Build-OK0501 | 2026-06-18 | Jesse Garcia | Active | SSO testing
APP-016 | Okta Identity Cloud | Security | UAT | 2026.04.5 | Build-OK0405 | 2026-06-13 | Emma Watson | Active | Access review
APP-016 | Okta Identity Cloud | Security | Pre-prod | 2026.04.4 | Build-OK0404 | 2026-06-08 | Mason Gray | Active | Policy verified
APP-016 | Okta Identity Cloud | Security | Prod | 2026.04.3-GA | Build-OK0403 | 2026-06-01 | Margaret Noble | Active | Enterprise IAM
APP-016 | Okta Identity Cloud | Security | DR | 2026.04.3-GA | Build-OK0403 | 2026-06-02 | Michael Bastion | Active | Federated DR
APP-017 | Blue Yonder WMS | Logistics | Dev | 2026.3-dev | Build-BY263 | 2026-06-21 | Jamie Patel | Active | AI forecasting
APP-017 | Blue Yonder WMS | Logistics | Test | 2026.2.5 | Build-BY2625 | 2026-06-16 | Robin Chen | Active | Wave planning test
APP-017 | Blue Yonder WMS | Logistics | UAT | 2026.2.4 | Build-BY2624 | 2026-06-11 | Sophie Turner | Active | Warehouse review
APP-017 | Blue Yonder WMS | Logistics | Pre-prod | 2026.2.3 | Build-BY2623 | 2026-06-06 | Logan Stone | Active | Peak load OK
APP-017 | Blue Yonder WMS | Logistics | Prod | 2026.2.2-GA | Build-BY2622 | 2026-05-30 | Diana Prince | Active | 5 DCs live
APP-017 | Blue Yonder WMS | Logistics | DR | 2026.2.2-GA | Build-BY2622 | 2026-05-31 | David Tower | Active | Regional backup
APP-018 | Terraform Enterprise | IT | Dev | 1.8.0-dev | Build-TF180 | 2026-06-24 | Riley Kim | Active | Provider updates
APP-018 | Terraform Enterprise | IT | Test | 1.7.5 | Build-TF175 | 2026-06-19 | Dana Wilson | Active | Module testing
APP-018 | Terraform Enterprise | IT | UAT | 1.7.4 | Build-TF174 | 2026-06-14 | Mia Collins | Active | Infra review
APP-018 | Terraform Enterprise | IT | Pre-prod | 1.7.3 | Build-TF173 | 2026-06-09 | Jacob Hill | Active | State migrated
APP-018 | Terraform Enterprise | IT | Prod | 1.7.2-GA | Build-TF172 | 2026-06-02 | Helena Troy | Active | IaC platform
APP-018 | Terraform Enterprise | IT | DR | 1.7.2-GA | Build-TF172 | 2026-06-03 | Richard Wall | Active | Workspace sync
APP-019 | Oracle Hyperion HFM | Finance | Dev | 11.2.14-dev | Build-HFM214 | 2026-06-20 | Quinn Johnson | Active | Consolidation rules
APP-019 | Oracle Hyperion HFM | Finance | Test | 11.2.13 | Build-HFM213 | 2026-06-15 | Kelly Nguyen | Active | Close cycle test
APP-019 | Oracle Hyperion HFM | Finance | UAT | 11.2.12 | Build-HFM212 | 2026-06-10 | Isabella Moore | Active | Finance review
APP-019 | Oracle Hyperion HFM | Finance | Pre-prod | 11.2.11 | Build-HFM211 | 2026-06-05 | Aiden Clark | Active | Period close OK
APP-019 | Oracle Hyperion HFM | Finance | Prod | 11.2.10-GA | Build-HFM210 | 2026-05-28 | Sophia Grace | Active | Multi-entity
APP-019 | Oracle Hyperion HFM | Finance | DR | 11.2.10-GA | Build-HFM210 | 2026-05-29 | Thomas Castle | Active | Oracle RAC DR
APP-020 | HubSpot CRM | CRM | Dev | 2026.Q2-dev | Build-HS26Q2 | 2026-06-23 | Avery Williams | Active | Marketing hub
APP-020 | HubSpot CRM | CRM | Test | 2026.Q1.5 | Build-HS26Q15 | 2026-06-18 | Terry Brooks | Active | Campaign tests
APP-020 | HubSpot CRM | CRM | UAT | 2026.Q1.4 | Build-HS26Q14 | 2026-06-13 | Olivia James | Active | Marketing review
APP-020 | HubSpot CRM | CRM | Pre-prod | 2026.Q1.3 | Build-HS26Q13 | 2026-06-08 | Jackson Moore | Active | API verified
APP-020 | HubSpot CRM | CRM | Prod | 2026.Q1.2-GA | Build-HS26Q12 | 2026-06-01 | Alexandra Reid | Active | All hubs live
APP-020 | HubSpot CRM | CRM | DR | 2026.Q1.2-GA | Build-HS26Q12 | 2026-06-02 | Charles Vault | Active | Cloud native DR
APP-021 | Jira Service Management | IT | Dev | 5.15.0-dev | Build-JSM515 | 2026-06-22 | Drew Martinez | Active | AI agent update
APP-021 | Jira Service Management | IT | Test | 5.14.5 | Build-JSM5145 | 2026-06-17 | Skyler Davis | Active | Queue testing
APP-021 | Jira Service Management | IT | UAT | 5.14.4 | Build-JSM5144 | 2026-06-12 | Ava Mitchell | Active | Help desk review
APP-021 | Jira Service Management | IT | Pre-prod | 5.14.3 | Build-JSM5143 | 2026-06-07 | Sebastian Hall | Active | SLA config OK
APP-021 | Jira Service Management | IT | Prod | 5.14.2-GA | Build-JSM5142 | 2026-05-31 | Christina Vale | Active | IT service desk
APP-021 | Jira Service Management | IT | DR | 5.14.2-GA | Build-JSM5142 | 2026-06-01 | Daniel Bunker | Active | Atlassian DR
APP-022 | Palo Alto Cortex XDR | Security | Dev | 23.10.1-dev | Build-PA2310 | 2026-06-24 | Cameron Brown | Active | CSPM updates
APP-022 | Palo Alto Cortex XDR | Security | Test | 23.9.5 | Build-PA2395 | 2026-06-19 | Jordan Reed | Active | Policy testing
APP-022 | Palo Alto Cortex XDR | Security | UAT | 23.9.4 | Build-PA2394 | 2026-06-14 | Charlotte Price | Active | SOC review
APP-022 | Palo Alto Cortex XDR | Security | Pre-prod | 23.9.3 | Build-PA2393 | 2026-06-09 | Caleb Young | Active | Scan verified
APP-022 | Palo Alto Cortex XDR | Security | Prod | 23.9.2-GA | Build-PA2392 | 2026-06-02 | Natasha Roman | Active | Multi-cloud
APP-022 | Palo Alto Cortex XDR | Security | DR | 23.9.2-GA | Build-PA2392 | 2026-06-03 | Matthew Haven | Active | SaaS DR
APP-023 | Oracle HCM Cloud | HR | Dev | 26B-dev | Build-OHCM26B | 2026-06-21 | Taylor Singh | Active | Benefits update
APP-023 | Oracle HCM Cloud | HR | Test | 26A.5 | Build-OHCM26A5 | 2026-06-16 | Alex Foster | Active | Payroll cycle
APP-023 | Oracle HCM Cloud | HR | UAT | 26A.4 | Build-OHCM26A4 | 2026-06-11 | Amelia Scott | Active | HR team review
APP-023 | Oracle HCM Cloud | HR | Pre-prod | 26A.3 | Build-OHCM26A3 | 2026-06-06 | Owen King | Active | OCI tested
APP-023 | Oracle HCM Cloud | HR | Prod | 26A.2-GA | Build-OHCM26A2 | 2026-05-30 | Amanda Cross | Active | Global payroll
APP-023 | Oracle HCM Cloud | HR | DR | 26A.2-GA | Build-OHCM26A2 | 2026-05-31 | Anthony Secure | Active | Oracle DR
APP-024 | Rockwell FactoryTalk | Manufacturing | Dev | 14.0.0-dev | Build-FT140 | 2026-06-23 | Blake Thompson | Active | SCADA update
APP-024 | Rockwell FactoryTalk | Manufacturing | Test | 13.5.5 | Build-FT1355 | 2026-06-18 | Morgan Hayes | Active | PLC integration
APP-024 | Rockwell FactoryTalk | Manufacturing | UAT | 13.5.4 | Build-FT1354 | 2026-06-13 | Harper Lewis | Active | Plant floor test
APP-024 | Rockwell FactoryTalk | Manufacturing | Pre-prod | 13.5.3 | Build-FT1353 | 2026-06-08 | Liam Wright | Active | OT network OK
APP-024 | Rockwell FactoryTalk | Manufacturing | Prod | 13.5.2-GA | Build-FT1352 | 2026-06-01 | Rebecca Stone | Active | 6 plants live
APP-024 | Rockwell FactoryTalk | Manufacturing | DR | 13.5.2-GA | Build-FT1352 | 2026-06-02 | Mark Backup | Active | Historian DR
APP-025 | Thomson Reuters Legal Tracker | Legal | Dev | 2026.3-dev | Build-PL263 | 2026-06-22 | Alex Rivera | Active | Knowledge base
APP-025 | Thomson Reuters Legal Tracker | Legal | Test | 2026.2.5 | Build-PL2625 | 2026-06-17 | Sam Anderson | Active | Search testing
APP-025 | Thomson Reuters Legal Tracker | Legal | UAT | 2026.2.4 | Build-PL2624 | 2026-06-12 | Rachel Green | Active | Legal review
APP-025 | Thomson Reuters Legal Tracker | Legal | Pre-prod | 2026.2.3 | Build-PL2623 | 2026-06-07 | Nathan Cole | Active | Content sync
APP-025 | Thomson Reuters Legal Tracker | Legal | Prod | 2026.2.2-GA | Build-PL2622 | 2026-05-31 | Victoria Sterling | Active | All libraries
APP-025 | Thomson Reuters Legal Tracker | Legal | DR | 2026.2.2-GA | Build-PL2622 | 2026-06-01 | Robert Shield | Active | SaaS replicated
APP-026 | Manhattan Associates WMS | Logistics | Dev | 2026.2.0-dev | Build-MA2620 | 2026-06-24 | Jordan Lee | Active | Labor mgmt
APP-026 | Manhattan Associates WMS | Logistics | Test | 2026.1.5 | Build-MA2615 | 2026-06-19 | Chris Park | Active | Pick path test
APP-026 | Manhattan Associates WMS | Logistics | UAT | 2026.1.4 | Build-MA2614 | 2026-06-14 | Monica Geller | Active | DC team review
APP-026 | Manhattan Associates WMS | Logistics | Pre-prod | 2026.1.3 | Build-MA2613 | 2026-06-09 | Ethan Black | Active | Performance OK
APP-026 | Manhattan Associates WMS | Logistics | Prod | 2026.1.2-GA | Build-MA2612 | 2026-06-02 | Elizabeth Crown | Active | 3 warehouses
APP-026 | Manhattan Associates WMS | Logistics | DR | 2026.1.2-GA | Build-MA2612 | 2026-06-03 | William Guard | Active | Replicated
APP-027 | Workday Financials | Finance | Dev | 2026R2.1-dev | Build-WF26R2 | 2026-06-21 | Casey Chen | Active | Revenue module
APP-027 | Workday Financials | Finance | Test | 2026R1.5 | Build-WF26R15 | 2026-06-16 | Pat Murphy | Active | GL testing
APP-027 | Workday Financials | Finance | UAT | 2026R1.4 | Build-WF26R14 | 2026-06-11 | Phoebe Buffay | Active | Controller review
APP-027 | Workday Financials | Finance | Pre-prod | 2026R1.3 | Build-WF26R13 | 2026-06-06 | Lucas White | Active | Close cycle OK
APP-027 | Workday Financials | Finance | Prod | 2026R1.2-GA | Build-WF26R12 | 2026-05-30 | Catherine Royal | Active | Core financials
APP-027 | Workday Financials | Finance | DR | 2026R1.2-GA | Build-WF26R12 | 2026-05-31 | James Fortress | Active | Cloud DR
APP-028 | Splunk SIEM | Security | Dev | 6.3.0-dev | Build-SOAR63 | 2026-06-23 | Morgan Taylor | Active | Playbook update
APP-028 | Splunk SIEM | Security | Test | 6.2.5 | Build-SOAR625 | 2026-06-18 | Jesse Garcia | Active | Automation test
APP-028 | Splunk SIEM | Security | UAT | 6.2.4 | Build-SOAR624 | 2026-06-13 | Emma Watson | Active | SOC validation
APP-028 | Splunk SIEM | Security | Pre-prod | 6.2.3 | Build-SOAR623 | 2026-06-08 | Mason Gray | Active | Integration OK
APP-028 | Splunk SIEM | Security | Prod | 6.2.2-GA | Build-SOAR622 | 2026-06-01 | Margaret Noble | Active | Active response
APP-028 | Splunk SIEM | Security | DR | 6.2.2-GA | Build-SOAR622 | 2026-06-02 | Michael Bastion | Active | SIEM linked
APP-029 | Oracle Manufacturing Cloud | Manufacturing | Dev | 26B.2-dev | Build-OMC26B2 | 2026-06-22 | Jamie Patel | Active | Quality module
APP-029 | Oracle Manufacturing Cloud | Manufacturing | Test | 26B.1 | Build-OMC26B1 | 2026-06-17 | Robin Chen | Active | BOM testing
APP-029 | Oracle Manufacturing Cloud | Manufacturing | UAT | 26A.5 | Build-OMC26A5 | 2026-06-12 | Sophie Turner | Active | Production review
APP-029 | Oracle Manufacturing Cloud | Manufacturing | Pre-prod | 26A.4 | Build-OMC26A4 | 2026-06-07 | Logan Stone | Active | OCI tested
APP-029 | Oracle Manufacturing Cloud | Manufacturing | Prod | 26A.3-GA | Build-OMC26A3 | 2026-05-31 | Diana Prince | Active | 3 facilities
APP-029 | Oracle Manufacturing Cloud | Manufacturing | DR | 26A.3-GA | Build-OMC26A3 | 2026-06-01 | David Tower | Active | Oracle RAC
APP-030 | Datadog | IT | Dev | 7.50.0-dev | Build-DD750 | 2026-06-24 | Riley Kim | Active | APM update
APP-030 | Datadog | IT | Test | 7.49.5 | Build-DD7495 | 2026-06-19 | Dana Wilson | Active | Agent testing
APP-030 | Datadog | IT | UAT | 7.49.4 | Build-DD7494 | 2026-06-14 | Mia Collins | Active | Dashboard review
APP-030 | Datadog | IT | Pre-prod | 7.49.3 | Build-DD7493 | 2026-06-09 | Jacob Hill | Active | Integration OK
APP-030 | Datadog | IT | Prod | 7.49.2-GA | Build-DD7492 | 2026-06-02 | Helena Troy | Active | Observability
APP-030 | Datadog | IT | DR | 7.49.2-GA | Build-DD7492 | 2026-06-03 | Richard Wall | Active | Multi-region
📖 QUICK REFERENCE: Version Tracking (Collapsible Section for Web)
ENV FLOW: Dev → Test → UAT → Pre-prod → Prod → DR (DR must = Prod)
VERSION CHECK: Before deploy, verify Pre-prod = planned release version
ROLLBACK: Document current Prod version as rollback target before deployment
[▼ Full documentation below]
📋 APPLICATION VERSIONS - COMPREHENSIVE GUIDE
🎯 PURPOSE OF VERSION TRACKING
This sheet maintains a complete inventory of application versions across all environments.
Version tracking is essential for understanding what's deployed where and planning promotions.
WHY VERSION TRACKING MATTERS:
• Enables quick identification of version discrepancies between environments
• Supports rollback planning — know exactly what version to revert to
• Provides audit trail of what was deployed, when, and by whom
• Identifies environment drift when versions don't follow expected promotion path
📊 EXPECTED ENVIRONMENT PROMOTION FLOW
Standard promotion path: Dev → Test → UAT → Pre-prod → Prod → DR
• Dev: Latest features, may be unstable (highest version number)
• Test: QA validation in progress (version behind Dev)
• UAT: Business user acceptance testing (version behind Test)
• Pre-prod: Final validation, mirrors Prod config (version = next Prod release)
• Prod: Current production version (stable, verified)
• DR: Disaster Recovery — should ALWAYS mirror Prod exactly
🎯 HOW TO USE THIS DATA FOR RELEASE DECISIONS
PRE-RELEASE PLANNING:
• Find your application and check current versions across all environments
• Verify Test/UAT have the version you're planning to release to Prod
• If Pre-prod version doesn't match planned release version, promotion is needed first
IDENTIFYING PROBLEMS:
• Version in UAT > version in Pre-prod: Promotion step was skipped — testing not valid
• Version in DR ≠ version in Prod: DR environment is out of sync — major risk
• Same version across Dev/Test/UAT/Pre-prod: May indicate stalled deployments
ROLLBACK PREPARATION:
• Before any deployment, document current Prod version as rollback target
• Verify rollback version still exists in deployment pipeline
• Confirm rollback procedure has been tested in Pre-prod
✅ BEST PRACTICES:
1. UPDATE IMMEDIATELY: Record version changes within hours of deployment
2. INCLUDE BUILD NUMBERS: Version alone may be ambiguous
3. VERIFY DR SYNC: After every Prod deploy, confirm DR mirrors within 24hrs
4. TRACK DEPLOYER: Knowing who deployed aids troubleshooting
5. CROSS-REFERENCE DRIFT: Version differences may indicate Drift issues
6. ARCHIVE HISTORY: Keep historical records for compliance and post-incident

## System Mapping
Enterprise System Integration Map
Legend:
Core ERP/Platform | Central hub systems
Bidirectional Integration | Two-way data flow
Data Feed (Upstream) | Sends data to other systems
Data Feed (Downstream) | Receives data from other systems
Shared Services | Cross-department systems
CORE SYSTEMS HUB
System | Department | Type | Integrates With | Data Flow | Key Data Exchanged
SAP S/4HANA (ERP) | Finance / Manufacturing | Core ERP | All Departments | Bidirectional | GL, AP, AR, Inventory, Orders, Cost Centers
Workday HCM | HR | Core HCM | Finance, IT, Security | Bidirectional | Employee Data, Payroll, Org Structure
ServiceNow ITSM | IT | Service Platform | All Departments | Bidirectional | Incidents, Changes, Assets, CMDB
Salesforce CRM | CRM | Core CRM | Finance, Manufacturing, Logistics | Bidirectional | Customers, Opportunities, Orders, Contracts
DEPARTMENT INTEGRATION MATRIX
From \ To | Finance | HR | IT | CRM | Manufacturing | Logistics | Legal | Security
Finance | — | ● | ● | ● | ● | ● | ● | ○
HR | ● | — | ● | ○ | ○ | ○ | ● | ●
IT | ● | ● | — | ● | ● | ● | ● | ●
CRM | ● | ○ | ● | — | ● | ● | ● | ○
Manufacturing | ● | ○ | ● | ● | — | ● | ○ | ○
Logistics | ● | ○ | ● | ● | ● | — | ○ | ○
Legal | ● | ● | ● | ● | ○ | ○ | — | ●
Security | ○ | ● | ● | ○ | ○ | ○ | ● | —
● Primary Integration | Critical data exchange, real-time or daily sync
○ Secondary Integration | Periodic data exchange, reporting or audit
KEY INTEGRATION FLOWS
Flow ID | Source System | Target System | Integration Type | Frequency | Data Elements | Business Purpose
INT-001 | Salesforce CRM | SAP S/4HANA | API / Real-time | Real-time | Sales Orders, Customer Master | Order-to-Cash Process
INT-002 | SAP S/4HANA | Workday HCM | Batch / API | Daily | Cost Centers, GL Accounts | Payroll & Financial Reporting
INT-003 | Workday HCM | Okta Identity | SCIM | Real-time | User Provisioning, Roles | Identity & Access Management
INT-004 | SAP Manufacturing | Blue Yonder WMS | API / Batch | Hourly | Production Orders, BOM | Supply Chain Execution
INT-005 | Blue Yonder WMS | SAP Transportation | API | Real-time | Shipments, Inventory | Logistics Coordination
INT-006 | ServiceNow ITSM | Splunk SIEM | API | Real-time | Incidents, Alerts | Security Operations
INT-007 | CrowdStrike | Microsoft Sentinel | API | Real-time | Threat Intelligence | Security Monitoring
INT-008 | DocuSign CLM | SAP S/4HANA | API | On-demand | Contracts, Vendor Terms | Procurement & Legal
INT-009 | Anaplan | SAP S/4HANA | Batch | Daily | Budgets, Forecasts | Financial Planning
INT-010 | Oracle HCM | ADP Workforce | Batch | Bi-weekly | Payroll Data, Time | Payroll Processing
INT-011 | Salesforce CRM | Zendesk | API | Real-time | Cases, Customer Data | Customer Service
INT-012 | SAP S/4HANA | IBM Cognos | Batch | Daily | Financial Data | Business Intelligence
INT-013 | ServiceNow | CyberArk PAM | API | Real-time | Access Requests | Privileged Access
INT-014 | Workday | Cornerstone LMS | API | Daily | Employee, Training | Learning Management
INT-015 | SAP Concur | SAP S/4HANA | API | Daily | Expenses, T&E | Expense Management
SYSTEM ARCHITECTURE DIAGRAM
╔══════════════════════════════════════════════════════════════════════════════════════════════════════════════╗
║ ENTERPRISE INTEGRATION LAYER ║
║ (API Gateway / ESB / Integration Platform) ║
╚════════════╦═══════════════╦═══════════════╦═══════════════╦═══════════════╦═══════════════╦═════════════════╝
║ ║ ║ ║ ║ ║
▼ ▼ ▼ ▼ ▼ ▼
┌──────────────┐ ┌──────────────┐ ┌──────────────┐ ┌──────────────┐ ┌──────────────┐ ┌──────────────┐
│ FINANCE │ │ HR │ │ IT │ │ CRM │ │ MANUFACTURING│ │ LOGISTICS │
├──────────────┤ ├──────────────┤ ├──────────────┤ ├──────────────┤ ├──────────────┤ ├──────────────┤
│ SAP S/4HANA │ │ Workday HCM │ │ ServiceNow │ │ Salesforce │ │ SAP S/4 Manu │ │ SAP TM │
│ Anaplan │ │ SuccessFactors│ │ Splunk │ │ Dynamics 365 │ │ Siemens MES │ │ Blue Yonder │
│ Hyperion HFM │ │ ADP Workforce│ │ Dynatrace │ │ Zendesk │ │ Rockwell FT │ │ Manhattan │
│ IBM Cognos │ │ Cornerstone │ │ PagerDuty │ │ HubSpot │ │ AVEVA MES │ │ FourKites │
└──────┬───────┘ └──────┬───────┘ └──────┬───────┘ └──────┬───────┘ └──────┬───────┘ └──────┬───────┘
│ │ │ │ │ │
│◄──────────────►│◄──────────────►│◄──────────────►│◄──────────────►│◄──────────────►│
│ │ │ │ │ │
└────────────────┴────────────────┴───────┬────────┴────────────────┴────────────────┘
│
┌──────────────────────────┼──────────────────────────┐
│ │ │
▼ ▼ ▼
┌──────────────┐ ┌──────────────┐ ┌──────────────┐
│ LEGAL │◄─────────►│ SECURITY │◄─────────►│ SHARED SVC │
├──────────────┤ ├──────────────┤ ├──────────────┤
│ DocuSign CLM │ │ CrowdStrike │ │ ServiceNow │
│ Ironclad │ │ Okta Identity│ │ Active Dir │
│ Legal Tracker│ │ CyberArk PAM │ │ Email/Collab │
│ Agiloft CLM │ │ MS Sentinel │ │ SharePoint │
└──────────────┘ └──────────────┘ └──────────────┘
══════════════════════════════════════════════════════════════════════════════════════════════════════════════════
DATA FLOW LEGEND
══════════════════════════════════════════════════════════════════════════════════════════════════════════════════
◄──────────────► = Bidirectional Integration (Real-time or Batch sync)
───────────────► = Unidirectional Data Flow (Source to Target)
║ = Connection to Integration Layer
══════════════════════════════════════════════════════════════════════════════════════════════════════════════════
SHARED ENVIRONMENT & RESOURCE DEPENDENCIES
Environment | Type | Shared By | Capacity | Booking Required | Conflict Risk
FIN-TEST-01 | Test | Finance, Legal, CRM | Limited (3 concurrent) | Yes - 2 weeks advance | HIGH
FIN-TEST-02 | Test | Finance | Standard | Yes - 1 week advance | Medium
FIN-UAT-01 | UAT | Finance, Legal, Manufacturing | Limited (2 concurrent) | Yes - 3 weeks advance | HIGH
IT-TEST-01 | Test | IT, Security, All Depts | Shared Pool | Yes - 1 week advance | HIGH
IT-UAT-01 | UAT | IT, Security | Limited | Yes - 2 weeks advance | HIGH
CRM-TEST-01 | Test | CRM, Sales Ops | Standard | Recommended | Medium
CRM-UAT-01 | UAT | CRM, Marketing | Standard | Yes - 1 week advance | Medium
MAN-TEST-01 | Test | Manufacturing, Logistics | Limited | Yes - 2 weeks advance | HIGH
LOG-TEST-01 | Test | Logistics, Manufacturing | Standard | Recommended | Medium
SEC-TEST-01 | Test | Security, IT | Restricted | Yes - 2 weeks advance | Medium
HR-TEST-01 | Test | HR, Payroll | Standard | Yes - 1 week advance | Low
INTEG-01 | Integration | ALL DEPARTMENTS | Critical Shared | Mandatory - 4 weeks | CRITICAL
CRITICAL INTEGRATION PATHS (Release Impact Analysis)
Path ID | Integration Path | Upstream Systems | Downstream Systems | Release Coordination | Blackout Windows | Notes
PATH-001 | Order-to-Cash | Salesforce → SAP | SAP → Logistics → Finance | Mandatory joint testing | Month-end, Quarter-end | Revenue impacting - CFO approval required
PATH-002 | Procure-to-Pay | SAP → Coupa → Vendors | AP → Treasury → Banking | Finance sign-off required | Month-end close (Days 1-5) | Payment processing critical
PATH-003 | Hire-to-Retire | Workday → Okta → All Apps | Payroll → Finance → Tax | HR + IT + Security coord | Payroll windows | Employee data sensitive
PATH-004 | Record-to-Report | All Source Systems → SAP | SAP → Cognos → Reporting | Finance freeze periods | Close periods | SOX compliance required
PATH-005 | Plan-to-Produce | SAP → MES → WMS | Production → Inventory → Ship | Manufacturing + Logistics | Production schedules | Supply chain disruption risk
PATH-006 | Security Operations | All Systems → SIEM | SIEM → SOC → Incident | Security team approval | Never (24/7 ops) | Cannot have monitoring gaps
PATH-007 | Identity Lifecycle | Workday → Okta → Apps | Access → Audit → Compliance | HR + IT + Security | Audit periods | Access control critical
PATH-008 | Contract Lifecycle | Legal → DocuSign → SAP | Procurement → Vendors | Legal + Procurement | Contract renewals | Legal/financial obligations
📋 RELEASE MANAGER NOTES:
1. Always check Integration Matrix before scheduling cross-department releases
2. Shared environments (especially FIN-TEST-01, IT-TEST-01, INTEG-01) require advance booking
3. Critical Integration Paths require coordinated testing across all connected systems
4. Month-end, Quarter-end, and Year-end are high-risk periods - minimize changes
5. Security systems (PATH-006, PATH-007) require 24/7 availability - schedule carefully
6. SAP S/4HANA is the central hub - any SAP changes impact multiple departments
📖 QUICK REFERENCE: System Integrations (Collapsible Section for Web)
INTEGRATION TYPES: API ¦ File Transfer ¦ Message Queue ¦ Direct DB
BEFORE RELEASE: Filter by your app → Find all connected systems → Notify teams
RULE: Test ALL High criticality integrations before Prod deployment
[▼ Full documentation below]
📋 SYSTEM MAPPING - COMPREHENSIVE GUIDE
🎯 PURPOSE OF SYSTEM MAPPING
This sheet visualizes the integration relationships between enterprise systems.
Understanding system dependencies is critical for assessing release impact and planning testing.
WHY SYSTEM MAPPING MATTERS:
• Changes to one system can cascade to dependent systems unexpectedly
• Integration testing must cover all connected systems, not just the changed application
• Outage impact analysis requires knowing which systems will be affected
• Data flow understanding prevents unintended data corruption across systems
📊 UNDERSTANDING THE DATA COLUMNS
COLUMN ¦ MEANING
─────────────────────────────────────────────────────────────────
Source System ¦ The system initiating data or service calls
Target System ¦ The system receiving data or service calls
Integration Type ¦ API, File Transfer, Message Queue, Direct DB, etc.
Data Flow Direction ¦ One-way (→) or Bidirectional (↔)
Sync Frequency ¦ Real-time, Batch Daily, Hourly, Event-driven
Criticality ¦ High/Medium/Low — impact if integration fails
SLA (ms) ¦ Maximum acceptable response time or latency
Last Verified ¦ Date when integration was last tested or validated
Owner Team ¦ Team responsible for maintaining the integration
🚦 HOW TO USE FOR RELEASE DECISIONS
BEFORE SCHEDULING A RELEASE:
• Filter by Target System = your application — see all systems that DEPEND on you
• Filter by Source System = your application — see all systems you DEPEND on
• Identify all High criticality integrations that require testing
DURING RELEASE PLANNING:
• Real-time integrations need same-day deployment coordination
• Batch integrations may only need testing during batch windows
• Notify Owner Teams of all High/Medium criticality connected systems
IMPACT ASSESSMENT:
• If your release changes an API: check which systems call that API (filter Target)
• If your release changes data format: check downstream file consumers
• Document expected integration behavior changes in release notes
✅ BEST PRACTICES
1. KEEP MAPPINGS CURRENT: Update when integrations are built or retired
2. VERIFY ANNUALLY: Last Verified > 1 year old = stale data, revalidate
3. TEST CRITICAL PATHS: Before major releases, test High criticality integrations
4. COORDINATE DEPLOYMENTS: Real-time integrations need coordinated releases
5. DOCUMENT SLA CHANGES: Latency increases affect downstream systems
6. CROSS-REFERENCE: System Mapping + Dependencies sheet = full picture
7. NOTIFY EARLY: Give connected teams 2+ weeks notice for interface changes
⚠️ WARNING: Undocumented integrations are a major release risk.
If you discover an unlisted integration, ADD IT IMMEDIATELY.

## Monitoring Alerts
Alert ID | Timestamp | Application | Department | Alert Type | Severity | Metric | Threshold | Current Value | Status | Assigned To | Environment
ALT-001 | 2026-06-28 21:36 | SAP S/4HANA Finance | Finance | Memory Threshold Exceeded | Critical | Memory Usage | 85% | 94% | Active | Alex Rivera | Prod
ALT-002 | 2026-06-28 19:12 | Oracle Hyperion HFM | Finance | CPU Utilization High | Warning | CPU Usage | 80% | 82% | Active | Jordan Lee | Prod
ALT-003 | 2026-06-28 16:48 | Salesforce Service Cloud | CRM | Latency Over SLA | Critical | Response Time | 200ms | 450ms | Active | Casey Chen | Prod
ALT-004 | 2026-06-28 14:24 | Blue Yonder WMS | Logistics | Disk Space Low | Warning | Disk Usage | 90% | 88% | Acknowledged | Morgan Taylor | UAT
ALT-005 | 2026-06-28 12:00 | Datadog | IT | Network Connectivity Issue | Critical | Packet Loss | 1% | 5% | Active | Jamie Patel | Prod
ALT-006 | 2026-06-28 09:36 | CrowdStrike Falcon | Security | Security Scan Failed | Critical | Scan Status | Pass | Failed | Active | Riley Kim | Prod
ALT-007 | 2026-06-28 07:12 | Zendesk | CRM | Application Error Rate High | Warning | Error Rate | 1% | 3.2% | Active | Quinn Johnson | Test
ALT-008 | 2026-06-28 04:48 | Manhattan Associates WMS | Logistics | Database Connection Pool Exhausted | Critical | Pool Usage | 80% | 100% | Active | Avery Williams | Prod
ALT-009 | 2026-06-28 02:24 | HubSpot CRM | CRM | API Response Time Degraded | Warning | API Latency | 500ms | 780ms | Acknowledged | Drew Martinez | Prod
ALT-010 | 2026-06-28 | Okta Identity Cloud | Security | SSL Certificate Expiring | Warning | Days to Expiry | 30 | 14 | Active | Cameron Brown | Prod
ALT-011 | 2026-06-27 21:36 | SAP SuccessFactors | HR | Backup Failed | Critical | Backup Status | Success | Failed | Active | Taylor Singh | Prod
ALT-012 | 2026-06-27 19:12 | Oracle HCM Cloud | HR | Replication Lag | Warning | Lag Time | 5min | 12min | Active | Blake Thompson | DR
ALT-013 | 2026-06-27 16:48 | Anaplan | Finance | Message Queue Backlog | Warning | Queue Depth | 1000 | 2500 | Acknowledged | Sam Anderson | Prod
ALT-014 | 2026-06-27 14:24 | Coupa | Finance | Cache Hit Rate Low | Info | Hit Rate | 95% | 87% | Active | Chris Park | Prod
ALT-015 | 2026-06-27 12:00 | Splunk Enterprise | IT | Load Balancer Health Check Failed | Critical | Health Status | Healthy | Unhealthy | Active | Pat Murphy | Prod
ALT-016 | 2026-06-27 09:36 | Microsoft Dynamics 365 CRM | CRM | Authentication Failures Spike | Warning | Failed Logins | 10/hr | 45/hr | Active | Jesse Garcia | Prod
ALT-017 | 2026-06-27 07:12 | Plex Smart Manufacturing | Manufacturing | Memory Threshold Exceeded | Warning | Memory Usage | 85% | 86% | Resolved | Robin Chen | Test
ALT-018 | 2026-06-27 04:48 | AVEVA MES | Manufacturing | CPU Utilization High | Info | CPU Usage | 80% | 75% | Resolved | Dana Wilson | Dev
ALT-019 | 2026-06-27 02:24 | Workday HCM | HR | Latency Over SLA | Warning | Response Time | 200ms | 280ms | Active | Kelly Nguyen | Prod
ALT-020 | 2026-06-27 | DocuSign CLM | Legal | Disk Space Low | Info | Disk Usage | 90% | 85% | Resolved | Terry Brooks | UAT
ALT-021 | 2026-06-28 20:24 | Kyriba | Finance | Memory Threshold Exceeded | Critical | Memory Usage | 85% | 92% | Active | Alex Rivera | Prod
ALT-022 | 2026-06-28 18:00 | Mitratech TeamConnect | Legal | Database Connection Pool Exhausted | Warning | Pool Usage | 80% | 85% | Active | Jordan Lee | Prod
ALT-023 | 2026-06-28 15:36 | Dynatrace | IT | Application Error Rate High | Warning | Error Rate | 1% | 2.1% | Acknowledged | Casey Chen | Prod
ALT-024 | 2026-06-28 13:12 | CyberArk PAM | Security | Authentication Failures Spike | Critical | Failed Logins | 10/hr | 120/hr | Active | Morgan Taylor | Prod
ALT-025 | 2026-06-28 10:48 | Jira Service Management | IT | API Response Time Degraded | Info | API Latency | 500ms | 620ms | Active | Jamie Patel | Test
ALT-026 | 2026-06-28 08:24 | Rockwell FactoryTalk | Manufacturing | Network Connectivity Issue | Warning | Packet Loss | 1% | 2.5% | Active | Riley Kim | Prod
ALT-027 | 2026-06-28 06:00 | ADP Workforce Now | HR | Backup Failed | Warning | Backup Status | Success | Partial | Active | Quinn Johnson | Prod
ALT-028 | 2026-06-28 03:36 | Ironclad | Legal | SSL Certificate Expiring | Info | Days to Expiry | 30 | 22 | Resolved | Avery Williams | Prod
ALT-029 | 2026-06-28 01:12 | HighRadius | Finance | Replication Lag | Warning | Lag Time | 5min | 8min | Active | Drew Martinez | DR
ALT-030 | 2026-06-27 22:48 | Kinaxis RapidResponse | Logistics | Load Balancer Health Check Failed | Warning | Health Status | Healthy | Degraded | Active | Cameron Brown | Prod
ALT-031 | 2026-06-28 21:07 | Oracle Transportation Management | Logistics | CPU Utilization High | Critical | CPU Usage | 80% | 95% | Active | Taylor Singh | Prod
ALT-032 | 2026-06-28 18:43 | Cornerstone OnDemand | HR | Memory Threshold Exceeded | Warning | Memory Usage | 85% | 87% | Active | Blake Thompson | UAT
ALT-033 | 2026-06-28 16:19 | Agiloft CLM | Legal | Latency Over SLA | Info | Response Time | 200ms | 220ms | Resolved | Sam Anderson | Test
ALT-034 | 2026-06-28 13:55 | Palo Alto Cortex XDR | Security | Security Scan Failed | Warning | Scan Status | Pass | Warning | Active | Chris Park | Prod
ALT-035 | 2026-06-28 11:31 | BMC Remedy | IT | Message Queue Backlog | Critical | Queue Depth | 1000 | 5200 | Active | Pat Murphy | Prod
ALT-036 | 2026-06-28 09:07 | Zuora | Finance | Cache Hit Rate Low | Warning | Hit Rate | 95% | 82% | Active | Jesse Garcia | Prod
ALT-037 | 2026-06-28 06:43 | RevPro | Finance | Disk Space Low | Warning | Disk Usage | 90% | 91% | Acknowledged | Robin Chen | Prod
ALT-038 | 2026-06-28 04:19 | Siemens Opcenter | Manufacturing | Database Connection Pool Exhausted | Warning | Pool Usage | 80% | 88% | Active | Dana Wilson | Prod
ALT-039 | 2026-06-28 01:55 | Microsoft Sentinel | Security | Application Error Rate High | Info | Error Rate | 1% | 1.5% | Resolved | Kelly Nguyen | Dev
ALT-040 | 2026-06-27 23:31 | SAP S/4HANA Manufacturing | Manufacturing | Network Connectivity Issue | Warning | Packet Loss | 1% | 1.8% | Active | Terry Brooks | Prod
📖 QUICK REFERENCE: Monitoring Alerts (Collapsible Section for Web)
SEVERITY: Critical 🔴 STOP ¦ Warning 🟡 ASSESS ¦ Info 🟢 OK
PRE-DEPLOY CHECK: Filter by App → Count Critical (must be 0) → Review Warnings
RULE: 0 Critical alerts = ✅ Proceed ¦ Any Critical = 🛑 Do NOT deploy
[▼ Full documentation below]
📋 MONITORING ALERTS - COMPREHENSIVE GUIDE
🎯 PURPOSE OF MONITORING ALERTS
This sheet tracks infrastructure and application health alerts that may impact releases.
Active alerts indicate system instability that should be resolved before deployment.
WHY MONITORING MATTERS FOR RELEASES:
• Deploying to an unstable system increases failure risk significantly
• Pre-existing alerts mask new issues caused by your release
• Critical alerts may indicate the system cannot handle additional load
• Security alerts may require immediate patching, overriding scheduled releases
📊 ALERT SEVERITY LEVELS
SEVERITY ¦ MEANING ¦ RELEASE IMPACT
─────────────────────────────────────────────────────────────────
Critical ¦ Immediate outage or security risk ¦ 🔴 STOP - Do NOT deploy
Warning ¦ Performance degraded or threshold ¦ 🟡 WAIT - Assess before deploy
Info ¦ Informational, no action required ¦ 🟢 OK - Monitor during deploy
GENERAL RULE:
• Zero Critical alerts = safe to proceed
• Any Warning alerts = investigate root cause first
• Info alerts = acknowledge but can proceed
🔔 ALERT TYPES AND THEIR IMPLICATIONS
ALERT TYPE ¦ WHAT IT MEANS FOR YOUR RELEASE
─────────────────────────────────────────────────────────────────
Memory Threshold Exceeded ¦ App may crash under additional load
CPU Utilization High ¦ Deployment may fail or cause timeouts
Latency Over SLA ¦ User experience already degraded
Disk Space Low ¦ Deployment may fail, logs may be lost
Network Connectivity Issue ¦ May lose connection during deployment
Security Scan Failed ¦ Security team must approve any release
Application Error Rate High ¦ Existing bugs need fixing first
Database Connection Exhausted ¦ DB cannot handle more connections
API Response Time Degraded ¦ Integrations may fail during deployment
SSL Certificate Expiring ¦ May cause security warnings/failures
Backup Failed ¦ No rollback safety net available
Cache Hit Rate Low ¦ Performance will be poor post-deploy
🚦 PRE-DEPLOYMENT CHECKLIST
BEFORE DEPLOYING, CHECK:
1. Filter by Application = your target application
2. Filter by Status = Active (ignore Resolved/Acknowledged)
3. Count Critical alerts: must be ZERO to proceed
4. Review Warning alerts: understand root cause
5. Check Last Check timestamp: alerts older than 24hrs may be stale
GO/NO-GO DECISION:
• 0 Critical, 0 Warning → ✅ PROCEED
• 0 Critical, 1+ Warning → ⚠️ PROCEED WITH CAUTION (document in release notes)
• 1+ Critical → 🛑 DO NOT DEPLOY until resolved
✅ BEST PRACTICES
1. CHECK MORNING OF RELEASE: Alert status changes — verify day-of
2. MONITOR POST-DEPLOY: Watch for new alerts for 30 minutes after release
3. DOCUMENT BASELINE: Record pre-release alert count for comparison
4. ESCALATE CRITICAL: Never ignore Critical alerts — escalate immediately
5. OWN YOUR ALERTS: Assign alerts to team members for accountability
6. SET THRESHOLDS: Work with Ops to set appropriate thresholds per app
7. CLEAR STALE ALERTS: Resolve or dismiss alerts that are no longer valid
⚠️ IMPORTANT: This data refreshes from monitoring systems.
Check Dashboard for real-time summary of alert counts by severity.

## Incidents
Incident ID | Timestamp | Application | Department | Severity | Title | Status | Impact | Assigned To | Related Release | Environment
INC-001 | 2026-06-28 22:48 | SAP S/4HANA Finance | Finance | P1 | Complete system outage - users cannot access | Active | Down | Alex Rivera | REL-0015 | Prod
INC-002 | 2026-06-28 20:24 | Manhattan Associates WMS | Logistics | P1 | Order processing frozen - critical warehouse operations halted | Investigating | Down | Jordan Lee | REL-0002 | Prod
INC-003 | 2026-06-28 18:00 | Datadog | IT | P1 | Monitoring blackout - no metrics collection | Active | Down | Casey Chen |  | Prod
INC-004 | 2026-06-28 15:36 | Salesforce Service Cloud | CRM | P2 | Severe performance degradation - 5+ second response times | Active | Degraded | Morgan Taylor | REL-0012 | Prod
INC-005 | 2026-06-28 13:12 | CrowdStrike Falcon | Security | P2 | Agent deployment failures affecting 30% of endpoints | Investigating | Degraded | Jamie Patel |  | Prod
INC-006 | 2026-06-28 10:48 | Okta Identity Cloud | Security | P2 | SSO intermittent failures - some users affected | Active | Partial | Riley Kim | REL-0018 | Prod
INC-007 | 2026-06-28 08:24 | Blue Yonder WMS | Logistics | P2 | Inventory sync delays - 15 min lag | Acknowledged | Degraded | Quinn Johnson |  | UAT
INC-008 | 2026-06-28 06:00 | Splunk Enterprise | IT | P3 | Search performance slow during peak hours | Active | Partial | Avery Williams |  | Prod
INC-009 | 2026-06-28 03:36 | Zendesk | CRM | P3 | Ticket attachment uploads failing intermittently | Investigating | Partial | Drew Martinez | REL-0003 | Prod
INC-010 | 2026-06-28 01:12 | AVEVA MES | Manufacturing | P3 | Dashboard refresh delays | Resolved | Partial | Cameron Brown | REL-0004 | UAT
INC-011 | 2026-06-27 22:48 | Kyriba | Finance | P2 | Payment processing delays - batch jobs queued | Active | Degraded | Taylor Singh | REL-0001 | Prod
INC-012 | 2026-06-27 20:24 | Oracle Hyperion HFM | Finance | P3 | Report generation timeouts | Acknowledged | Partial | Blake Thompson |  | Prod
INC-013 | 2026-06-27 18:00 | Plex Smart Manufacturing | Manufacturing | P1 | Production line integration failure | Investigating | Down | Sam Anderson | REL-0025 | Prod
INC-014 | 2026-06-27 15:36 | CyberArk PAM | Security | P2 | Password rotation failures - manual override needed | Active | Degraded | Chris Park |  | Prod
INC-015 | 2026-06-27 13:12 | BMC Remedy | IT | P3 | Email notifications delayed | Resolved | Partial | Pat Murphy |  | Prod
INC-016 | 2026-06-27 | Workday HCM | HR | P2 | Payroll processing errors - validation failures | Resolved | Degraded | Jesse Garcia | REL-0022 | Prod
INC-017 | 2026-06-26 12:00 | SAP SuccessFactors | HR | P3 | Time-off requests not syncing | Resolved | Partial | Robin Chen |  | Prod
INC-018 | 2026-06-26 | HubSpot CRM | CRM | P3 | Marketing email scheduling issues | Resolved | Partial | Dana Wilson |  | Prod
📖 QUICK REFERENCE: Incident Status (Collapsible Section for Web)
SEVERITY: P1 🔴 ALL FROZEN ¦ P2 🟡 Related halted ¦ P3 🟢 Proceed cautiously
STATUS: Active/Investigating = Check before deploy ¦ Mitigated/Resolved = OK
RULE: ANY P1 Active = 🛑 ALL deployments frozen company-wide
[▼ Full documentation below]
📋 INCIDENTS - COMPREHENSIVE GUIDE
🎯 PURPOSE OF INCIDENT TRACKING
This sheet tracks active and recent incidents that may affect release planning.
Active incidents represent system instability requiring immediate attention.
WHY INCIDENTS MATTER FOR RELEASES:
• Active P1/P2 incidents = ALL releases should be paused
• Recent incidents may indicate underlying instability
• Deploying during an incident complicates root cause analysis
• Post-incident releases need extra verification steps
📊 INCIDENT SEVERITY LEVELS
SEVERITY ¦ DEFINITION ¦ RELEASE IMPACT
─────────────────────────────────────────────────────────────────
P1 ¦ Critical outage, business stopped ¦ 🔴 ALL RELEASES FROZEN
P2 ¦ Major degradation, significant impact ¦ 🟡 HALT related releases
P3 ¦ Minor issue, workaround available ¦ 🟢 Proceed with caution
STATUS DEFINITIONS:
• Active: Incident ongoing, teams working to resolve
• Investigating: Root cause analysis in progress
• Mitigated: Temporary fix in place, monitoring
• Resolved: Incident closed, post-mortem pending
🚦 RELEASE DECISION GUIDE DURING INCIDENTS
BEFORE DEPLOYING, CHECK:
1. Filter by Status = Active or Investigating
2. Check Severity: Any P1 = global release freeze
3. Check Application: Is your app affected or related?
4. Review Related Release column: Was the incident caused by a release?
GO/NO-GO MATRIX:
• P1 Active anywhere → 🛑 ALL DEPLOYMENTS FROZEN
• P2 Active on your app → 🛑 DO NOT DEPLOY to that app
• P2 Active on unrelated app → ⚠️ PROCEED CAUTIOUSLY
• P3 only → ✅ PROCEED (document in release notes)
• All Resolved → ✅ PROCEED
✅ BEST PRACTICES
1. CHECK BEFORE EVERY RELEASE: Incident status can change in minutes
2. WAIT 24 HOURS POST-P1: Allow time for stability verification
3. COORDINATE WITH INCIDENT MANAGER: Get explicit approval during incidents
4. LINK RELEASES TO INCIDENTS: If a release caused an incident, document it
5. POST-INCIDENT REVIEW: Check if your release needs changes based on findings
6. COMMUNICATE PROACTIVELY: If your release might worsen an incident, speak up
7. UPDATE STATUS: Mark incidents Resolved when confirmed fixed
⚠️ CRITICAL RULE:
Never deploy during a P1 incident, even if your application is unrelated.
P1 incidents often cascade to other systems unexpectedly.

## Application Status
Application | Department | Environment | Status | Last Check | Uptime % | Notes
SAP S/4HANA Finance | Finance | Prod | Down | 2026-06-28 23:46 | 98.5% | Complete outage - INC-001 open
Manhattan Associates WMS | Logistics | Prod | Down | 2026-06-28 23:46 | 99.1% | Order processing frozen - INC-002
Datadog | IT | Prod | Down | 2026-06-28 23:46 | 99.8% | Monitoring blackout - INC-003
Plex Smart Manufacturing | Manufacturing | Prod | Down | 2026-06-28 23:46 | 97.2% | Production line failure - INC-013
Salesforce Service Cloud | CRM | Prod | Degraded | 2026-06-28 23:46 | 99.2% | Performance issues - INC-004
CrowdStrike Falcon | Security | Prod | Degraded | 2026-06-28 23:46 | 99.5% | Agent deployment issues - INC-005
Okta Identity Cloud | Security | Prod | Degraded | 2026-06-28 23:46 | 99.9% | SSO intermittent - INC-006
Kyriba | Finance | Prod | Degraded | 2026-06-28 23:46 | 99.3% | Payment delays - INC-011
CyberArk PAM | Security | Prod | Degraded | 2026-06-28 23:46 | 99.4% | Password rotation issues - INC-014
Oracle Hyperion HFM | Finance | Prod | Healthy | 2026-06-28 23:46 | 99.7%
Blue Yonder WMS | Logistics | Prod | Healthy | 2026-06-28 23:46 | 99.8%
Workday HCM | HR | Prod | Healthy | 2026-06-28 23:46 | 99.6%
SAP SuccessFactors | HR | Prod | Healthy | 2026-06-28 23:46 | 99.4%
Zendesk | CRM | Prod | Healthy | 2026-06-28 23:46 | 99.5%
HubSpot CRM | CRM | Prod | Healthy | 2026-06-28 23:46 | 99.7%
Splunk Enterprise | IT | Prod | Healthy | 2026-06-28 23:46 | 99.9%
AVEVA MES | Manufacturing | Prod | Healthy | 2026-06-28 23:46 | 99.3%
Anaplan | Finance | Prod | Healthy | 2026-06-28 23:46 | 99.8%
Coupa | Finance | Prod | Healthy | 2026-06-28 23:46 | 99.6%
BMC Remedy | IT | Prod | Healthy | 2026-06-28 23:46 | 99.2%
Blue Yonder WMS | Logistics | UAT | Down | 2026-06-28 23:31 | 95.5% | Refresh in progress
AVEVA MES | Manufacturing | UAT | Down | 2026-06-28 23:31 | 94.8% | Database migration
Zendesk | CRM | UAT | Degraded | 2026-06-28 23:31 | 97.2% | Performance testing impact
SAP S/4HANA Finance | Finance | UAT | Healthy | 2026-06-28 23:31 | 98.9%
Salesforce Service Cloud | CRM | UAT | Healthy | 2026-06-28 23:31 | 99.1%
Workday HCM | HR | UAT | Healthy | 2026-06-28 23:31 | 98.7%
Oracle Hyperion HFM | Finance | UAT | Healthy | 2026-06-28 23:31 | 99%
Kyriba | Finance | Test | Down | 2026-06-28 23:31 | 92.1% | Environment rebuild
Manhattan Associates WMS | Logistics | Test | Down | 2026-06-28 23:31 | 91.5% | Data refresh
Oracle HCM Cloud | HR | Test | Degraded | 2026-06-28 23:31 | 96.3% | Integration testing
SAP S/4HANA Finance | Finance | Test | Healthy | 2026-06-28 23:31 | 97.5%
Workday HCM | HR | Test | Healthy | 2026-06-28 23:31 | 98.2%
Splunk Enterprise | IT | Dev | Down | 2026-06-28 23:31 | 88.5% | Configuration changes
Datadog | IT | Dev | Degraded | 2026-06-28 23:31 | 93.2% | Plugin updates
SAP S/4HANA Finance | Finance | Dev | Healthy | 2026-06-28 23:31 | 95.1%
Zendesk | CRM | Dev | Healthy | 2026-06-28 23:31 | 94.8%
📖 QUICK REFERENCE: Application Health (Collapsible Section for Web)
STATUS: Healthy ✅ ¦ Degraded ⚠️ CAUTION ¦ Down 🛑 NO DEPLOY
UPTIME: < 95% = Instability warning ¦ Check Last Check timestamp for freshness
RULE: Target environment must be HEALTHY before deployment
[▼ Full documentation below]
📋 APPLICATION STATUS - COMPREHENSIVE GUIDE
🎯 PURPOSE OF APPLICATION STATUS
This sheet provides real-time health status of all applications across environments.
Use this to verify system readiness before deploying or to assess current stability.
WHY APPLICATION STATUS MATTERS:
• Deploying to a degraded application may worsen the situation
• Lower environment issues (Test/UAT) may block testing before Prod release
• DR environment status affects disaster recovery readiness
• Uptime % indicates historical stability and reliability
📊 STATUS DEFINITIONS
STATUS ¦ MEANING ¦ CAN YOU DEPLOY?
─────────────────────────────────────────────────────────────────
Healthy ¦ All functions operational ¦ ✅ YES
Degraded ¦ Partial functionality, performance ¦ ⚠️ CAUTION NEEDED
Down ¦ System unavailable ¦ 🛑 NO - WAIT FOR RECOVERY
ENVIRONMENT PRIORITY:
• Prod status: Critical — must be Healthy for go-live
• UAT status: Important — must be Healthy for user acceptance
• Test status: Helpful — affects QA testing pace
• Dev status: Informational — developers manage internally
• DR status: Critical — must mirror Prod for disaster readiness
🚦 PRE-DEPLOYMENT CHECKLIST
BEFORE DEPLOYING TO ANY ENVIRONMENT:
1. Filter by Application = your target application
2. Check ALL environments your release will touch
3. Verify target environment is Healthy, not Degraded or Down
4. Check Uptime %: Below 95% indicates instability — proceed cautiously
5. Review Last Check timestamp: Data older than 1 hour may be stale
GO/NO-GO BY ENVIRONMENT:
• Prod Healthy, UAT Healthy → ✅ FULL RELEASE APPROVED
• Prod Healthy, UAT Degraded → ⚠️ PROD ONLY (skip UAT testing)
• Prod Degraded → 🛑 WAIT until Prod is Healthy
• Prod Down → 🛑 DO NOT DEPLOY — focus on recovery
✅ BEST PRACTICES
1. CHECK IMMEDIATELY BEFORE RELEASE: Status can change in minutes
2. VERIFY DR STATUS: Ensure DR matches Prod before critical releases
3. MONITOR POST-DEPLOY: Check status again 30 minutes after release
4. TRACK UPTIME TRENDS: Decreasing uptime % signals recurring issues
5. ESCALATE DOWN STATUS: Notify support teams immediately
6. DOCUMENT DEGRADED DEPLOYMENTS: Note any compromises in release log
7. COORDINATE WITH OPS: They may have visibility you don't
⚠️ IMPORTANT:
Application Status is a point-in-time snapshot.
Always verify immediately before deployment, not hours in advance.

## Planned Maintenance
Maintenance ID | Scheduled Date | Start Time | End Time | Type | Application(s) | Environment(s) | Department | Impact | Requestor | Approval Status | Notes
MNT-001 | 2026-06-29 | 18:00 | 22:00 | Scheduled Outage | SAP S/4HANA Finance | Prod | Finance | Full Outage | Alex Rivera | Approved | Quarterly maintenance window
MNT-002 | 2026-06-29 | 20:00 | 23:00 | DB Refresh | Blue Yonder WMS | UAT | Logistics | Full Outage | Jordan Lee | Approved | UAT refresh from Prod
MNT-003 | 2026-06-29 | 19:00 | 21:00 | Patch Window | Datadog | Prod | IT | Partial | Casey Chen | Approved | Security patches
MNT-004 | 2026-06-30 | 2:00 | 6:00 | Vendor Maintenance | Salesforce Service Cloud | Prod | CRM | Full Outage | Morgan Taylor | Approved | Salesforce scheduled maintenance
MNT-005 | 2026-06-30 | 22:00 | 2:00 | DB Refresh | AVEVA MES | UAT | Manufacturing | Full Outage | Jamie Patel | Approved | Monthly UAT refresh
MNT-006 | 2026-07-01 | 3:00 | 5:00 | Infrastructure | Oracle Hyperion HFM | All | Finance | Read-Only | Riley Kim | Approved | Storage migration
MNT-007 | 2026-07-01 | 18:00 | 20:00 | Scheduled Outage | Kyriba | Test | Finance | Full Outage | Quinn Johnson | Pending | Test environment rebuild
MNT-008 | 2026-07-02 | 0:00 | 4:00 | Vendor Maintenance | Workday HCM | Prod | HR | Read-Only | Avery Williams | Approved | Workday scheduled maintenance
MNT-009 | 2026-07-02 | 20:00 | 22:00 | DB Refresh | Manhattan Associates WMS | Test | Logistics | Full Outage | Drew Martinez | Approved | Weekly test refresh
MNT-010 | 2026-07-03 | 2:00 | 6:00 | Scheduled Outage | CrowdStrike Falcon | Prod | Security | Partial | Cameron Brown | Approved | Agent upgrade deployment
MNT-011 | 2026-07-04 | 1:00 | 3:00 | Infrastructure | Splunk Enterprise | Prod | IT | Partial | Taylor Singh | Pending | Index optimization
MNT-012 | 2026-07-04 | 22:00 | 2:00 | Vendor Maintenance | Okta Identity Cloud | Prod | Security | Read-Only | Blake Thompson | Approved | Okta scheduled maintenance
MNT-013 | 2026-07-05 | 18:00 | 22:00 | DB Refresh | Zendesk | UAT | CRM | Full Outage | Sam Anderson | Approved | Bi-weekly UAT refresh
MNT-014 | 2026-07-06 | 2:00 | 8:00 | Scheduled Outage | SAP SuccessFactors | Prod | HR | Full Outage | Chris Park | Approved | Major version upgrade
MNT-015 | 2026-07-07 | 0:00 | 4:00 | Vendor Maintenance | HubSpot CRM | Prod | CRM | Partial | Pat Murphy | Pending | HubSpot maintenance window
MNT-016 | 2026-07-08 | 3:00 | 5:00 | Infrastructure | BMC Remedy | Prod | IT | Read-Only | Jesse Garcia | Approved | Database optimization
MNT-017 | 2026-07-09 | 22:00 | 2:00 | DB Refresh | Anaplan | UAT | Finance | Full Outage | Robin Chen | Approved | Monthly UAT refresh
MNT-018 | 2026-07-10 | 1:00 | 5:00 | Patch Window | CyberArk PAM | Prod | Security | Partial | Dana Wilson | Approved | Security patches
MNT-019 | 2026-06-28 | 2:00 | 4:00 | Scheduled Outage | Plex Smart Manufacturing | Prod | Manufacturing | Full Outage | Kelly Nguyen | Completed | Completed successfully
MNT-020 | 2026-06-27 | 20:00 | 23:00 | DB Refresh | Coupa | Test | Finance | Full Outage | Terry Brooks | Completed | Completed successfully
📖 QUICK REFERENCE: Maintenance Windows (Collapsible Section for Web)
TYPES: Outage 🛑 ¦ DB Refresh 🛑 ¦ Vendor Maint ⚠️ ¦ Patch Window ⚠️
TIMING: Deploy 2+ hrs BEFORE or 1+ hr AFTER maintenance window
RULE: NEVER deploy during a scheduled outage or DB refresh
[▼ Full documentation below]
📋 PLANNED MAINTENANCE - COMPREHENSIVE GUIDE
🎯 PURPOSE OF MAINTENANCE TRACKING
This sheet tracks all planned outages, database refreshes, and vendor maintenance windows.
Coordinating releases with maintenance windows prevents conflicts and downtime.
WHY MAINTENANCE AWARENESS MATTERS:
• Deploying during a maintenance window wastes effort — system will be down
• DB refreshes may overwrite data changes from your release
• Vendor maintenance may affect integrations your release depends on
• Infrastructure patches may require application restarts
📊 MAINTENANCE TYPES
TYPE ¦ IMPACT ¦ CONFLICT
─────────────────────────────────────────────────────────────────
Scheduled Outage ¦ Full unavailability ¦ 🛑 DO NOT SCHEDULE
DB Refresh ¦ Data reset or migration ¦ 🛑 DATA WILL BE LOST
Vendor Maintenance ¦ External system unavailable ¦ ⚠️ CHECK INTEGRATIONS
Patch Window ¦ Brief restarts ¦ ⚠️ SCHEDULE AFTER
Infrastructure ¦ Network, storage changes ¦ ⚠️ VERIFY ENV STABLE
IMPACT LEVELS:
• Full Outage: System completely unavailable
• Partial: Some functions work, others don't
• Read-Only: No writes allowed, data frozen
🚦 COORDINATING RELEASES WITH MAINTENANCE
BEFORE SCHEDULING A RELEASE:
1. Filter by Application(s) Affected = your target application
2. Check Scheduled Date overlaps with your release window
3. Verify Environment(s) — is your target env affected?
4. Review Start Time and End Time — plan release outside this window
5. Check Approval Status — unapproved maintenance may be rescheduled
TIMING GUIDELINES:
• Schedule releases at least 2 hours BEFORE maintenance starts
• OR wait until 1 hour AFTER maintenance completes (allow buffer)
• DB Refresh: Wait 24 hours to verify data integrity
• Vendor Windows: Confirm integrations work post-maintenance
✅ BEST PRACTICES
1. CHECK WEEKLY: Review upcoming maintenance when planning releases
2. SUBSCRIBE TO ALERTS: Get notified when new maintenance is scheduled
3. COORDINATE EARLY: If you need a window moved, request 2+ weeks ahead
4. LEVERAGE WINDOWS: Use maintenance downtime for non-critical releases
5. VERIFY POST-MAINTENANCE: Confirm your application works after outage
6. DOCUMENT CONFLICTS: Record any release delays caused by maintenance
7. PLAN AROUND DB REFRESH: These are usually weekly — know the schedule
⚠️ IMPORTANT:
Maintenance windows are often scheduled weeks in advance.
Check this sheet BEFORE finalizing release dates to avoid conflicts.

## Releases_FS
RELEASES PAGE - FUNCTIONAL SPECIFICATION
Document Version: | 1 | Last Updated: | 2026-06-29 | Status: | Draft
TABLE OF CONTENTS
1 | Global Layout & UI Shell | Row 12
2 | Releases Data Grid | Row 35
3 | Filter System | Row 75
4 | Pagination | Row 115
5 | User Preferences & Persistence | Row 140
6 | Interactions & Behaviors | Row 165
7 | Error Handling & Accessibility | Row 195
1. GLOBAL LAYOUT & UI SHELL
1.1 TOP HEADER BAR
Component | Specification | Behavior
Application Logo | Left-aligned, fixed position, clickable | Click → Navigate to Landing Page/Dashboard
Application Name | Release Desk' text next to logo | Static display, acts as brand identifier
Search Bar | Center position, global search input | Type → Live search across releases, users, apps
Notifications Bell | Right side, icon with badge count | Click → Dropdown with recent notifications
User Avatar/Name | Right side, shows logged-in user | Click → Dropdown: Profile, Settings, Help
Logout Button | Inside user dropdown or standalone | Click → Confirm dialog → Logout → Login page
Header Height | Fixed 60px height | Always visible, sticky position on scroll
1.2 LEFT NAVIGATION PANEL
Property | Specification | Notes
Position | Fixed left side, full viewport height minus header | Remains visible during page scroll
Width (Expanded) | 240px - shows icon + label text | Default state for desktop users
Width (Collapsed) | 60px - shows icons only | Hover on icon shows tooltip with label
Toggle Control | Hamburger menu icon or << >> arrows | Click toggles expand/collapse state
State Persistence | Collapse state saved in user preferences | Remembered across sessions
Active Page Indicator | Highlight/accent color on current page | Left border accent + background highlight
Navigation Items | Dashboard, Releases, Calendar, Risks, Env Booking, Dependencies, Approvals, Admin | Icons + Labels, grouped by category
Responsive Behavior | Auto-collapse on screens < 1024px | Mobile: Overlay drawer with backdrop
2. RELEASES DATA GRID
2.1 GRID COLUMNS SPECIFICATION
Column | Data Type | Sortable | Width | Display Format
Actions | Icons | No | 120px | View, Edit, Delete icons (permission-based visibility)
2.2 Release ID Hyperlink Behavior
Property | Value
Link Target | /releases/{Release_ID} - Individual Release Detail Page
Link Style | Blue text, underline on hover, pointer cursor
Click Behavior | Single click navigates to Release Detail page
Open in New Tab | Ctrl+Click OR Middle-Click opens in new tab
Tooltip | "Click to view release details" on hover
2.3 Sorting Behavior
Property | Value
Sortable Columns | All columns marked 'Sortable=Yes' in grid spec
Sort Indicator | ▲ for ascending, ▼ for descending, next to column header
Default Sort | Start Date (Ascending) - nearest releases first
Multi-Column Sort | Shift+Click adds secondary sort column
Sort Persistence | User sort preference saved in localStorage per user
SECTION 3: FILTER SYSTEM
3.1 Filter Bar Layout
Property | Value
Position | Fixed below page header, above data grid
Background | Light gray (#F8F9FA) with 1px bottom border
Padding | 16px vertical, 24px horizontal
Collapse/Expand | Toggle icon to show/hide filter bar; state persisted
3.2 Available Filters
Filter Name | Type | Options | Default | Multi-Select
Department | Dropdown | All, Finance, Logistics, CRM, Manufacturing, IT, HR, Legal, Security | All | Yes
Application | Dropdown | All, + Dynamic list from Applications sheet | All | Yes
Status | Dropdown | All, Draft, Planning, Testing, Pending CAB, Approved, Blocked | All | Yes
Time Period | Date Range | All Time, This Week, This Month, This Quarter, Custom Range | All Time | No
Conflict | Toggle | All, Has Conflict, No Conflict | All | No
Priority | Dropdown | All, P1-Critical, P2-High, P3-Medium, P4-Low | All | Yes
3.3 Filter Configuration (Gear Icon)
Feature | Specification
Access | Gear icon at end of filter bar opens configuration panel
Show/Hide Filters | Checkbox list to enable/disable individual filters
Filter Order | Drag-and-drop to reorder visible filters
Save Configuration | Save button persists filter visibility and order per user
Reset to Default | Reset button restores system default filter configuration
3.4 Filter Actions
Action | Behavior
Apply | Auto-apply on filter change (no Apply button needed)
Clear All | "Clear Filters" button resets all filters to default, pagination to page 1
Result Count | Display "Showing X of Y releases" dynamically updated
Active Filter Indicator | Blue dot or badge on filters with non-default values
SECTION 4: PAGINATION SYSTEM
4.1 Page Size Options
Property | Value
Available Sizes | 10, 25, 50, 100 releases per page
Default Size | 25 releases per page
Size Selector | Dropdown: "Show [10/25/50/100] per page"
Size Persistence | User selection saved in localStorage
4.2 Pagination Controls
Control | Specification
First Page | «« button - jumps to page 1; disabled on page 1
Previous Page | « button - goes to previous page; disabled on page 1
Page Numbers | Show current page + 2 pages before/after (e.g., 1 2 [3] 4 5)
Ellipsis | "..." shown when pages are skipped (e.g., 1 ... 4 [5] 6 ... 10)
Next Page | » button - goes to next page; disabled on last page
Last Page | »» button - jumps to last page; disabled on last page
Jump to Page | Input field: "Go to page [__]" with Enter to navigate
4.3 Position Indicator
Element | Format
Record Range | "Showing 1-25 of 80 releases" (dynamic based on page/filters)
Page Position | "Page 1 of 4" displayed near pagination controls
Location | Bottom of data grid, aligned with pagination controls
SECTION 5: USER PREFERENCES & PERSISTENCE
5.2 Non-Persisted Settings (Session Only)
Setting | Reason
Active Filter Values | User expects fresh view on new session; filters reset to defaults
Current Page Number | Always start at page 1; data may have changed
Selected Rows | Selection is temporary; cleared on navigation/refresh
Search Query | Global search cleared on page load
SECTION 6: INTERACTIONS & BEHAVIORS
6.1 Click Actions
Element | Single Click | Ctrl+Click | Double Click
Release ID | Navigate to Release Detail page | Open Release Detail in new tab | Same as single click
Data Row | Highlight row (selection) | Add row to multi-selection | Open Release Detail page
Row Checkbox | Toggle row selection | Same as single click | Same as single click
Column Header | Sort by column (toggle asc/desc) | N/A | N/A
Action Icons | Execute action (View/Edit/Delete) | Open in new tab (View/Edit) | Same as single click
6.2 Hover States
Element | Hover Effect
Data Row | Background: #F5F5F5 (light gray), cursor: default
Release ID Link | Text: underline, cursor: pointer, tooltip appears
Action Icons | Icon: highlight/scale, tooltip shows action name
Sortable Header | Background: darker shade, cursor: pointer, sort hint tooltip
Filter Dropdowns | Border: highlight color, cursor: pointer
Pagination Buttons | Background: highlight, cursor: pointer (except disabled)
6.3 Keyboard Navigation
Key | Action
Tab | Move focus to next interactive element
Shift+Tab | Move focus to previous interactive element
Arrow Up/Down | Move selection between rows in data grid
Enter | Open Release Detail for focused/selected row
Space | Toggle checkbox for focused row
Escape | Close open dropdowns, cancel selection, close modals
Ctrl+A | Select all rows on current page
6.4 Loading States
Trigger | Loading Indicator
Initial Page Load | Full-page spinner with "Loading releases..." text
Filter Change | Grid overlay spinner, filters remain interactive
Pagination | Grid overlay spinner, pagination controls disabled
Sort Change | Brief spinner (< 200ms), or skeleton rows for longer loads
SECTION 7: ERROR HANDLING & ACCESSIBILITY
7.1 Empty States
Condition | Display
No Releases (System) | "No releases found. Create your first release." + Create button
No Filter Results | "No releases match your filters." + Clear Filters button
Search No Results | "No results for '[query]'. Try different keywords." + suggestion
7.2 Error States
Error Type | User Message | Action
Network Error | "Unable to load releases. Please check your connection." | Retry button
Server Error (500) | "Something went wrong. Our team has been notified." | Retry button, Support link
Timeout | "Request timed out. Please try again." | Retry button
Permission Denied | "You don't have permission to view this release." | Back to list, Contact Admin
7.3 Accessibility (WCAG 2.1 AA Compliance)
Requirement | Implementation
Color Contrast | Minimum 4.5:1 ratio for text, 3:1 for large text and UI components
Focus Indicators | Visible focus ring (2px solid blue) on all interactive elements
ARIA Labels | All buttons, icons, and controls have descriptive aria-label
Screen Reader | Data grid announced as table; live regions for dynamic updates
Skip Links | "Skip to main content" link at top of page for keyboard users
Responsive Text | Text scales with browser zoom up to 200% without loss of content
7.4 Responsive Design
Breakpoint | Behavior
Desktop (>1200px) | Full layout: expanded nav, all columns visible, full filter bar
Tablet (768-1199px) | Collapsed nav by default, horizontal scroll on grid, stacked filters
Mobile (<768px) | Hamburger menu for nav, card view for releases, bottom sheet for filters
--- END OF FUNCTIONAL SPECIFICATION ---
Document Version: 1.0 ¦ Last Updated: 29-Jun-2026

## Global_Components_FS
GLOBAL UI COMPONENTS - FUNCTIONAL SPECIFICATION
Version: 1.0 | Date: 29-Jun-2026 | Status: Draft | Applies To: All Pages
TABLE OF CONTENTS
Section 1: Top Header Bar | Row 10
Section 2: Left Navigation Panel | Row 35
Section 3: Page Layout Template | Row 70
Section 4: Common UI Patterns | Row 95
SECTION 1: TOP HEADER BAR (GLOBAL)
1.1 Header Structure
Property | Value
Position | Fixed top, full width, z-index: 1000
Height | 64px
Background | #FFFFFF with bottom shadow (0 2px 4px rgba(0,0,0,0.1))
Logo Position | Left side, 24px from edge, max-height 40px
App Name | "Release Desk" - 18px bold, adjacent to logo
Global Search | Center, 400px width, placeholder: "Search releases, apps, users..."
User Section | Right side: Notifications icon, User Avatar, User Name dropdown
Responsive | Search collapses to icon on tablet; hamburger menu on mobile
1.2 Header Components Detail
Component | Behavior | Click Action | Tooltip
Logo | Clickable, cursor pointer | Navigate to Dashboard/Home | "Go to Dashboard"
App Name | Static text display | N/A | N/A
Global Search | Expandable, auto-suggest | Opens search results overlay | "Search (Ctrl+K)"
Notifications Bell | Badge shows unread count (red dot) | Opens notification panel | "Notifications (X unread)"
User Avatar | Circular, 32px, initials or photo | Opens user dropdown menu | "User Menu"
User Name | Display name + dropdown arrow | Opens user dropdown menu | "Account Settings"
Logout | Inside user dropdown | Confirm dialog → Logout | "Sign out of Release Desk"
SECTION 2: LEFT NAVIGATION PANEL (GLOBAL)
2.1 Navigation Structure
Property | Value
Position | Fixed left, below header (top: 64px), full height
Width (Expanded) | 240px
Width (Collapsed) | 64px (icons only)
Background | #F8F9FA light gray
Toggle Button | Bottom of nav, chevron icon (« / »)
Collapse State | Persisted in localStorage per user
Active Item | Blue background highlight, left border indicator
Hover Effect | Light blue background on hoverable items
2.2 Navigation Items
Icon | Label | Route | Description
🏠 | Dashboard | /dashboard | Overview and metrics
📋 | Releases | /releases | Release management
📅 | Calendar | /calendar | Release calendar view
🖥️ | Env Booking | /env-booking | Environment reservations
⚠️ | Risk Factors | /risk-factors | Risk scoring model
🔄 | Drift | /drift | Configuration drift tracking
🔗 | Dependencies | /dependencies | Release dependencies
✅ | Approvals | /approvals | Approval workflows
🏖️ | Leave Calendar | /leave | Team availability
📦 | Versions | /versions | App version tracking
🗺️ | System Mapping | /system-map | Integration diagram
📊 | Monitoring | /monitoring | Alert management
🚨 | Incidents | /incidents | Incident tracking
💚 | App Status | /app-status | Application health
🔧 | Maintenance | /maintenance | Planned maintenance
⚙️ | Admin | /admin | System administration (Admin only)
❓ | Help | /help | Documentation & support
SECTION 3: PAGE LAYOUT TEMPLATE (GLOBAL)
3.1 Content Area Structure
Element | Specification
Position | Right of nav panel, below header (top: 64px, left: 240px/64px)
Padding | 24px all sides
Background | #FFFFFF
Page Title | H1, 24px bold, top-left of content area
Breadcrumb | Below title: Home > [Section] > [Page]
Action Buttons | Top-right: Primary actions (Create, Export, etc.)
Filter Bar | Below title/actions, collapsible
Main Content | Data grid, cards, or page-specific content below filters
3.2 Standard Page Sections (Top to Bottom)
Section | Height | Purpose
Page Header | Auto (~80px) | Title, breadcrumb, action buttons
Filter Bar | Auto (~60px) | Filters, search, filter toggle
Data Grid | Flex (fills remaining) | Main data table or content
Pagination | 48px fixed | Page controls, record count
Footer | Optional | Page-specific notes or help links
SECTION 4: COMMON UI PATTERNS (GLOBAL)
4.1 ID Hyperlinks (All Pages)
Property | Value
Style | Blue text (#0066CC), underline on hover
Cursor | Pointer
Single Click | Navigate to detail page
Ctrl+Click | Open in new tab
Tooltip | "Click to view [Entity] details"
Pattern | /[entity-type]/{ID} (e.g., /releases/REL-0001)
4.2 Status Badges
Status | Color | Use Case
Active | Green (#28A745) | Currently running, healthy
Pending | Yellow (#FFC107) | Awaiting action
Approved | Blue (#007BFF) | Approved/completed
Blocked | Red (#DC3545) | Blocked, critical issue
Draft | Gray (#6C757D) | Not yet submitted
Warning | Orange (#FD7E14) | Needs attention
Down | Dark Red (#721C24) | System unavailable
Investigating | Purple (#6F42C1) | Under review
4.3 Priority Indicators
Priority | Color | Icon
P1 - Critical | Red (#DC3545) | 🔴
P2 - High | Orange (#FD7E14) | 🟠
P3 - Medium | Yellow (#FFC107) | 🟡
P4 - Low | Green (#28A745) | 🟢
4.4 Confirmation Dialogs
Action Type | Dialog Title | Buttons
Delete | "Delete [Entity]?" | Cancel (gray), Delete (red)
Logout | "Sign out of Release Desk?" | Cancel, Sign Out
Discard Changes | "Unsaved changes will be lost" | Stay, Discard
Bulk Action | "Apply to X selected items?" | Cancel, Apply
Approval Decision | "Confirm [Approve/Reject]?" | Cancel, Confirm
--- END OF GLOBAL COMPONENTS SPECIFICATION ---

## Calendar_FS
CALENDAR PAGE - FUNCTIONAL SPECIFICATION
Version: 1.0 | Date: 29-Jun-2026 | Status: Draft | See: Global_Components_FS for shared UI
TABLE OF CONTENTS
Section 1: Calendar View | Row 11
Section 2: Event Display | Row 40
Section 3: Filters & Navigation | Row 65
Section 4: Interactions | Row 90
Section 5: Page-Specific Features | Row 115
SECTION 1: CALENDAR VIEW
1.1 Calendar View Modes
View Mode | Description | Default | Navigation
Month View | Standard calendar grid showing all days of month | Yes | < Prev Month ¦ Today ¦ Next Month >
Week View | 7-day horizontal view with time slots | No | < Prev Week ¦ Today ¦ Next Week >
Day View | Single day with hourly breakdown | No | < Prev Day ¦ Today ¦ Next Day >
Agenda View | Chronological list of upcoming events | No | Scroll-based navigation
Timeline View | Gantt-style horizontal timeline | No | Scroll/zoom controls
1.2 Calendar Grid Layout
Property | Value
Week Start Day | Monday (configurable in user preferences)
Day Header | Mon, Tue, Wed, Thu, Fri, Sat, Sun
Day Cell Height | Minimum 80px, expandable based on event count
Day Number Position | Top-left corner of cell
Today Highlight | Blue border, light blue background (#E6F2FF)
Weekend Styling | Light gray background (#F5F5F5)
Past Days | Slightly dimmed (opacity 0.7)
Current Month Days | Normal styling
Other Month Days | Dimmed text (gray), clickable to navigate
Holiday Indicator | Red text for day number, optional icon
Event Overflow | "+ X more" link when > 4 events
Cell Click | Opens day view or quick-add event modal
SECTION 2: EVENT DISPLAY
2.1 Event Types & Color Coding
Event Type | Color | Description
Release Go-Live | #28A745 (Green) | Scheduled release deployment
CAB Meeting | #007BFF (Blue) | Change Advisory Board meeting
UAT Start/End | #17A2B8 (Cyan) | User acceptance testing window
Testing Period | #6F42C1 (Purple) | Test environment booking
Change Freeze | #DC3545 (Red) | No deployments allowed
Maintenance Window | #FD7E14 (Orange) | Planned system maintenance
Holiday/Closure | #6C757D (Gray) | Business closure
Milestone | #E83E8C (Pink) | Project milestone/deadline
Resource Leave | #20C997 (Teal) | Key resource unavailable
2.2 Event Card Display
Property | Value
Card Height | 22px (single line) in month view
Card Content | Time (if applicable) + Event Title
Truncation | Ellipsis (...) if text exceeds width
Border Radius | 4px rounded corners
Left Border | 3px colored border indicating event type
Hover Effect | Slight elevation shadow, full title tooltip
Click Action | Opens event detail popup/modal
SECTION 3: FILTERS & NAVIGATION
3.1 Filter Options
Filter | Type | Options
Event Type | Multi-select checkboxes | All event types (see 2.1)
Department | Dropdown multi-select | All departments + "All"
Application | Dropdown multi-select | All applications + "All"
Priority | Checkbox group | P1, P2, P3, P4
Status | Checkbox group | Approved, Pending, Blocked
Date Range | Date picker range | Custom start/end dates
Owner | Search/select | User lookup with autocomplete
Show Conflicts Only | Toggle switch | On/Off
3.2 Navigation Controls
Control | Behavior
Previous Button (<) | Navigates to previous period (month/week/day)
Next Button (>) | Navigates to next period
Today Button | Jumps to current date, highlights today
Month/Year Picker | Dropdown for quick month/year selection
View Toggle | Buttons: Month ¦ Week ¦ Day ¦ Agenda ¦ Timeline
Mini Calendar | Small calendar in sidebar for quick date jumping
Keyboard: Arrow Keys | Navigate between days/weeks in grid
SECTION 4: INTERACTIONS
4.1 Event Interactions
Action | Trigger | Result
View Event Details | Click on event card | Opens event detail modal/popup
Navigate to Release | Click Release ID in detail | Navigates to Release detail page
Drag & Drop | Drag event to new date | Opens confirmation dialog to reschedule
Quick Edit | Double-click event | Opens inline edit form
Create Event | Click empty day cell | Opens "Add Event" modal
Extend Duration | Drag event edge | Adjusts end date (with validation)
Copy Event | Ctrl+C then Ctrl+V | Creates duplicate event on target date
Delete Event | Right-click > Delete | Shows confirmation dialog
4.2 Conflict Detection & Indicators
Conflict Type | Visual Indicator
Environment Overlap | Red warning icon on both events
Resource Conflict | Orange warning icon with tooltip
Change Freeze Violation | Red striped background on event
Dependency Conflict | Chain icon with red exclamation
Multiple Conflicts | Stacked warning icons, count badge
Conflict Tooltip | Hover shows: "Conflicts with: [Release IDs]"
SECTION 5: PAGE-SPECIFIC FEATURES
5.1 Legend Panel
Property | Value
Position | Top-right or collapsible sidebar
Content | Color swatches with event type labels
Toggle Visibility | Click legend item to show/hide event type
Collapsed State | "Show Legend" button
Persistence | User preference for collapsed/expanded
5.2 Export & Print Options
Action | Details
Export to iCal | Downloads .ics file with filtered events
Export to PDF | Prints current view as PDF document
Subscribe to Feed | Generates iCal subscription URL
Print View | Print-optimized layout, optional date range
Share Calendar Link | Copy URL with current filters applied
5.3 Accessibility (Calendar-Specific)
Requirement | Implementation
Keyboard Navigation | Arrow keys move focus between days; Enter opens day
Screen Reader | Announce: "June 29, 2026, 3 events"
Focus Indicator | Clear visible border on focused day/event
Skip to Today | Shortcut key (T) jumps to today
Event Announcements | Read event title, time, type on focus
--- END OF CALENDAR PAGE SPECIFICATION ---

## EnvBooking_FS
ENVIRONMENT BOOKING PAGE - FUNCTIONAL SPECIFICATION
Version: 1.0 | Date: 29-Jun-2026 | Status: Draft | See: Global_Components_FS for shared UI
TABLE OF CONTENTS
Section 1: Booking Grid | Row 12
Section 2: Timeline/Gantt View | Row 50
Section 3: Conflict Detection | Row 80
Section 4: Filters & Search | Row 110
Section 5: Booking Actions | Row 135
Section 6: Notifications | Row 160
SECTION 1: BOOKING GRID
1.1 Data Grid Columns
Column | Type | Sortable | Filterable | Description
Booking ID | Hyperlink | Yes | Yes | Unique booking identifier (BK-XXXX)
Release ID | Hyperlink | Yes | Yes | Linked release (REL-XXXX)
Application | Text | Yes | Dropdown | Target application name
Department | Text | Yes | Dropdown | Owning department
Release Size | Badge | Yes | Dropdown | Small, Medium, Large, X-Large
Test Env | Text | Yes | Dropdown | Test environment code
Test Start | Date | Yes | Date Range | Test period start date
Test End | Date | Yes | Date Range | Test period end date
UAT Env | Text | Yes | Dropdown | UAT environment code
UAT Start | Date | Yes | Date Range | UAT period start date
UAT End | Date | Yes | Date Range | UAT period end date
Pre-Prod Env | Text | Yes | Dropdown | Pre-production environment
Pre-Prod Start | Date | Yes | Date Range | Pre-prod start date
Pre-Prod End | Date | Yes | Date Range | Pre-prod end date
Status | Badge | Yes | Dropdown | Confirmed, Pending, Cancelled
Conflict Flag | Icon | Yes | Toggle | ⚠️ if conflict exists
Owner | User | Yes | User Search | Booking owner
Notes | Text (truncated) | No | Text Search | Additional notes
1.2 Grid Behaviors
Feature | Specification
Default Sort | Test Start Date (ascending)
Row Selection | Checkbox for bulk actions
Row Hover | Light highlight, quick action icons appear
Row Click | Opens booking detail side panel
Double Click | Opens edit booking modal
Conflict Row Styling | Light red background, ⚠️ icon
Expired Booking | Grayed out text, strikethrough
Today's Bookings | Blue left border indicator
Pagination | 10, 25, 50, 100 per page (default: 25)
SECTION 2: TIMELINE / GANTT VIEW
2.1 Timeline Layout
Property | Specification
Y-Axis (Rows) | Environment names (grouped by type: Test, UAT, Pre-Prod)
X-Axis (Columns) | Date timeline with day/week/month granularity
Bar Display | Horizontal bars representing booking periods
Bar Height | 20px per booking, stacked if multiple per env/day
Bar Color | By department (color-coded legend)
Bar Label | Release ID displayed on bar (if space permits)
Today Line | Vertical red dashed line for current date
Weekend Shading | Light gray columns for Sat/Sun
Holiday Shading | Light red columns for holidays
Zoom Levels | Day ¦ Week ¦ Month view toggles
Scroll Behavior | Horizontal scroll with sticky left column (env names)
View Toggle | Grid View ↔ Timeline View button
2.2 Timeline Interactions
Action | Trigger | Result
View Booking | Click bar | Opens booking detail popup
Extend Booking | Drag bar edge | Adjusts end date with validation
Move Booking | Drag entire bar | Moves to new date range (validation)
Create Booking | Click+drag on empty area | Opens new booking modal with dates pre-filled
Hover Bar | Mouse over | Shows tooltip: Release, Owner, Dates
Navigate to Release | Ctrl+Click bar | Opens release detail in new tab
Conflict Warning | Overlapping bars | Red border on both bars, tooltip shows conflict
Zoom In/Out | Mouse wheel + Ctrl | Changes timeline granularity
SECTION 3: CONFLICT DETECTION
3.1 Conflict Types
Conflict Type | Detection Rule | Visual Indicator
Environment Overlap | Same environment booked for overlapping dates | ⚠️ icon, red background
Resource Conflict | Same owner has overlapping bookings | 🔄 icon, orange background
Dependency Conflict | Dependent release env booked in wrong sequence | 🔗 icon, yellow background
Change Freeze Violation | Booking during declared change freeze | 🚫 icon, striped red background
Capacity Exceeded | Environment max concurrent bookings exceeded | 📊 icon, purple indicator
Maintenance Overlap | Booking during planned maintenance window | 🔧 icon, gray striped
Holiday Booking | Booking spans business closure date | 📅 icon, info warning
3.2 Conflict Resolution Workflow
Step | Action
1 | System detects conflict on save/create
2 | Warning dialog shows conflicting bookings
3a | User can adjust dates to resolve
3b | User can request override (requires approval)
3c | User can contact conflicting owner (email link)
4 | Override requests go to Environment Admin queue
5 | Admin approves/rejects with comments
6 | Both parties notified of resolution
7 | Conflict flag cleared upon resolution
SECTION 4: FILTERS & SEARCH
4.1 Filter Options
Filter | Type | Default
Environment Type | Checkbox group | All selected
Environment Name | Multi-select dropdown | All
Department | Multi-select dropdown | All
Application | Multi-select dropdown | All
Date Range | Date picker (From - To) | Current month
Status | Checkbox group | All except Cancelled
Conflict Status | Toggle: Show conflicts only | Off
My Bookings | Toggle: Show my bookings only | Off
Release Size | Checkbox group | All
Owner | User search autocomplete | Any
Search | Text input | Searches ID, Release, Notes
SECTION 5: BOOKING ACTIONS
5.1 Available Actions
Action | Access | Description
New Booking | Toolbar button | Opens create booking modal
Edit Booking | Row action / double-click | Opens edit modal (owner/admin only)
Cancel Booking | Row action | Marks as cancelled with reason
Clone Booking | Row action | Creates copy with new dates
Extend Booking | Row action | Adjusts end date only
Transfer Booking | Row action | Assigns to different release
Request Override | Conflict dialog | Requests admin approval for conflict
Export Selected | Bulk action | Exports selected rows to CSV
Bulk Cancel | Bulk action (admin) | Cancels multiple selected bookings
View History | Row action | Shows audit log for booking
Send Reminder | Row action | Sends email reminder to owner
SECTION 6: NOTIFICATIONS & ALERTS
6.1 Notification Triggers
Event | Recipients | Channel
Booking Created | Owner, Env Admin | Email, In-app
Booking Modified | Owner, Impacted parties | Email, In-app
Booking Cancelled | Owner, Dependent releases | Email, In-app
Conflict Detected | Both booking owners | Email, In-app (urgent)
Conflict Resolved | Both parties, Admin | Email, In-app
Booking Starting Soon | Owner (T-2 days) | Email reminder
Booking Expired | Owner (auto) | In-app only
Override Requested | Env Admin queue | Email, In-app (urgent)
Override Decision | Requester | Email, In-app
Environment Maintenance | All booked users | Email (advance notice)
--- END OF ENVIRONMENT BOOKING PAGE SPECIFICATION ---

## RiskFactors_FS
RISK FACTORS PAGE - FUNCTIONAL SPECIFICATION
Version: 1.0 | Date: 29-Jun-2026 | Status: Draft | See: Global_Components_FS for shared UI
TABLE OF CONTENTS
Section 1: Risk Scoring Model | Row 11
Section 2: Risk Factor Definitions | Row 45
Section 3: Risk Dashboard View | Row 95
Section 4: Risk Management Actions | Row 130
Section 5: Alerts & Thresholds | Row 155
SECTION 1: RISK SCORING MODEL
1.1 Scoring Overview
Property | Value
Score Range | 0 - 100 points (calculated)
Calculation | Sum of (Factor Score × Weight) across all factors
Auto-Refresh | Real-time recalculation on data change
Display Format | Numeric score + color-coded badge
Decimal Precision | 1 decimal place (e.g., 72.5)
History Tracking | Score snapshots saved at each status change
Trend Indicator | ↑ ↓ → showing score change from last week
1.2 Risk Score Thresholds
Score Range | Level | Color | Action Required
0 - 25 | Low Risk | Green (#28A745) | Standard approval process
26 - 50 | Medium Risk | Yellow (#FFC107) | Additional review recommended
51 - 75 | High Risk | Orange (#FD7E14) | Manager approval required
76 - 90 | Critical Risk | Red (#DC3545) | Executive approval required
91 - 100 | Extreme Risk | Dark Red (#721C24) | Release may be blocked
1.3 Factor Weight Distribution
Category | Weight % | Factors Included
Release Complexity | 25% | Size, Dependencies, New Tech
Resource Factors | 20% | Team Experience, Key Person Risk, Leave
Environment Factors | 15% | Env Conflicts, Test Coverage, UAT
Timing Factors | 20% | Change Freeze, Holiday, End-of-Quarter
Historical Factors | 10% | Past Incidents, Rollback History
Business Impact | 10% | Revenue, Customer, Regulatory Impact
SECTION 2: RISK FACTOR DEFINITIONS
2.1 Release Complexity Factors
Factor | Values | Points | Weight
Release Size | Small / Medium / Large / X-Large | 1 / 3 / 6 / 10 | 8%
Dependencies Count | 0 / 1-2 / 3-5 / 6+ | 0 / 2 / 5 / 10 | 7%
New Technology | No / Minor / Significant / Major | 0 / 3 / 6 / 10 | 5%
Integration Points | 0-1 / 2-3 / 4-5 / 6+ | 1 / 3 / 6 / 10 | 5%
2.2 Resource Factors
Factor | Values | Points | Weight
Team Experience | Expert / Experienced / Moderate / New | 0 / 2 / 5 / 10 | 7%
Key Person Risk | None / Low / Medium / High | 0 / 2 / 5 / 10 | 6%
Leave Overlap | None / 1 person / 2+ / Lead absent | 0 / 3 / 6 / 10 | 4%
Resource Availability | Full / 75%+ / 50-75% / <50% | 0 / 2 / 5 / 10 | 3%
2.3 Environment Factors
Factor | Values | Points | Weight
Environment Conflicts | None / 1 / 2+ / Unresolved | 0 / 3 / 6 / 10 | 5%
Test Coverage | >90% / 70-90% / 50-70% / <50% | 0 / 2 / 5 / 10 | 5%
UAT Completion | Complete / 75%+ / 50-75% / <50% | 0 / 2 / 5 / 10 | 5%
2.4 Timing Factors
Factor | Values | Points | Weight
Change Freeze Proximity | None / 7+ days / 3-7 days / <3 days | 0 / 2 / 5 / 10 | 6%
Holiday Proximity | None / 7+ days / 3-7 days / Adjacent | 0 / 2 / 4 / 8 | 5%
End-of-Period | Normal / Month-end / Quarter-end / Year-end | 0 / 3 / 6 / 10 | 5%
Peak Business Period | No / Low / Medium / High | 0 / 2 / 5 / 10 | 4%
2.5 Historical Factors
Factor | Values | Points | Weight
Past Incidents (12mo) | 0 / 1 / 2 / 3+ | 0 / 3 / 6 / 10 | 5%
Rollback History | 0 / 1 / 2+ | 0 / 4 / 10 | 5%
2.6 Business Impact Factors
Factor | Values | Points | Weight
Revenue Impact | None / Low / Medium / High | 0 / 2 / 5 / 10 | 4%
Customer Impact | Internal / Low / Medium / High | 0 / 2 / 5 / 10 | 3%
Regulatory Impact | None / Audit / Compliance / Legal | 0 / 3 / 6 / 10 | 3%
SECTION 3: RISK DASHBOARD VIEW
3.1 Dashboard Layout Components
Component | Position | Content
Risk Summary Card | Top-left | Total releases by risk level (counts + %)
Risk Score Distribution | Top-center | Histogram of all release scores
Trend Chart | Top-right | 7/30/90 day trend of avg risk score
High Risk Releases | Middle | Table of releases with score > 75
Factor Breakdown | Middle-right | Pie chart of contributing factors
Risk Heatmap | Bottom-left | Dept × Priority heatmap
Upcoming High Risk | Bottom-center | Next 14 days high-risk releases
Risk Alerts | Bottom-right | Active alerts and warnings
3.2 Release Risk Grid
Column | Type | Sortable | Description
Release ID | Hyperlink | Yes | Link to release detail
Release Name | Text | Yes | Release title
Risk Score | Number + Badge | Yes | 0-100 score with color
Risk Level | Badge | Yes | Low/Medium/High/Critical
Top Risk Factor | Text | Yes | Highest contributing factor
Department | Text | Yes | Owning department
Go-Live Date | Date | Yes | Scheduled deployment date
Days to Go-Live | Number | Yes | Countdown (negative if past)
Trend | Icon | Yes | ↑↓→ change from last calc
Actions | Buttons | No | View Details, Mitigate
SECTION 4: RISK MANAGEMENT ACTIONS
4.1 Available Actions
Action | Access | Description
View Risk Breakdown | Any user | See detailed factor scores
Add Mitigation Note | Owner/Admin | Document mitigation steps taken
Request Override | Owner | Request exception for high-risk
Override Risk Factor | Admin | Manually adjust factor value
Recalculate Score | Any user | Force refresh of score
Set Risk Watch | Any user | Get alerts when score changes
Export Risk Report | Any user | PDF/Excel of risk details
Compare Releases | Any user | Side-by-side risk comparison
View Risk History | Any user | Historical score changes
Configure Weights | Admin only | Adjust factor weights
SECTION 5: ALERTS & THRESHOLDS
5.1 Automatic Alerts
Trigger | Recipients | Channel
Score crosses into High (>50) | Owner, Manager | Email, In-app
Score crosses into Critical (>75) | Owner, Manager, Exec | Email (urgent), In-app
Score increases by >10 points | Owner | In-app notification
New Extreme Risk (>90) | All stakeholders | Email (urgent), Teams
Risk factor manually overridden | Audit log, Admin | Audit trail
7 days to go-live with High risk | Owner, Manager | Email reminder
3 days to go-live with Critical | Exec sponsor | Email escalation
Score decreased (good news) | Owner | In-app (positive)
--- END OF RISK FACTORS PAGE SPECIFICATION ---

## Drift_FS
CONFIGURATION DRIFT PAGE - FUNCTIONAL SPECIFICATION
Version: 1.0 | Date: 29-Jun-2026 | Status: Draft | See: Global_Components_FS
SECTION 1: DRIFT DATA GRID
1.1 Grid Columns
Column | Type | Sortable | Description
Drift ID | Hyperlink | Yes | Unique identifier (DRIFT-XXXX)
Detected Date | Date/Time | Yes | When drift was detected
Application | Text | Yes | Affected application
Environment | Text | Yes | Test/UAT/Prod environment
Component | Text | Yes | Specific config component
Drift Type | Badge | Yes | Schema/Config/Code/Data
Severity | Badge | Yes | Low/Medium/High/Critical
Expected Value | Text (code) | No | What should be configured
Actual Value | Text (code) | No | Current configuration
Variance | Text | No | Diff description
Status | Badge | Yes | Open/Investigating/Resolved/Ignored
Assigned To | User | Yes | Owner of remediation
Last Updated | Date/Time | Yes | Most recent activity
Actions | Buttons | No | View, Remediate, Ignore
1.2 Severity Definitions
Severity | Color | Criteria
Critical | Red (#DC3545) | Security risk, production-impacting, compliance violation
High | Orange (#FD7E14) | May cause issues, performance impact, data integrity
Medium | Yellow (#FFC107) | Non-critical config, minor functionality impact
Low | Green (#28A745) | Cosmetic, documentation, non-functional
SECTION 2: DRIFT DETECTION
2.1 Detection Methods
Method | Description
Scheduled Scan | Daily/weekly automated config comparison
Post-Deployment | Auto-scan triggered after any deployment
Manual Scan | User-initiated scan for specific environment
Baseline Comparison | Compare against golden config baseline
Cross-Env Comparison | Compare config between environments
Real-time Monitoring | Webhook alerts for config changes
SECTION 3: REMEDIATION WORKFLOW
3.1 Remediation Actions
Action | Access | Result
Auto-Remediate | Admin | System applies expected value automatically
Manual Fix | Owner | Mark as fixing manually, update status
Create Ticket | Any | Generate Jira/ServiceNow ticket
Ignore (with reason) | Admin | Mark as acceptable variance
Update Baseline | Admin | Accept current as new baseline
Escalate | Any | Notify manager/security team
View Diff | Any | Side-by-side config comparison
View History | Any | Timeline of drift changes
--- END OF DRIFT PAGE SPECIFICATION ---

## Dependencies_FS
DEPENDENCIES PAGE - FUNCTIONAL SPECIFICATION
Version: 1.0 | Date: 29-Jun-2026 | Status: Draft | See: Global_Components_FS
SECTION 1: DEPENDENCY DATA GRID
1.1 Grid Columns
Column | Type | Sortable | Description
Dependency ID | Text | Yes | Unique identifier (DEP-XXXX)
Release ID | Hyperlink | Yes | The dependent release
Release Name | Text | Yes | Dependent release name
Depends On ID | Hyperlink | Yes | The prerequisite release
Depends On Name | Text | Yes | Prerequisite release name
Dependency Type | Badge | Yes | Hard/Soft/Optional
Status | Badge | Yes | Pending/Satisfied/Blocked/Broken
Impact if Blocked | Badge | Yes | Low/Medium/High/Critical
Notes | Text | No | Additional details
Actions | Buttons | No | View Chain, Edit, Remove
1.2 Dependency Types
Type | Color | Behavior
Hard | Red (#DC3545) | Blocks release if unsatisfied; cannot proceed
Soft | Yellow (#FFC107) | Warning only; release can proceed with risk
Optional | Gray (#6C757D) | Informational; no blocking behavior
SECTION 2: DEPENDENCY VISUALIZATION
2.1 Dependency Graph/Tree View
Feature | Description
View Toggle | Grid View ↔ Graph View button
Graph Layout | Directed acyclic graph (DAG) showing dependencies
Node Display | Release ID + Name + Status badge
Edge Style | Arrows from dependent → prerequisite
Edge Color | Hard=Red, Soft=Yellow, Optional=Gray
Blocked Path | Red dashed line for broken chain
Node Click | Opens release detail panel
Zoom/Pan | Mouse wheel zoom, drag to pan
Filter by Release | Show only dependencies for selected release
Export Graph | PNG/SVG export of visualization
SECTION 3: IMPACT ANALYSIS
3.1 Impact Analysis Features
Feature | Description
Upstream Analysis | Shows all releases that THIS release depends on
Downstream Analysis | Shows all releases that depend on THIS release
Critical Path | Highlights the longest dependency chain
Circular Detection | Alerts if circular dependency detected
What-If Analysis | Simulate: "If REL-001 is delayed, what's impacted?"
Cascade Alert | Notify all downstream owners if blocker occurs
Dependency Score | Risk score based on chain length/complexity
Timeline View | Gantt showing dependent releases in sequence
--- END OF DEPENDENCIES PAGE SPECIFICATION ---

## Approvals_FS
APPROVALS PAGE - FUNCTIONAL SPECIFICATION
Version: 1.0 | Date: 29-Jun-2026 | Status: Draft | See: Global_Components_FS
SECTION 1: APPROVAL QUEUE GRID
1.1 Grid Columns
Column | Type | Sortable | Description
Approval ID | Text | Yes | Unique identifier (APR-XXXX)
Release ID | Hyperlink | Yes | Related release
Release Name | Text | Yes | Release title
Approval Type | Badge | Yes | CAB/Manager/Technical/Security
Approver | User | Yes | Assigned approver name
Approver Role | Text | Yes | Role/title of approver
Submitted Date | Date/Time | Yes | When submitted for approval
Due Date | Date | Yes | Approval deadline
Decision Date | Date/Time | Yes | When decision was made
Decision | Badge | Yes | Pending/Approved/Rejected/Deferred
Comments | Text | No | Approver comments
CAB Meeting ID | Hyperlink | Yes | Associated CAB meeting
Days Pending | Number | Yes | Days awaiting decision
Actions | Buttons | No | Approve, Reject, Defer, View
1.2 Approval Types & Workflows
Type | Approvers | Trigger
CAB Approval | CAB members | Releases requiring change board review
Manager Approval | Department manager | High/Critical risk releases
Technical Review | Tech lead/Architect | Complex technical changes
Security Review | Security team | Security-impacting changes
Executive Approval | VP/Director | Critical risk or major impact
Emergency Approval | On-call manager | Urgent/hotfix releases
SECTION 2: DECISION WORKFLOW
2.1 Decision Actions
Action | Effect | Requirements
Approve | Release proceeds to next stage | Optional comment
Approve with Conditions | Approved but conditions must be met | Mandatory conditions list
Reject | Release blocked, requires rework | Mandatory rejection reason
Defer | Decision postponed to future CAB | New target date required
Request Info | Holds decision pending info | Questions sent to submitter
Delegate | Reassign to another approver | Select new approver
Escalate | Push to higher authority | Escalation reason
SECTION 3: CAB MEETING INTEGRATION
3.1 CAB Features
Feature | Description
CAB Agenda | Auto-generated agenda from pending approvals
Meeting Calendar | Link to CAB meeting schedule
Batch Decisions | Approve/reject multiple items in meeting
Meeting Notes | Record discussion points per item
Quorum Tracking | Ensure required attendees present
Voting System | Record individual votes if needed
Meeting Minutes | Auto-generate minutes from decisions
Attendance Log | Track who participated in each meeting
--- END OF APPROVALS PAGE SPECIFICATION ---

## LeaveCalendar_FS
LEAVE CALENDAR PAGE - FUNCTIONAL SPECIFICATION
Version: 1.0 | Date: 29-Jun-2026 | Status: Draft | See: Global_Components_FS
SECTION 1: LEAVE DATA GRID
1.1 Grid Columns
Column | Type | Sortable | Description
Leave ID | Text | Yes | Unique identifier (LV-XXXX)
User ID | Hyperlink | Yes | Link to user profile
User Name | Text | Yes | Full name of resource
Department | Text | Yes | User's department
Leave Type | Badge | Yes | PTO/Sick/WFH/Training/Holiday
Start Date | Date | Yes | Leave start date
End Date | Date | Yes | Leave end date
Duration (Days) | Number | Yes | Total business days
Status | Badge | Yes | Approved/Pending/Rejected
Impacted Releases | Count/Link | Yes | Releases during leave period
Risk Flag | Icon | Yes | ⚠️ if impacts critical release
Notes | Text | No | Leave notes/reason
SECTION 2: CALENDAR VISUALIZATION
2.1 Resource Calendar View
Feature | Description
Y-Axis | Resource names (grouped by department)
X-Axis | Date timeline (day/week/month)
Leave Bars | Horizontal bars showing leave periods
Color Coding | By leave type (PTO=Blue, Sick=Red, WFH=Green)
Today Line | Vertical marker for current date
Release Overlay | Optional: show release dates in same view
Conflict Highlight | Red border when leave overlaps release owner
Filter by Dept | Show only specific department resources
SECTION 3: RELEASE RISK IMPACT
3.1 Risk Assessment
Feature | Description
Auto-Detection | Flags when release owner is on leave during release
Key Person Alert | Extra flag for critical/lead resources
Coverage Check | Warns if no backup assigned during leave
Impact Score | Adds to release risk score calculation
Suggested Actions | Recommend backup assignment or reschedule
Notification | Alert release owner of team leave overlap
Dashboard Widget | Shows leaves impacting upcoming releases
Report Export | Resource availability report by date range
--- END OF LEAVE CALENDAR PAGE SPECIFICATION ---

## Versions_FS
VERSION MANAGEMENT PAGE - FUNCTIONAL SPECIFICATION
Version: 1.0 | Date: 29-Jun-2026 | Status: Draft | See: Global_Components_FS
SECTION 1: VERSION TRACKING GRID
1.1 Grid Columns
Column | Type | Sortable | Description
Application | Hyperlink | Yes | Link to application detail
Dev Version | Text | Yes | Current version in Dev env
Test Version | Text | Yes | Current version in Test env
UAT Version | Text | Yes | Current version in UAT env
Pre-Prod Version | Text | Yes | Current version in Pre-Prod
Prod Version | Text | Yes | Current version in Production
Last Deployed | Date/Time | Yes | Most recent deployment
Deploy Status | Badge | Yes | Synced/Drift/Pending
Next Release | Hyperlink | Yes | Upcoming release ID
Owner | User | Yes | Application owner
Health | Icon | Yes | 🟢/🟡/🔴 status indicator
SECTION 2: VERSION COMPARISON & DRIFT
2.1 Drift Detection
Feature | Description
Version Mismatch Alert | Highlights when env versions don't match expected
Expected Flow | Dev → Test → UAT → Pre-Prod → Prod sequence
Skip Detection | Warns if version skips an environment
Rollback Detection | Alerts if Prod version is older than lower env
Sync Status | Shows which envs are in sync
Time Since Deploy | Days since last deployment to each env
Pending Releases | Count of releases waiting to deploy
SECTION 3: DEPLOYMENT HISTORY
3.1 History Features
Feature | Description
Deployment Log | Full history of all deployments per app
Version Timeline | Visual timeline of version changes
Compare Versions | Diff between any two versions
Rollback History | Track of rollbacks with reasons
Deploy Duration | Time taken for each deployment
Success Rate | % of successful deployments
Filter by Date | View history for specific date range
Export History | CSV export of deployment log
--- END OF VERSION MANAGEMENT PAGE SPECIFICATION ---

## SystemMapping_FS
SYSTEM MAPPING PAGE - FUNCTIONAL SPECIFICATION
Version: 1.0 | Date: 29-Jun-2026 | Status: Draft | See: Global_Components_FS
SECTION 1: INTEGRATION DIAGRAM VIEW
1.1 Diagram Features
Feature | Description
Diagram Type | Interactive network graph of system integrations
Node: Application | Circles representing each application
Node Size | Based on number of integrations
Node Color | By department or status (healthy/warning/down)
Edge: Integration | Lines connecting integrated systems
Edge Direction | Arrows showing data flow direction
Edge Label | Integration type (API, File, DB, Message)
Edge Weight | Line thickness = data volume/frequency
Cluster View | Group by department or integration type
Zoom/Pan | Mouse controls for navigation
Search | Find and highlight specific system
Filter | Show/hide by dept, status, or integration type
Layout Options | Hierarchical, Force-directed, Circular
Export | PNG/SVG/PDF export of diagram
SECTION 2: NODE INTERACTIONS
2.1 Node Click/Hover Actions
Action | Trigger | Result
View Details | Click node | Side panel shows system info
Highlight Connections | Hover node | Connected systems highlighted
Expand/Collapse | Double-click | Show/hide connected nodes
Navigate to App | Ctrl+Click | Opens application detail page
Show Impact | Right-click > Impact | Highlights downstream systems
View Releases | Right-click > Releases | Shows releases affecting system
Check Status | Right-click > Status | Real-time health check
Add Integration | Right-click > Add | Opens add integration modal
SECTION 3: IMPACT ANALYSIS
3.1 Impact Analysis Features
Feature | Description
What-If Mode | Simulate system outage and see affected systems
Cascade Visualization | Animated propagation of impact
Critical Path | Identify single points of failure
Dependency Depth | Show N-levels of dependencies
Impact Score | Calculate business impact rating
Affected Releases | List releases impacted by change
Notification List | Show who needs to be notified
Export Impact Report | PDF summary of impact analysis
--- END OF SYSTEM MAPPING PAGE SPECIFICATION ---

## Monitoring_FS
MONITORING ALERTS PAGE - FUNCTIONAL SPECIFICATION
Version: 1.0 | Date: 29-Jun-2026 | Status: Draft | See: Global_Components_FS
SECTION 1: ALERT DATA GRID
1.1 Grid Columns
Column | Type | Sortable | Description
Alert ID | Text | Yes | Unique identifier (ALT-XXXX)
Timestamp | Date/Time | Yes | When alert was triggered
Application | Hyperlink | Yes | Affected application
Environment | Badge | Yes | Dev/Test/UAT/Prod
Alert Type | Badge | Yes | Performance/Error/Security/Availability
Severity | Badge | Yes | P1/P2/P3/P4
Metric | Text | Yes | What was measured
Threshold | Number | Yes | Configured threshold value
Current Value | Number | Yes | Actual value at alert time
Status | Badge | Yes | Active/Acknowledged/Resolved/Silenced
Assigned To | User | Yes | Owner of resolution
Duration | Time | Yes | How long alert has been active
Related Release | Hyperlink | Yes | If triggered by deployment
Actions | Buttons | No | Ack, Resolve, Silence, View
SECTION 2: ALERT ACTIONS & WORKFLOW
2.1 Alert Actions
Action | Effect | Requirements
Acknowledge | Marks alert as being worked on | Assigns to current user
Resolve | Closes alert as fixed | Resolution notes required
Silence | Mutes alert for duration | Duration + reason required
Escalate | Pushes to on-call/manager | Escalation reason required
Create Incident | Creates incident record | Pre-fills from alert data
Link to Release | Associates with deployment | Select release from list
Add Note | Records investigation notes | Timestamp auto-added
View History | Shows alert timeline | Read-only view
SECTION 3: MONITORING DASHBOARD
3.1 Dashboard Components
Component | Content
Alert Summary | Active alerts by severity (P1: 2, P2: 5, etc.)
Trend Chart | Alert volume over past 24h/7d/30d
Top Affected Apps | Applications with most alerts
Alert Heatmap | Time of day × day of week alert frequency
SLA Compliance | % of alerts resolved within SLA
On-Call Status | Current on-call roster and availability
Recent Activity | Live feed of alert state changes
Noise Metrics | False positive rate, silence frequency
--- END OF MONITORING ALERTS PAGE SPECIFICATION ---

## Incidents_FS
INCIDENTS PAGE - FUNCTIONAL SPECIFICATION
Version: 1.0 | Date: 29-Jun-2026 | Status: Draft | See: Global_Components_FS
SECTION 1: INCIDENT DATA GRID
1.1 Grid Columns
Column | Type | Sortable | Description
Incident ID | Hyperlink | Yes | Unique identifier (INC-XXXX)
Created | Date/Time | Yes | When incident was created
Application | Hyperlink | Yes | Affected application
Environment | Badge | Yes | Impacted environment
Severity | Badge | Yes | P1-Critical to P4-Low
Title | Text | Yes | Incident summary title
Status | Badge | Yes | Open/Investigating/Resolved/Closed
Impact | Text | Yes | Business impact description
Assigned To | User | Yes | Current owner
Related Release | Hyperlink | Yes | Release that caused incident
Duration | Time | Yes | Time open (or time to resolve)
RCA Status | Badge | Yes | Pending/In Progress/Complete
Customers Affected | Number | Yes | Count of impacted customers
Updates | Count | Yes | Number of status updates
Actions | Buttons | No | View, Update, Resolve, RCA
1.2 Severity Levels
Severity | Color | SLA Response | SLA Resolve
P1 - Critical | Red (#FF0000) | 15 minutes | 4 hours
P2 - High | Orange (#FF6600) | 30 minutes | 8 hours
P3 - Medium | Yellow (#FFD700) | 2 hours | 24 hours
P4 - Low | Blue (#4472C4) | 8 hours | 5 business days
1.3 Status Workflow
Status | Color | Next Status | Required Action
Open | Red | Investigating | Assign owner and acknowledge
Investigating | Orange | Mitigating/Resolved | Identify root cause
Mitigating | Yellow | Resolved | Apply temporary fix
Resolved | Green | Closed | Confirm service restored
Closed | Gray | - | RCA complete (if required)
SECTION 2: FILTER OPTIONS
Filter | Type | Options | Default
Status | Multi-select | Open, Investigating, Mitigating, Resolved, Closed | Open, Investigating, Mitigating
Severity | Multi-select | P1, P2, P3, P4 | All
Application | Dropdown | From Applications list | All
Environment | Multi-select | PROD, UAT, TEST, DEV | PROD
Assigned To | User Picker | Active users | All
Date Range | Date Picker | Custom, Today, Last 7/30/90 days | Last 30 days
RCA Status | Multi-select | Pending, In Progress, Complete, N/A | All
Related Release | Dropdown | Release IDs | All